## Summary
Sisa Hari Kerja |  | 8
Update Progress Summary Per PIC
Team 1&3 Development
No | Status | PIC | [5 empty] | PIC | % Task Complete | % Task Open
|  | Agung Saputra | Teddy Juanda | Komang Tri | Suryana | Haeriah | Hafidz | Agung Saputra | 68.88% | 4.149%
1 | Open | 10 | 10 | 1 | 16 | 15 | 0 | Teddy Juanda | 82.75% | 1.938%
2 | In Progress | 0 | 0 | 0 | 5 | 0 | 0 | Komang Tri | 93.4% | 0.3472%
3 | Closed | 43 | 8 | 0 | 23 | 23 | 0 | Suryana Saputra | 86.45% | 3.738%
4 | Need Review | 0 | 18 | 17 | 8 | 0 | 0 | Siti Haeriah | 86.13% | 4.335%
5 | In Testing | 0 | 0 | 0 | 0 | 0 | 0 | Hafidz Bachtiar | 0% | 0%
6 | Re Testing | 0 | 12 | 0 | 0 | 0 | 0
7 | Ready To Production | 11 | 34 | 0 | 4 | 0 | 0
8 | V&V | 0 | 0 | 0 | 0 | 0 | 0
9 | Complete | 166 | 427 | 269 | 370 | 298 | 228
10 | On Hold | 11 | 7 | 1 | 2 | 10 | 0
TOTAL Task |  | 241 | 516 | 288 | 428 | 346 | 228
Progress Proejct Charter
https://docs.google.com/spreadsheets/d/1QYZuol0V7mZKK78ngu4fFG8v_mA-7nG2/edit?gid=608938671#gid=608938671
All Pic
Total Task Open |  | 52 | 2.859% | Percentage Dari Task Open
Total Task Complete |  | 1530 | 84.11% | Percentage Dari Task Complete
Total Task All |  | 1819
4595300%
4596100%

## Task Priority
|  | New Timeline Project Charter 2025 - Priority 3 Month | [5 empty] | 1 |  | JUNI |  |  |  | JULI |  |  |  | AGUSTUS
WBS | Department | Project | Task | PIC | Start Date | End Date | Status | Percentage (%) | Keterangan | Week 1 | Week 2 | Week 3 | Week 4 | Week 12 | Week 23 | Week 34 | Week 45 | Week 16 | Week 27 | Week 38 | Week 49 | Closed Task
1 | ACC | Limit kredit pelanggan | Limit kredit pelanggan | Agung Saputra | 4539700% | 4550400% | Completed | 100% | Wating Data Limit Per Pelanggan AR | [12 empty] | Juli
1.1 | ACC | Limit kredit pelanggan | Pengerjaan Task | Agung Saputra | 4583900% | 4584700% | Completed | 100% | Wating Data Limit Per Pelanggan AR | [12 empty] | Juli
1.2 | ACC | Limit kredit pelanggan | Testing QA | Sigit Suntoro | 4585000% | 4585700% | Completed | 100% | Wating Data Limit Per Pelanggan AR | [12 empty] | Juli
1.3 | ACC | Limit kredit pelanggan | Dokumentasi Technical Writer | Reno Rimawan | 4585900% | 4586700% | Not Started | 0% | Wating Data Limit Per Pelanggan AR | [12 empty] | Agustus
1.4 | ACC | Limit kredit pelanggan | Final Review Noted Terakhir | Agung Saputra | 4586700% | 4586900% | Completed | 100% | Wating Data Limit Per Pelanggan AR | [12 empty] | Juli
1.5 | ACC | Limit kredit pelanggan | V&V Limit Kredit Pelanggan | Resa Puji Rianto | 4586700% | 4586900% | Completed | 100% | [13 empty] | Agustus
2 | ACC | Cash Flow | Cash flow | Agung Saputra | 4581800% | 4587700% | Completed | 100% | [13 empty] | Juni
2.1 | ACC | Cash Flow | Digital Harian Report Kasir | Siti Haeriah, Oka Rizky Nirlandi | 4581900% | 4585300% | Completed | 100% | [13 empty] | Juli
2.2 | ACC | Cash Flow | Update Report Cash Flow | Anas Darmawan | 4585600% | 4586600% | Completed | 100% | [13 empty] | Juli
2.3 | ACC | Cash Flow | V&V Data Cash Flow | Fanny Tri fajar Sari | 4586600% | 4586800% | Completed | 100% | [13 empty] | Mei
3 | ACC | Monitoring Transaksi Claim | Monitoring transaksi claim | Agung Saputra, Samsudin | 4583400% | 4587700% | In Progress | 95.38% | [13 empty] | Mei
3.1 | ACC | Monitoring Transaksi Claim | Meeting Mekanisme Proses Claim | Samsudin, Agung Saputra | 4582800% | 4582800% | Completed | 100% | 2025-06-22 | [12 empty] | Mei
3.2 | ACC | Monitoring Transaksi Claim | Task MDBA | Teddy Juanda | 4583400% | 4584600% | Ready Implement | 95.77% | [13 empty] | Mei
3.3 | ACC | Monitoring Transaksi Claim | Pengerjaan Task Report | Anas Darmawan | 4584600% | 4588600% | Not Started | 0% | [13 empty] | April
3.4 | ACC | Monitoring Transaksi Claim | V&V Data Claim | Taufik Hidayat | 4588600% | 4588700% | Not Started | 0% | [13 empty] | April
3.5 | ACC | Monitoring Transaksi Claim | Testing QA | Sigit Suntoro | 4583400% | 4583900% | In Progress | 70% | [13 empty] | -
4 | HRD | Mekanisme Asset 1 Pintu | Mekanisme Asset 1 Pintu | Agung Saputra | 4578300% | 4585600% | In Progress | 92.86% | [13 empty] | Agustus
4.1 | HRD | Mekanisme Asset 1 Pintu | Task Dari HRIS & EIS | Agung Saputra | 4578300% | 4580800% | Completed | 100% | [13 empty] | Agustus
4.2 | HRD | Mekanisme Asset 1 Pintu | Task Modust Utilities | Iyan Hadi Mulyana | 4579700% | 4583200% | Completed | 100% | [13 empty] | -
4.3 | HRD | Mekanisme Asset 1 Pintu | Task Mobile EIS | Komang Tri Dharma Putra | 4578300% | 4578600% | Completed | 100% | [13 empty] | Juni
4.4 | HRD | Mekanisme Asset 1 Pintu | Task Dari HRIS & EIS | Oka Rizky Nirlandi | 4584800% | 4590000% | Completed | 100% | [13 empty] | Juni
4.5 | HRD | Mekanisme Asset 1 Pintu | Report Data Asset | Erdian Ananda | 4585200% | 4585300% | Completed | 100% | [13 empty] | Juni
4.6 | HRD | Mekanisme Asset 1 Pintu | Dokumentasi Technical Writer | Reno Rimawan | 4584500% | 4585300% | Completed | 100% | [13 empty] | Juli
4.7 | HRD | Mekanisme Asset 1 Pintu | V&V Data Asset | Fanny Tri fajar Sari, Teguh Wibowo | 4585500% | 4585600% | In Progress | 50% | [13 empty] | Juli
5 | HRD | E-Learning | E-Learning | Agung Saputra | 4578300% | 4579600% | Completed | 100% | [13 empty] | Juni
5.1 | HRD | E-Learning | Task E-Learning | Suryana Saputra | 4578300% | 4579600% | Completed | 100% | [13 empty] | Agustus
5.2 | HRD | E-Learning | Testing QA | Sigit Suntoro | 4579200% | 4579600% | Completed | 100% | [13 empty] | Juli
5.3 | HRD | E-Learning | Dokumentasi Technical Writer | Yudistira, Reno Rimawan | 4579200% | 4579600% | Completed | 100% | [13 empty] | Juli
5.4 | HRD | E-Learning | Report E-Learning | Rudianto | 4584800% | 4585000% | In Progress | 90% | [13 empty] | September
5.5 | HRD | E-Learning | V&V E-Learning | Taufik Hidayat | 4585900% | 4586000% | Not Started | 0% | [13 empty] | Juli
6 | HRD | KPI & Penilaian Karyawan | KPI & Penilaian Karyawan (Rotasi/Mutasi & PKWT) | Agung Saputra | 4576100% | 4577700% | Completed | 100% | [13 empty] | Juli
6.1 | HRD | KPI & Penilaian Karyawan | Task KPI & Penilaian Karyawan | Suryana Saputra | 4576100% | 4577700% | Completed | 100% | [13 empty] | Mei
6.2 | HRD | KPI & Penilaian Karyawan | Testing QA | Sigit Suntoro | 4576700% | 4577700% | Completed | 100% | [13 empty] | Agustus
6.3 | HRD | KPI & Penilaian Karyawan | Dokumentasi Technical Writer | Yudistira, Reno Rimawan | 4577600% | 4577700% | Completed | 100% | [13 empty] | Juli
6.4 | HRD | KPI & Penilaian Karyawan | Report KPI & Penilaian Karyawan | Rudianto | 4577700% | 4577700% | Completed | 100% | [13 empty] | Juli
6.5 | HRD | KPI & Penilaian Karyawan | Fixing Bugs & Update Patch | Suryana Saputra |  |  | In Progress | 0% | [13 empty] | -
7 | PCH | New Dashboard Purchasing | New Dashboard Purchasing | Samsudin | 4576800% | 4584500% | Completed | 100% | [13 empty] | Juni
7.1 | PCH | New Dashboard Purchasing | Task Dashboard Tahap 1 | Rudianto | 4576800% | 4583800% | Completed | 100% | [13 empty] | -
7.2 | PCH | New Dashboard Purchasing | V&V Dashboard Purchasing Tahap 1 | Resa Puji Rianto | 4584100% | 4584500% | Completed | 100% | [13 empty] | -
8 | GA | Asset Management | Asset Management | Iyan Hadi Mulyana | 4559400% | 4586600% | Completed | 100% | [13 empty] | Agustus
8.1 | GA | Asset Management | Task Modust Utilities | Iyan Hadi Mulyana | 4559400% | 4586600% | Completed | 100% | [13 empty] | Agustus
8.2 | GA | Asset Management | Testing QA | Sigit Suntoro | 4586600% | 4587300% | Not Started | 0% | [13 empty] | Agustus
8.3 | GA | Asset Management | Dokumentasi Technical Writer | Reno Rimawan | 4583400% | 4583800% | Completed | 100%
8.4 | GA | Asset Management | Report Asset | Erdian Ananda | 4586600% | 4587400% | Completed | 100%
8.5 | GA | Asset Management | V&V Data Aset | Fanny Tri fajar Sari | 4587300% | 4587400% | In Progress | 50%
9 | GA | Mobile Re-Asset Apps Scan | Mobile Re-Asset Apps Scan | Iyan Hadi Mulyana | 4561000% | 4562300% | Completed | 100%
9.1 | GA | Mobile Re-Asset Apps Scan | Task Mobile Re-Asset Apps Scan | Arga Fauzianto | 4561000% | 4562300% | Completed | 100%
9.2 | GA | Mobile Re-Asset Apps Scan | Testing QA | Eri Septian | 4569800% | 4570100% | Completed | 100%
9.3 | GA | Mobile Re-Asset Apps Scan | Dokumentasi Technical Writer | Reno Rimawan | 4566000% | 4566400% | Completed | 100%
9.4 | GA | Mobile Re-Asset Apps Scan | Monitoring Asset Scan | Oka Rizky Nirlandi | 4584700% | 4587900% | Completed | 100%
10 | GA | Mobile Re-Asset Apps Scan | V&V Data Aset | Fanny Tri fajar Sari | 4587400% | 4587500% | Completed | 100%
11 | GA | ITD - Peminjaman Asset | ITD - Peminjaman Asset | Iyan Hadi Mulyana | 4556000% | 4587800% | Ready Implement | 98.33%
11.1 | GA | ITD - Peminjaman Asset | Task ITD - Peminjaman Asset | Ratu Della | 4556000% | 4587800% | Ready Implement | 95%
11.2 | GA | ITD - Peminjaman Asset | Testing QA | Eri Septian | 4586100% | 4586300% | Completed | 100%
11.3 | GA | ITD - Peminjaman Asset | Dokumentasi Technical Writer | Reno Rimawan | 4583100% | 4583800% | Completed | 100%
11.4 | GA | ITD - Peminjaman Asset | Report ITD - Peminjaman Asset | Erdian Ananda | 4585300% | 4586200% | Completed | 100%
12 | GA | ITD - Peminjaman Asset | V&V Data ITD Peminjaman Asset | Resa Puji Rianto | 4586400% | 4586600% | Not Started | 0%
13 | SC | Realtime Monitoring | New Project with SC (Control Tower = Easy Go => Realtime Monitoring) | Samsudin, Iyan Hadi Mulyana | 4581000% | 4589900% | Not Started | 0% | Monitoring Easygo
13.1 | SC | Realtime Monitoring | Task Waterin | Deden Wahyudi | 4581000% | 4589900% | Not Started | 0% | Monitoring Easygo
13.2 | SC | Realtime Monitoring | Task Realtime Monitoring | Rudianto | 4581000% | 4589900% | Not Started | 0% | Monitoring Easygo
13.3 | SC | Realtime Monitoring | V&V Realtime Monitoring | Resa Puji Rianto | 4581000% | 4589900% | Not Started | 0% | Monitoring Easygo
14 | SC | Live Stock Real Time | Live Stock Real Time | Samsudin | 4583100% | 4587700% | Completed | 100%
14.1 | SC | Live Stock Real Time | Task Stock Real Time | Anas Darmawan | 4583100% | 4587400% | Completed | 100%
14.2 | SC | Live Stock Real Time | V&V Stock Real Time | Taufik Hidayat | 4584900% | 4587700% | Completed | 100%
15 | SC | Safety Checklist Armada | Safety Checklist Armada (PIC Lead Trainer = Pak Sugi (Temporary) => Production MRT & TBK | Iyan Hadi Mulyana | 4572100% | 4576300% | Ready Implement | 90% | Waiting Pak Syafei
15.1 | SC | Safety Checklist Armada | Task Safety Checklist Armada | Deden Wahyudi | 4572100% | 4576300% | Ready Implement | 90% | Waiting Pak Syafei
15.2 | SC | Safety Checklist Armada | Testing QA | Eri Septian | 4581000% | 4589900% | Completed | 100% | Waiting Pak Syafei
15.3 | SC | Safety Checklist Armada | Dokumentasi Technical Writer | Reno Rimawan | 4587500% | 4588500% | Completed | 100%
15.4 | SC | Safety Checklist Armada | Report Safety Checklist Armada | Erdian Ananda | 4587000% | 4587500% | Not Started | 0%
16 | OPR | DSC | DSC | Iyan Hadi Mulyana | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.1 | OPR | DSC | E-Tilang (With HR & IA) | Oka Rizky Nirlandi | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.2 | OPR | DSC | MDBA RTG Perbaikan | Suryana Saputra | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.3 | OPR | DSC | Mobile RTG Security | Pandu Pradana Putra | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.4 | OPR | DSC | Report WMS | Anas Darmawan | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.5 | OPR | DSC | V&V WMS | Taufik Hidayat, Resa Puji Rianto | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.6 | OPR | DSC | Report DSC | Oka Rizky Nirlandi | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
16.7 | OPR | DSC | Report Setoran Kasir (Alert) | Erdian Ananda | 4577200% | 4589900% | Completed | 100% | Implement 9 Depo
17 | OPR | GPS Tracking Armada Distribusi | GPS Tracking Armada Distribusi (Untuk NOVA) | Iyan Hadi Mulyana, Agung Saputra |  |  | On Hold | 0%
17.1 | OPR | GPS Tracking Armada Distribusi | Meeting Koordinasi Easy Go | Agung Saputra, Iyan Hadi Mulyana | 4581200% | 4581200% | Completed | 100% | Sudah Terinstall di Armada Nova
17.2 | OPR | GPS Tracking Armada Distribusi | Timeline Menunggu PO Order Ke Easy GO | Iyan Hadi Mulyana, Agung Saputra | 4581200% | 4581400% | Completed | 100% | Sudah Terinstall di Armada Nova
17.3 | OPR | GPS Tracking Armada Distribusi | Proses Installasi GPS |  | 4582100% | 4582800% | Completed | 100% | Sudah Terinstall di Armada Nova
17.4 | OPR | GPS Tracking Armada Distribusi | Interfacing (menyusul) | Samsudin |  |  | On Hold | 0% | Menunggu Meeting Selanjutnya
17.5 | OPR | GPS Tracking Armada Distribusi | Task Interfacing with nexsoft | Oka Rizky Nirlandi |  |  | On Hold | 0% | Menunggu Meeting Selanjutnya
18 | OPR | Mobile Apps Stock Opname (Asset OPR) | Mobile Apps Stock Opname (Asset OPR) | Iyan Hadi Mulyana | 4581700% | 4589900% | Ready Implement | 95% | Menunggu Meeting
18.1 | OPR | Mobile Apps Stock Opname (Asset OPR) | Task Mobile Opname Asset OPR | Arga Fauzianto | 4581700% | 4589900% | Ready Implement | 90% | Menunggu Meeting
18.2 | OPR | Mobile Apps Stock Opname (Asset OPR) | Testing QA | Eri Septian | 4581800% | 4589900% | Completed | 100% | Menunggu Meeting
18.3 | OPR | Mobile Apps Stock Opname (Asset OPR) | Dokumentasi Technical Writer | Reno Rimawan | 4581800% | 4589900% | Not Started | 0% | Menunggu Meeting
19 | SND | MDBA PO-MT | MDBA PO-MT | Samsudin, Agung Saputra | 4583100% | 4584700% | Completed | 100%
19.1 | SND | MDBA PO-MT | Task MDBA PO-MT | Teddy Juanda, Suryana Saputra | 4583100% | 4584700% | Completed | 100%
19.2 | SND | MDBA PO-MT | Testing QA | Sigit Suntoro | 4585000% | 4585400% | Completed | 100%
19.3 | SND | MDBA PO-MT | Dokumentasi Technical Writer | Reno Rimawan | 4585600% | 4586600% | Not Started | 0%
19.4 | SND | MDBA PO-MT | Report MDBA PO-MT | Samsudin | 4585600% | 4587000% | Completed | 100%
19.5 | SND | MDBA PO-MT | V&V Report | Fanny Tri fajar Sari | 4587100% | 4587300% | Completed | 100%
19.6 | SND | MDBA PO-MT | Design UI & UX | Hafid Bachtiar | 4583100% | 4583100% | Completed | 100%
20 | SND | Dashboard Performance All Depo & All | Dashboard Performance All Depo & All | Samsudin | 4581000% | 4589900% | Completed | 100% | Waiting Template SND
20.1 | SND | Dashboard Performance All Depo & All | Task Dashboard Performance All Depo & All | Rudianto | 4581000% | 4589900% | Completed | 100% | Waiting Template SND
20.2 | SND | Dashboard Performance All Depo & All | V&V Report | Taufik Hidayat, Resa Puji Rianto | 4581000% | 4589900% | Completed | 100% | Waiting Template SND
21 | SND | Waterout Approval SA | MDBA Approval SA | Agung Saputra | 4582400% | 4587000% | Ready Implement | 96.11%
21.1 | SND | Waterout Approval SA | Task Approval SA Waterout | Agung Saputra | 4582400% | 4584000% | Ready Implement | 95%
21.2 | SND | Waterout Approval SA | Task Approval SA Waterout | Deden Wahyudi | 4584300% | 4585200% | Ready Implement | 95%
21.3 | SND | Waterout Approval SA | Testing QA | Eri Septian | 4585500% | 4585900% | Completed | 100%
21.4 | SND | Waterout Approval SA | Dokumentasi Technical Writer | Reno Rimawan | 4586200% | 4587000% | Not Started | 0%
22 | POOL | Mobile Mekanik Apps Multi User | Mobile Mekanik Apps Multi User | Iyan Hadi Mulyana | 4549500% | 4552500% | Completed | 100%
22.1 | POOL | Mobile Mekanik Apps Multi User | Task Mobile Mekanik Apps Multi User | Pandu Pradana Putra | 4549500% | 4552500% | Completed | 100%
22.2 | POOL | Mobile Mekanik Apps Multi User | Dokumentasi Technical Writer | Reno Rimawan | 4538300% | 4538800% | Completed | 100%
22.3 | POOL | Mobile Mekanik Apps Multi User | Report Mobile Mekanik Apps Multi User | Rudianto | 4552500% | 4553000% | Completed | 100%
22.4 | POOL | Mobile Mekanik Apps Multi User | Design UI & UX | Hafid Bachtiar | 4548800% | 4550200% | Completed | 100%
23 | OPR | Mobile RTG SPV Delivery | Mobile RTG SPV Delivery | Iyan Hadi Mulyana | 4555900% | 4567400% | On Hold | 90% | Waiting Meeting Dengan OPR
23.1 | OPR | Mobile RTG SPV Delivery | Task Mobile RTG SPV Delivery | Arga Fauzianto | 4555900% | 4567400% | On Hold | 90% | Waiting Meeting Dengan OPR
23.2 | OPR | Mobile RTG SPV Delivery | Testing QA | Eri Septian | 4567200% | 4567500% | Not Started | 0% | Waiting Meeting Dengan OPR
23.3 | OPR | Mobile RTG SPV Delivery | Dokumentasi Technical Writer | Reno Rimawan | 4567400% | 4567700% | Completed | 100%
23.4 | OPR | Mobile RTG SPV Delivery | Report Mobile RTG SPV Delivery | Erdian Ananda | 4585300% | 4586400% | Not Started | 0% | Waiting Meeting Dengan OPR
23.5 | OPR | Mobile RTG SPV Delivery | Design UI & UX | Hafid Bachtiar | 4548800% | 4555400% | Completed | 100%
24 | IA | WBS (Pelaporan Audit) | WBS (Pelaporan Audit) | Agung Saputra | 4578200% | 4584900% | Completed | 100%
24.1 | IA | WBS (Pelaporan Audit) | Task WBS (Pelaporan Audit) | Suryana Saputra | 4577900% | 4583900% | Completed | 100%
24.2 | IA | WBS (Pelaporan Audit) | Testing QA | Sigit Suntoro | 4584500% | 4585900% | Completed | 100%
24.3 | IA | WBS (Pelaporan Audit) | Dokumentasi Technical Writer | Reno Rimawan | 4585700% | 4586600% | Completed | 100% | Completed 7 Agustus 2025
24.4 | IA | WBS (Pelaporan Audit) | Report WBS (Pelaporan Audit) | Samsudin | 4584800% | 4586100% | Completed | 100%
24.5 | IA | WBS (Pelaporan Audit) | Design UI & UX | Hafid Bachtiar | 4576200% | 4577900% | Completed | 100%
25 | IA | WBS (Pelaporan Audit) | V&V Report WBS | Resa Puji Rianto | 4584800% | 4586100% | Completed | 100%
26 | CSQM | IM Digital (Number Letter) | IM Digital (TTD QR Code) | Agung Saputra | 4583100% | 4589000% | Ready Implement | 97.5%
26.1 | CSQM | IM Digital (Number Letter) | Design UI & UX | Hafid Bachtiar | 4583100% | 4584600% | Completed | 100% | Completed 16 Juli 2025
26.2 | CSQM | IM Digital (Number Letter) | Task IM Digital (TTD QR Code) | Teddy Juanda | 4585200% | 4586700% | Ready Implement | 97.5%
26.3 | CSQM | IM Digital (Number Letter) | Testing QA | Sigit Suntoro | 4586700% | 4587700% | Completed | 100%
26.4 | CSQM | IM Digital (Number Letter) | Dokumentasi Technical Writer | Reno Rimawan | 4589000% | 4590000% | Not Started | 0%
27 | POOL | New Dashboard Pool | New Dashboard Pool | Samsudin | 4583200% | 4588100% | In Progress | 33.33%
27.1 | POOL | New Dashboard Pool | Dashboard JobCard Mechanic | Rudianto | 4583200% | 4588100% | Completed | 100%
27.2 | POOL | New Dashboard Pool | Dashboard Tire Pool | Rudianto | 4588200% | 4594500% | Not Started | 0%
27.3 | POOL | New Dashboard Pool | Dashboard Part Pool | Rudianto | 4594800% | 4595300% | Not Started | 0%
27.4 | POOL | New Dashboard Pool | V&V Report Dashboard Pool | Taufik Hidayat, Resa Puji Rianto | 4594800% | 4595600% | In Progress | 10%
28 | POOL | Mobile Apps Driver Management | Mobile Apps Driver Management | Agung Saputra | 4585900% | 4589900% | Ready Implement | 100%
28.1 | POOL | Mobile Apps Driver Management | Start Meeting | Agung Saputra | 4582600% | 4582600% | Completed | 100%
28.2 | POOL | Mobile Apps Driver Management | Task Apps Driver Management | Komang Tri Dharma Putra | 4585900% | 4588200% | Completed | 100%
28.3 | POOL | Mobile Apps Driver Management | Testing QA | Eri Septian | 4588900% | 4589400% | Completed | 100%
28.4 | POOL | Mobile Apps Driver Management | Design UI & UX | Hafid Bachtiar | 4585200% | 4585900% | Completed | 100%
28.5 | POOL | Mobile Apps Driver Management | Dokumentasi Technical Writer | Reno Rimawan | 4589400% | 4589900% | Not Started | 0%
28.6 | POOL | Mobile Apps Driver Management | Report Driver Management | Samsudin | 4593800% | 4593900% | Completed | 100%
28.7 | POOL | Mobile Apps Driver Management | V&V Report Driver Management | Taufik Hidayat | 4594000% | 4594500% | Completed | 100%
29 | FA | NEW GL | NEW GL | Agung Saputra | 4581000% | 4589900% | In Progress | 96.11% | Need Training From ZOG
29.1 | FA | NEW GL | Task Implementasi & Kawal GL | Teddy Juanda, Siti Haeriah | 4581000% | 4589900% | In Progress | 96.11%
29.2 | FA | NEW GL | V&V NEW GL | Fanny Tri fajar Sari | 4581000% | 4589900% | In Progress | 95%
30 | NOVA | Nexsoft | Koordinator Implementation | Samsudin, Resa Puji Rianto, Taufik Hidayat | 4581000% | 4589900% | Not Started | 0%
31 | ICT | Project IP CCTV | Project IP CCTV | Andrianto, Ari Wibowo | 4581000% | 4589900% | In Progress | 60% | 6

## Agung Saputra (hidden)
Details for TC - Assigned to: Agung Saputra
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly
MDBA | Update MOM Limit Kredit 290824 | Kartu piutang hanya dimunculkan yang belum bayar |  | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Hold by case untuk all pelanggan masih by user (Dari AR tanpa approval) |  | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Allow Over checklist in case kredit limit (Roolback setelah 7 hari) |  | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Lock pengajuan extend limit kredit dibuat 15 hari |  | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Limit kredit notif 95% (warning) |  | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Customer saat di hapus, harusnya masih bisa di input | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Filter Kategori NPWP dan Filter Approval | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | View List KTP di Menu Pusat | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Menambahkan sub menu untuk menambahkan Id Pelanggan, apabila NPWP sudah terbuat. | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | View List NPWP approve, menu NPWP Cust di E-FAKTUR pusat diganti Approval NPWP dan NPWP minlength = '15' dan KTP minglenth = '16' | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Notifikasi apabila saat pembuatan NPWP tidak ada gambar feedback by view sistem dan email. | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Id pelanggan yg sudah dipilih saat pembuatan NPWP dan KTP, tidak lagi muncul di pembuatan NPWP dan KTP berikutnya. | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Saat pembuatan NPWP dan KTP, apabila di kolom nama diinput dengan huruf kecil. Maka saat save akan menjadi besar (UPPER) | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Hapus status lunas/belum lunas - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Notif by email apabila di reject SPV Admin, Admin Invoice, ACO - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Notif by email untuk tax apabila customer baru (Tax Staff) - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Pencatatan Data KTP & Upload KTP data master - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Hanya pelanggan yang non aktif | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Bukti komunikasi (tidak mandatori muncul apabila Nama tidak sama) | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Nama Permintaan Pelanggan (Faktur Pajak) | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Nama Sesuai NPWP | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Edit form penambahan customer baru - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Customer badan usaha (Max 7 hari) untuk melakukan feedback - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Syarat standart pelanggan (Upload file KTP(Ci Anon) & NPWP(Tax staff) diwajibkan) - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Pencatatan NPWP sesuai dengan yang di inginkan pelanggan - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Pisahkan antara badan & pribadi (Customer Baru) - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Closed | 90% | 4550600% | 4551900% | - | #VALUE! | Project Existing | Agustus
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Supervisor Admin melakukan aksi verifikasi data customer (Kesalahan no npwp) & Upload BA perubahan NPWP (Depo Yang mengajukan) | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Modul AppTax, bisa diberikan di Depo, namun yang memvalidasi tetap dari pajak Pusat | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Pelanggan Baru PKP, Request faktur Pajak (Depo yang tambah pelanggan baru) | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | "Faktur Pajak Pengganti" untuk Tukar Faktur yang telah direvisi. | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Revisi Berdasarkan Invoice & Revisi Berdasarkan No NPWP salah / Sudah tercetak | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Ditambahkan Download Excel Invoice yang sudah diajukan faktur pajak vs E-Faktur yang sudah di upload | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Ditambahkan menu "Status Pengajuan Faktur Pajak" untuk mengetahui bahwa TF sudah di upload, diterima. | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Note Kolom Keterangan bagi Tukar faktur yang telah direvisi ditandai dengan "Revisi 1, Revisi 2" | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Tukar faktur yang FIX ditandai dengan "Cor" = Correct | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | View dimunculkan semua yang di ceklist & Pertanggal | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Report Terdapat Data Kartu Piutang yang tidak lengkap antara UMP vs Kartu Piutang | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA E-Faktur - MOM 13 Februari 2024 | Report Kolom Summary (terdapat Koma ,) | Update Mom | New Project | Update Feature | Agung Saputra | Closed | 90% | 4533800% | 4534500% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA TAX - Interface E - Faktur | 5. Menu Tolakan Invoice TAX => Approval Atasan | New Feature | New Project | New Feature | Agung Saputra | Closed | 90% | 4532300% | 4532900% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA TAX - Interface E - Faktur | 4. Validasi Tolak Invoice TAX | New Feature | New Project | New Feature | Agung Saputra | Closed | 90% | 4532300% | 4532900% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA TAX - Interface E - Faktur | 3. Simpan Invoice to Draft E-Faktur | New Feature | New Project | New Feature | Agung Saputra | Closed | 90% | 4532300% | 4532900% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA TAX - Interface E - Faktur | 2. Detail Invoice | New Feature | New Project | New Feature | Agung Saputra | Closed | 90% | 4532300% | 4532900% | - | #VALUE! | Project Charter | Februari
MDBA | MDBA TAX - Interface E - Faktur | 1. List Data Type DO Harian & Bulanan (All Transaksi Kredit Pelanggan KPP) | New Feature | New Project | New Feature | Agung Saputra | Closed | 90% | 4532300% | 4532900% | - | #VALUE! | Project Charter | Februari
HRIS - EIS | Payroll | PPh 21 In House Simulasi 2024 | Tarikan data karyawan simulasi - In Progress | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
HRIS - EIS | Payroll | PPh 21 In House Simulasi 2024 | Gaji + (ketentuan kesepakatan), tarikan data Januari - Desember 2023 - In Progress | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
HRIS - EIS | Payroll | PPh 21 In House Simulasi 2024 | Rekap All SA + PPh 21 (Januari - Desember 2023) - Open | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
HRIS - EIS | Payroll | PPh 21 In House Simulasi 2024 | Pengecekan hasil perhitungan (Gross Up & Net) ke system ESPT - Open | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
MDBA | Update MOM Evaluasi Cash Flow 30 September 2025 | Sosialisasi Depo Serang dan Kalibata 30 September 2025 |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4593000% | 4593600% | 4593600% | 6 | Project Existing | Oktober, 2025
MDBA | Update MOM Evaluasi Cash Flow 30 September 2025 | Trial Penginputan after update Cash Flow Sampai tanggal 4 Oktober dan di review kembali di tanggal Rabu 8 Oktober 2025 |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4593000% | 4593600% | 4593600% | 6 | Project Existing | Oktober, 2025
HRIS - EIS | HRIS - Penambahan kolom pengisian history training |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4592600% | 4592800% | 4592600% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Pada saat approval surat di user atasan tidak bisa print preview. Berikan akses untuk preview hanya isi suratnya saja tidak dengan tanda tangan (Semua Surat Rotasi Mutasi) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4592300% | 4592300% | 4592300% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Untuk Approval Digital Signnya di seragamkan Contoh (Nama : Rahmat Iswanto, Jabatan :HRM , Nik : XXX) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4592300% | 4592300% | 4592300% | 0 | Project Existing | September, 2025
MDBA | Plan Replace New Account & Cost Center 2024 | DMS (TVIP, ASA, MRT, TBK) 192.168.4.90 |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529500% | 4529700% | 4529700% | 2 | Project Existing | Januari
MDBA | Plan Replace New Account & Cost Center 2024 | Web MDBA Kasir . |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529500% | 4529700% | 4529700% | 2 | Project Existing | Januari
MDBA | Plan Replace New Account & Cost Center 2024 | GL (TVIP, ASA, MRT, TBK) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529500% | 4529700% | 4529700% | 2 | Project Existing | Januari
MDBA | Plan Replace New Account & Cost Center 2024 | Web MDBA Kasir Teddy: |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4529500% | 4529700% | 4529700% | 2 | Project Existing | Januari
MDBA | MDBA Limit Kredit - Extend Limit Kredit |  |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4589900% | 4589900% | 4589900% | 0 | Project Existing | September, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Lock Apps MDBA Limit Kredit |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4583800% | 4584700% | 4591500% | 77 | Project Charter | Juni, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Extend Limit Cust |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4578600% | 4579000% | 4591500% | 129 | Project Charter | April, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Limit Credit Cust |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4578100% | 4578500% | 4591500% | 134 | Project Charter | April, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Limit Credit |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4577600% | 4578000% | 4591500% | 139 | Project Charter | April, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Struktur Coding |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4577100% | 4577500% | 4591500% | 144 | Project Charter | April, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Mockup UI/UX (Matrial Design) |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4576600% | 4577000% | 4591500% | 149 | Project Charter | April, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Mapping Matriks |  | New Project | New Feature | Agung Saputra | Complete | 100% | 4576200% | 4576500% | 4591500% | 153 | Project Charter | April, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | SC Shiftingnya belum bisa di buat oleh mbk maya |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | View HRIS masih belum sesuai untuk TL nya |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Di menu tambah data master karyawan kolom input NPWP Tidak tebaca no NPWP di view pak mamet, untuk penginputan NPWP di buatkan formatnya oleh mbk mala |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Jika pengajuan PTK Cancel atau hangus atau reject status pengajuanya closed |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Update pengajuan belum masuk ke all data karyawan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk Asset 1 Pintu di mulai dari pengajuan PTK dari team HRD Harus kirim email konfrimasi ke ICT terkait kebutuhan Assetnya untuk karyawan / jabatan baru |  | Tunning | Update Feature | Agung Saputra | Complete | 90% | 4586000% | 4586300% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk jabatan ACO dapat menilai all spv admin incase |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586900% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Penilaian mid year perlu di update query dan logic untuk penilaian pertengahan tahun, akan di buat timelinenya |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
MDBA | Validation Upload VA txt - MDBA AR |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4530000% | 4530200% | 4530200% | 2 | Project Existing | Januari
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | HRIS - EiS Upload ke production selasa, 22 juli 2025 |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk Tanggal Approval Pak Rahmat Menjadi tanggal rilis SK (Semua SK) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk TTD Bu sandra di buat QR Code di semua SK |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Setelah di setting tanggal update karyawan team HRdapat setting NIK Untuk Kolom QR Code TTD "diajukan oleh" pada SK Penugasan, SK Penujukan, SK Keterangan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Update keterangan pada extend promosi "Extend Promosi Jabatan di karnakan keterangan sampai dengan tanggal punishment" |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Pada data approve mutasi dan rotasi jika terdapat extend promosi terkait penambahan project, data extend tidak tersambung jadi harus di tambahkan kolom input lain - lain |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Agustus, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | TRAINING DAN TRIAL PENGGUNAAN NEW GL |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4587600% | 4588700% | 4589500% | 19 | Project Existing | Agustus, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | SEEDING DATA MEI 2025 SETELAH POINT 4 SELESAI |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4587600% | 4588700% | 4589100% | 15 | Project Existing | Agustus, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | SEEDING DATA JAN-APR 2025 SETELAH POINT 3 SELESAI (ALL REPORTING & SALDO HARUS SAMA DENGAN FOXPRO) |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4587600% | 4588700% | 4588100% | 5 | Project Existing | Agustus, 2025
MDBA | Issue MDBA Peralihan CO dari Balaraja ke Manis3 |  | User pengajuan : (ZULFIKAR GEDE F) Jenis koreksi : (SISTEM ERROR/DOUBLE INPUT) Pemohon Adjustment : ZULFIKAR Kronologis : TERJADI DOUBLE INPUT SISTEM BTB ANTAR DEPO Konfirmasi Ke user depo Balaraja | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4529600% | 4530300% | 4543900% | 143 | Project Existing | Januari
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 9. Import data Jan-Apr 2025 to Production | TVIP | Tunning | Addhock | Agung Saputra | Complete | 100% | 4582400% | 4584300% | 4584300% | 19 | Project Existing | Juni, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 8. Backup data Dummy & Production | TVIP | Tunning | Addhock | Agung Saputra | Complete | 100% | 4582400% | 4584300% | 4584300% | 19 | Project Existing | Juni, 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Data Harga | Persiapan Realese & Import Data | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4571700% | 4571700% | 15 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Data Produk | Persiapan Realese & Import Data | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4571700% | 4571700% | 15 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Tambah Kolom Ext BTB Supplier | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Charter | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BTB Distribusi | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BKB Distribusi | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BTB Distribusi | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4572400% | 4572400% | 22 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BKB Distribusi | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4572400% | 4572400% | 22 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BTB Supplier | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4571700% | 4571700% | 15 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BKB Supplier | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4572000% | 4572000% | 18 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BKB Supplier | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4572000% | 4572000% | 18 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BTB Supplier | Inventory | New Project | New Feature | Agung Saputra | Complete | 100% | 4570200% | 4571200% | 4572300% | 21 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - KINO | Closing TBG | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Mutasi Internal Depo | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | BKB Depot | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | BTB Depot | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | BKB Supplier | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | BTB Supplier | Tutup Buku Gudang | New Project | New Feature | Agung Saputra | Complete | 100% | 4565600% | 4570200% | 4570200% | 46 | Project Existing | Desember
HRIS - EIS | Perhitungan PPH21 untuk persiapan Formula Baru |  | Perhitungan PPH21 untuk persiapan Formula Baru di update untuk persiapan pajak 2024 | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4531000% | 7 | Project Existing | Januari
MDBA | Update MOM Limit Kredit 290824 | Nominal limit kredit di munculkan apabila lebih dari orderan khusus pelanggan kredit |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | SO Pabrikan semua dari depo di tembak tunai tapi ada beberapa pelanggan by case dia kredit |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Group by customer (Indomaret, Carefoor, dll) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | 100% baru bisa hold pelanggan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Update MOM Limit Kredit 290824 | Email berdasarkan segment untuk spv depo apabila ada warning limit kredit |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4554600% | 4555900% | - | #VALUE! | Project Existing | September
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Hasil akhir yang sudah terverifikasi tax untuk di upload (Banding DO) - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Struktur mentah dan jadi hasil clustering antara tax (NPWP & KTP) berbeda - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | customer clustering invoice berdasarkan (invoice, sku, atau satuan) - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Upload berdasarkan Invoice = E-Faktur (Apakah bisa di ambil berdasarkan API) - Menunggu meeting dengan mitra pajakku | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Merge invoice yang di pilih oleh tax dari depo tetap satuan - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Inputan PO customer di Sales Order generate ke DO - 1 week | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Kesepakatan merge produk - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Penyeragaman nama customer (tarikan excel, verifikasi bu obi) - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Penyeragaman id produk, nama produk, satuan produk (tarikan excel, verifikasi bu obi) - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | Integrasi pembuatan Faktur Pajak (Depo & Pusat) | Konfirmasi untuk kelengkapan data terkait do invoice yang di merge - 3 month | MOM 020824 Meeting E-Faktur | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4550600% | 4551900% | 4593700% | 431 | Project Existing | Agustus
MDBA | MDBA - MOM Kartu Piutang | Secara view muncul data 1 tahun tapi filter sesuai dengan kebutuhan |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4544700% | 144 | Project Charter | Januari
MDBA | MDBA - MOM Kartu Piutang | Untuk akses view perdepo, pusat ALL |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4544700% | 144 | Project Charter | Januari
MDBA | MDBA - MOM Kartu Piutang | View Detail Export Excel |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4544700% | 144 | Project Charter | Januari
MDBA | MDBA - MOM Kartu Piutang | Detail yang belum bayar, muncul paling atas |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4544700% | 144 | Project Charter | Januari
MDBA | MDBA - MOM Kartu Piutang | Sisa Invoice di ambil dari sisa invoice pelanggan tersebut ALL ( 3 Tahun + Yang masih Open) |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4530300% | 4531000% | 4544700% | 144 | Project Charter | Januari
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Tampilkan berapa pcs dalam 1 karton di detail (BTB Supplier) | Update MOM MDBA KINO | New Project | New Feature | Agung Saputra | Complete | 100% | 4563000% | 4563000% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Sesuaikan BTB Supplier untuk supplier dan jasa pengangkut | Update MOM MDBA KINO | New Project | New Feature | Agung Saputra | Complete | 100% | 4563000% | 4563000% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | DO Kredit Inv Langsung tidak bisa applied | Update MOM MDBA KINO | New Project | New Feature | Agung Saputra | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | DO Kredit Limit tidak bisa di applied | Update MOM MDBA KINO | New Project | New Feature | Agung Saputra | Complete | 100% | 4563100% | 4563500% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | TBG CONVERT | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Agung Saputra | Complete | 100% | 4562100% | 4562500% | 4569400% | 73 | Project Charter | November
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Perubahan BTB Supplier | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Agung Saputra | Complete | 100% | 4562100% | 4563600% | 4563600% | 15 | Project Charter | November
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Pembuatan Tabel stok on hand dan harga (menggunakan tabel Produk Sales Info) | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Agung Saputra | Complete | 100% | 4562100% | 4563000% | 4563000% | 9 | Project Charter | November
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Margin ttd di bawah print invoice |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4561600% | 4561600% | 4561600% | 0 | Project Existing | November
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Hilangkan lembar kosong terakhir saat print invoice |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4561500% | 4561500% | 4561500% | 0 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pada saat user mengajuakan promosi jika masih ada data sebelumnya tidak dapat mengajukan, case saat ini ketika user mengajukan tetap tampil dan doubel |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Untuk Digitalisasi Data Karyawan Next Akan di buat view nya di HRIS menunggu format di buatkan di excel oleh mas bisyri |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Untuk All Barcode Tanda Tangan di berikan keterangan Format Tanda Tangan Digital "Di setujui dan di tandatangani secara elektronik pada tempat dan tanggal" |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pemberitahuan Extend Internal Memo Job Assigment di tambahkan : Menginformasi Extend PLT Jabatan dengan alasan (Under performance, Tidak Lulus Panel, User Menolak)" Kepada karyawan sebagai berikut : |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pemberitahuan Extend Pelaksanaan Tugas di tambahkan : Menginformasi Extend PLT Jabatan dengan alasan Under performance, Tidak Lulus Panel, User Menolak" Kepada karyawan sebagai berikut : |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Tambahkan keterangan dalam bentuk select option pada cancel pengajuan di mutasi rotasi (Under performance, Tidak Lulus Panel, User Menolak) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pilihan keterangan Extend di buat dropdown listing (Punishment Aktif & Under performance |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Tambahkan 1 kolom status pengajuan (Lulus/Tidak lulus) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Penambahan judul "Perubahan Aktual" di bawah data tabel , dan di atas Button save di berikan catatan " Apa bila ada perubahan rotasi mohon ajukan ulang pengajuan rotasi & mutasi" |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pada saat ada pengajuan Program promosi jika di cancel ada alert ke email user yang mengajukan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
MDBA | E-FAKTUR - Migrasi data NPWP |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4530200% | 4530600% | 4530600% | 4 | Project Existing | Januari
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Penambahan filter pencarian by nomor invoice ***(DONE)*** |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Karyawan TKBM yang di perbantukan ke pool / depo lain, tidak bisa di buatkan shift untuk minggu selanjutnya dari WUH depo asal |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Refund > perubahan data setelah refund belum otomatis terupdate di sistem |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Update setting keterlambatan x01: (1 menit setelah jam shift masuk) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Penambahan tgl efektif untuk pengangkatan kartap |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Perubahan alur approval untuk di E-PPD |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Data PTK yang roleback dan minta hapus masih muncul di tarikan excel PTK |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Saat ini belum ada menu untuk tim training baik untuk upload history training karyawan maupun untuk penarikan data training karyawan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Approval digital HRD Manager pada dokumen SPLT/IM/SK promos, rotasi & demos karyawan |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Perubahan alur approval untuk di EPPD |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Untuk proses extend / perpanjangan mutasi, ditambahan kolom alasan perpanjangan / extend (case yang ada, bisa karna performarce dibawah target, yang diharapkan atau adanya punishment surat teguran / SP yang masih aktif) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Belum ada opsi tindakan untuk case tidak lulus promosi (case yang ada, karyawan bisa dikembalikan ke level jabatan sebelumnya Bisa ke jabatan yang sama atau jabatan yang berbeda) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Jika Karyawan Renew saat transisi NIK dan data averagenya bisa tetap di perhitungkan base nik lama atau tidak ? Akan di cek history renewnya |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4558100% | 4566500% | 4566500% | 84 | Project Existing | Oktober
MDBA | MDBA AR - SO Pabrikan bisa lakukan payment oleh depo (Fixing bugs) |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4555900% | 4556100% | 4556100% | 2 | Project Existing | September
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Tambahkan Filter Feature Upload persetujuan direksi (Noted: file approval direksi) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Perubahan Alur Pengajuan PTK |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Feature Upload Data Peserta Training (Import Masal) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Tambahkan Historical sebelum approve mutasi dan Rotasi (Ambil di HRIS) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Tanda Tangan All Surat dibuat digital |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Kop surat di ganti menjadi seperti Surat Keterangan (Kop Surat untuk Paklaring & Non Aktif) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Upload punishment untuk OS dapat melakukan Upload dokumen |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | "Rilis punishment OS dibuatkan button aksi untuk send email ke HR TVIP, jika terjadi pembatalan punishment button cancel hanya ada di HR " "Approval 2 Category : 1. In House Langsung dari HR Manager 2. Out House oleh penanggung jawab oleh OS" |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
MDBA | MDBA Invoice - New Feature Print Invoice Alamat Penagih |  |  | Tunning | New Feature | Agung Saputra | Complete | 100% | 4551100% | 4552400% | 4552500% | 14 | Project Existing | Agustus
MDBA | MDBA Invoice - Setting printer cetak invoice (LQ & LX) |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4551600% | 4554800% | 4555800% | 42 | Project Existing | Agustus
MDBA | MDBA Invoice - Cancel Invoice tanpa Correction |  |  | Tunning | Addhock | Agung Saputra | Complete | 100% | 4549900% | 4550500% | 4550900% | 10 | Project Existing | Juli
MDBA | MDBA Invoice - Applied invoice akhir bulan All |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4548200% | 4550200% | 4560100% | 119 | Project Existing | Juli
MDBA | MDBA AR - Monitoring CO to DO |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4548200% | 4548400% | 4548900% | 7 | Project Existing | Juli
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Validasi Form Rekon VA pembayaran depo |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4546300% | 4547000% | 4547000% | 7 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Pengecekan cut off kartu piutang tidak sama dengan UMP |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4546300% | 4547000% | 4547000% | 7 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Pembayaran dilakukan pengembalian botol di depo |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4546300% | 4547000% | 4547000% | 7 | Project Existing | Juni
MDBA | MDBA Invoice - Update query UMP VS Kartu Piutang |  |  | Tunning | Validasi | Agung Saputra | Complete | 100% | 4542500% | 4543200% | 4545300% | 28 | Project Existing | Mei
HRIS - EIS | HRIS EiS - MOM Koordinasi HRD & ICT 07 Mei 2024 | Approval PTK ada di pak rahmat dan di mbk mala ada button Start sourcing |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4542000% | 4542700% | 4544600% | 26 | Project Charter | Mei
HRIS - EIS | HRIS EiS - MOM Koordinasi HRD & ICT 07 Mei 2024 | Pada saat pengajuan PTK terdapat Feature Rollback dari user pada saat HR Approve, jika terjadi pembatalan user yang melakukan pengajuan PTK Bisa melakukan Rollback |  | New Project | Update Feature | Agung Saputra | Complete | 100% | 4542000% | 4542700% | 4544600% | 26 | Project Charter | Mei
HRIS - EIS | HRIS EiS - Exiting Task (Finishing) | Form Input Module Training |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4539700% | 4540100% | 4540300% | 6 | Project Existing | April
HRIS - EIS | HRIS EiS - Exiting Task (Finishing) | Approval Perubahan shifting (Tentatif) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4539700% | 4540100% | 4539700% | 0 | Project Existing | April
HRIS - EIS | HRIS EiS - Exiting Task (Finishing) | Approval Cuti Team HR sampai dengan HR Manager |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4539700% | 4540100% | 4540100% | 4 | Project Existing | April
HRIS - EIS | HRIS EiS - Exiting Task (Finishing) | Approval Mutasi Rotasi sampai dengan HR Manager |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4539700% | 4540100% | 4540100% | 4 | Project Existing | April
HRIS - EIS | HRIS EiS - Exiting Task (Finishing) | Approval PTK sampai dengan HR Manager |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4539700% | 4540100% | 4540400% | 7 | Project Existing | April
MDBA | MDBA AR - Update query List Data Rekon |  |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538300% | 4538700% | 4539900% | 16 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Exclude Tissue dan Galon di Detail Invoice |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Menu Checklist Invoice dipindahkan di dalam detail invoice |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | View E-Faktur Pajak untuk mengatuhi invoice mana saja yang belum di ceklist oleh depo |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Verifikasi Data sebelum TAX Revisi Judul Menu di dalam invoice |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | "Perubahan NPWP lama ke NPWP baru, terdapat menu Approval oleh TAX (NPWP Dapat di pilih). Pengajuan disertakan **"Berita Acara"** dan upload foto npwp baru" NPWP Lama akan mati, jika pengajuan NPWP baru sudah di approve oleh TAX |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Summary Card untuk mengetahui (Open, Reject, Approve) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Di master Menu NPWP, ditambahkan Foto NPWP nya. |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA E-Faktur - MOM 28 April 2024 | Terdapat Validasi penginputan Nomor NPWP (15 Digit) |  | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4538400% | 4539000% | 4545300% | 69 | Project Existing | April
MDBA | MDBA Invoice - Update Trouble MDBA | Do Jambot TK Astrid tidak muncul di UMP |  | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4535100% | 4535700% | 4538700% | 36 | Project Existing | Februari
MDBA | MDBA Invoice - History Invoice |  |  | Tunning | New Feature | Agung Saputra | Complete | 100% | 4531900% | 4535200% | 4535200% | 33 | Project Existing | Januari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Pengajuan rotasi mutasi dibuat pindah 7 hari ke lokasi tujuan dan jabatan baru (update kembali ke data awal auto apabila belum di approve) | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4534600% | 5 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Karyawan pengajuan project mengikuti start tanggal efektif | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4534600% | 5 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Data peralihan masa kerja karyawan | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4534600% | 5 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Buat Timeline All Approval PTK Di Manager HRD | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4534600% | 5 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | di Login EIS dibuatkan menu KPI, Survei & Assesment | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4534600% | 5 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Untuk Login Assesment menggunakan Nik dan Password EIS | Update Mom | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4534100% | 4534600% | 4560900% | 268 | Project Existing | Februari
MDBA | MDBA AR - Fixing Bugs Rekon AR | Valiadasi untuk penginputan rekon apabila ada yang sudah di rekon mengurangi sisa invoice walaupun belum dilakukan payment oleh depo |  | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4534100% | 4534300% | 4534300% | 2 | Project Existing | Februari
MDBA | MDBA Invoice - Invoice Depo (Tanggal Tukar Faktur) |  | Update Feature | Tunning | Update Feature | Agung Saputra | Complete | 100% | 4532100% | 4532200% | 4533400% | 13 | Project Existing | Januari
MDBA | MDBA Invoice - Rekapan Kartu Piutang | Update Query Untuk menampilkan semua kartu piutang pelanggan 3 Tahun terakhir, karena saat ini menggunakan query yang menampilkan kartu piutang yg belum bayar saja | Fixing Bugs | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4538400% | 4538700% | 4544700% | 63 | Project Charter | April
MDBA | MDBA Invoice - Rekapan Kartu Piutang | Penamaan menu "Sisa Piutang Pelanggan" diganti "Kartu Piutang Pelanggan" | Fixing Bugs | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4538400% | 4538700% | 4544700% | 63 | Project Charter | April
MDBA | MDBA Invoice - Rekapan Kartu Piutang | Ditambahkan Filter untuk menampilkan sisa piutang yang 0 | Fixing Bugs | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4538400% | 4538700% | 4544700% | 63 | Project Charter | April
MDBA | MDBA Invoice - Correction & Cancel Invoice (Fixing Bugs) |  | Fixing Bugs | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4534100% | 4534500% | 4539900% | 58 | Project Existing | Februari
MDBA | MDBA AR - Fixing Bugs Rekon Upload Excel |  | Fixing Bugs | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4532000% | 4532200% | 4532400% | 4 | Project Existing | Januari
MDBA | MDBA AR - Delete Rekon | Pembuatan feature untuk delete rekon by excel apabila ada kesalahan dalam melakukan rekon dan akan di rekon ulang |  | Tunning | New Feature | Agung Saputra | Complete | 100% | 4532000% | 4532200% | 4532100% | 1 | Project Existing | Januari
MDBA | MDBA Invoice - Rekon VA (Fixing Bugs) | Fixing bugs rekon ar VA lebih besar dari nominal invoice |  | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4531000% | 4531000% | 4531500% | 5 | Project Existing | Januari
MDBA | MDBA Invoice - Query Rekon VA (Fixing Bugs) | Fixing bugs nominal DO Minus masuk rekon |  | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4531000% | 4531000% | 4531500% | 5 | Project Existing | Januari
MDBA | MDBA Invoice - Payment (Fixing Bugs) | Fixing bugs payment dengan nominal nol saat upload excel |  | Fixing Bugs | Fixing Bugs | Agung Saputra | Complete | 100% | 4531000% | 4531000% | 4531000% | 0 | Project Existing | Januari
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Jika Customer Tidak ada transaksi dalam 1 tahun kebelakang di hilangkan |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Untuk Email di kirim ke all admin invoice dan spv admin berdasarkan PT |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Pada List Customer Pada Menu List Data NPWP Jika ada customer yang di hapus dari list harus ada approval SPV Adminnya |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Filter NPWP berdasarkan ALL PT |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Untuk Button Applied DO Kredit pelanggan PKP di pindahkan di dalam View Detail |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | DO Tunai tetapi di jadikan 1 Invoice (data rekap di kirim dari depo) |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Tambahkan Filter Bulan Pada List DO (All Transaksi Kredit Pelanggan PKP) |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Tambahkan Alert Validasi pada saat FU Invoice |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Update Upload PDF Korteks Pajak dari TAX Agar Depo Depo dapat melihat hasil Koteks Pajak |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Monitoring Invoice yang sudah di upload oleh TAX untuk mengetahui admin depo yang sudah di buat faktur pajak |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | MDBA Invoice - Faktur Pajak (MOM 22 Januari 2025) | Monitoring Invoice VS E-Faktur Untuk mengetahui DO mana saja yang belum di upload atau di revisi |  | Tunning | Update Feature | Agung Saputra | On Hold | 0% | 4568000% | 4569100% | - | #VALUE! | Project Existing | Januari 2025
MDBA | Update Case Waterin Auto Billing (REKAP) (MOM MEETING 14/10/2025) | Transaksi Adjustman Berhasil namun di QTY saldo Tidak Berubah | Case MDBA Pool | Tunning | Update Feature | Agung Saputra | Open | 0% | 4594300% |  | - | #VALUE! | Project Existing | Oktober, 2025
MDBA | Update Case Waterin Auto Billing (REKAP) (MOM MEETING 14/10/2025) | Transaksi TBG MDBA vs TBG Tarikan DMS Seringkali Tidak Sesuai | Case MDBA Pool | Tunning | Update Feature | Agung Saputra | Open | 0% | 4594300% |  | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Tambahkan feature download data untuk historical kontrak |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Tambahkan 1 kolom "waktu evaluasi" setelah kolom "waktu berakhir" |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Untuk reminder automatic apakah bisa masuk ke email HRD terkait reminder H-2 Minggu penilaian kinerja dan PKWT dengan catatan |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Monitoring evaluasi dengan PKWT Normal 12 Bulan atau PKWT dengan catatan di lakukan evaluasi secara berkala (3 Bulan, 6 Bulan dan 1 Tahun) acuannya di E-KPI |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Untuk setiap reminder akan di buat lognya, mulai dari "CC" dan "TO" nya auto dari reminder pertama |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Request pembuatan akun pegangan untuk akses penilaian mid year |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Untuk barcode di seragamkan tambahan keterangan seperti Internal Memo dan Violation |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Tambahkan approval digital lainnya |  | Tunning | Update Feature | Agung Saputra | Open | 0% | 4587800% | 4589400% | 4591700% | 39 | Project Existing | Agustus, 2025
Waterout | Testing - Waterout Approval SA | 4. Nama driver kosong di detail approval AM |  | New Project | Update Feature | Agung Saputra | Ready To Production | 95% | 4589900% | 4590200% | - | #VALUE! | Project Charter | September, 2025
Waterout | Testing - Waterout Approval SA | 3. Pengajuan SA tidak masuk ke approval AM |  | New Project | Update Feature | Agung Saputra | Ready To Production | 95% | 4589900% | 4590200% | - | #VALUE! | Project Charter | September, 2025
Waterout | Testing - Waterout Approval SA | 2. Tambahkan keterangan status approval AM di tampilan admin |  | New Project | Update Feature | Agung Saputra | Ready To Production | 95% | 4589900% | 4590200% | - | #VALUE! | Project Charter | September, 2025
Waterout | Testing - Waterout Approval SA | 1. Jika ke SO kolom depo pengajuan kosong di history approval |  | New Project | Update Feature | Agung Saputra | Ready To Production | 95% | 4589900% | 4590200% | - | #VALUE! | Project Charter | September, 2025
Waterout | Waterout Approval SA (Project Charter) | List Data History Approval |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4584000% | 4583900% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | Kirim Email to SC Area |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4583900% | 4583900% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | Approval AM |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4583300% | 4583400% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | List Data AM (By Cover Depo) |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4583000% | 4583200% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | Submit Auto Kirim Email CRL to AM |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4582800% | 4582900% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | Penambahan Logic SA Perlu Approval AM (CRL) |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4582600% | 4582700% | - | #VALUE! | Project Charter | Juni, 2025
Waterout | Waterout Approval SA (Project Charter) | Approval SA By AM |  | New Project | New Feature | Agung Saputra | Ready To Production | 95% | 4582600% | 4584000% | - | #VALUE! | Project Charter | Juni, 2025

## Teddy Juanda
Details for TC - Assigned to: Teddy Juanda
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | insert data manual |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | filter by no surat , tanggal release dan no dokument |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | revamp tampilan karna ada filter |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | perbaikan upload excel di atas 1000 data karna limit post data |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Untuk upload full bisa pilih priode tapi lamgsung closed |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Tambahkan form digital claim satuan manual |  | Tunning | Update Feature | Teddy Juanda | Closed | 90% | 4590400% | 4590400% | - | #VALUE! | Project Existing | September, 2025
GL | Modul Inventory - Arus Barang + Auto Billing | 2. Mapping Account Persediaan, HPP | Modul Finance - Arus Barang | Tunning | New Feature | Teddy Juanda & Hariah | Closed | 90% | 4545600% | 4546700% | - | #VALUE! | Project Existing | Juni
GL | Modul Inventory - Arus Barang + Auto Billing | 1. Get Qty dari Dashboard Arus Barang | Modul Finance - Arus Barang | Tunning | New Feature | Teddy Juanda & Hariah | Closed | 90% | 4545600% | 4546700% | - | #VALUE! | Project Existing | Juni
MDBA Kino | NOVA - UPDATE API IDS KINO | post retur api SRE bug |  |  |  | Teddy Juanda | Complete | 100% | 4595000% | 4595100% | 4595100% | 1 | Project Existing | Oktober, 2025
MDBA | Issue MDBA Kasir | Continue - Issue MDBA Depo Kelapa Dua | 1.saldo awal kas kecil berbeda (DONE) 2.BCA KK KLD ada dua, (DONE) 3.saldo awal BCA KK KLD berbeda, (DONE) BTU dan BKU BCA KK KLD tidak masuk ke dalam cover BKU (DONE) 4.Ketika di Update Voucher Saldo Kas menjadi tidak sesuai (DONE) 5.Saldo Awal Kas Kecil Tidak Sesuai (DONE) | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
MDBA | Issue MDBA Kasir | Continue Issue MDBA Kasir - Depo Manis | 1.Settlement Kasir Masih Merah [DONE] 2.Saldo Kas Sementara Depo Manis masih belum sesuai [DONE] | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4529400% | 4529500% | 4529400% | 0 | Project Existing | Januari
MDBA Kino | NOVA - UPDATE API IDS KINO | post api to ids bug |  |  |  | Teddy Juanda | Complete | 100% | 4595000% | 4595100% | 4595100% | 1 | Project Existing | Oktober, 2025
MDBA Kino | NOVA - UPDATE API IDS KINO | get token api bug |  |  |  | Teddy Juanda | Complete | 100% | 4595000% | 4595100% | 4595100% | 1 | Project Existing | Oktober, 2025
MDBA | Issue MDBA Kasir | Issue MDBA Kasir - Pluit | 1.Saldo KK Tidak sesuai tanggal 2 & 3 Januari 2024 | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4529600% | 4529600% | 4529600% | 0 | Project Existing | Januari
GL | FIXING CASE NEWGL TAX | BUG laporan Subledger Overview jika tidak ada desc, text pada pdf menumpuk | Bug fix featur GL | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4593200% | 4593200% | 4593200% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | BUG data indikator call api | Bug fix featur GL | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4593200% | 4593200% | 4593200% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | BUG pada Saldo laporan Account SubLedger | Bug fix featur GL | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4593200% | 4593200% | 4593200% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | update query untuk penambahana account 200401 | Bug fix featur GL | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4593200% | 4593200% | 4593200% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | BUG pada posting jurnal entry duplicate key value violates unique | Bug fix featur GL | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4593200% | 4593200% | 4593200% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | rombak header nama akun jadi nama akun coa (bukan deskripsi) | FIX bug laporan Account Subladger | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4592900% | 4592900% | 4592900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | update query detail list data account subledger | FIX bug laporan Account Subladger | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4592900% | 4592900% | 4592900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | cek logic get ending balance | FIX bug laporan Account Subladger | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4592900% | 4592900% | 4592900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | cek alur login coding golang | FIX bug laporan Account Subladger | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4592900% | 4592900% | 4592900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan laporan LABA-RUGI DETAIL ke excel | New Fitur Laporan Laba-Rugi Montly dengan golang | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan laporan LABA-RUGI RECAP ke excel | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report SUM LABA-RUGI PER TYPE ACCOUNT | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report LABA BERSIH SETELAH PAJAK | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report LABA BERSIH SEBELUM PAJAK | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report LABA-RUGI RECAP DETAIl | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report LABA-RUGI RECAP HADER | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan model laporan laba rugi | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan service laporan laba rugi | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan handler laporan laba rugi | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan halaman ui laporan laba rugi | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan midelwhere menu laporan | New Fitur Laporan Laba-Rugi Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4592200% | 4592300% | 4592300% | 1 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan laporan NR ke excel | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591900% | 4591900% | 4591900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan laporan NRD ke excel | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591900% | 4591900% | 4591900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report Neraca berdasarkan activa dan pasiva | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report NERACA RECAP DETAIL (NR) | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan Query report NERACA RECAP HADER (NR) | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591700% | 4591700% | 4591700% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan model laporan neraca | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591700% | 4591700% | 4591700% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan service laporan neraca | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591600% | 4591600% | 4591600% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan handler laporan neraca | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591600% | 4591600% | 4591600% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan halaman ui laporan neraca | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591500% | 4591500% | 4591500% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | pembuatan midelwhere menu laporan | New Fitur Laporan Neraca Montly dengan golang | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4591500% | 4591500% | 4591500% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | posting jurnal saldo posting balance tidak update dengan saldo bulan sebelumnya | Fixing Bugs New GL | Tunning | Fixing Bugs | Teddy Juanda | Complete | 100% | 4591000% | 4591000% | 4591000% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | input jurnal entri COA hanya di perbolehkan 4, 6, 9 jadi saat ada coa berjumlah digit 7 error | Fixing Bugs New GL | Tunning | Fixing Bugs | Teddy Juanda | Complete | 100% | 4591000% | 4591000% | 4591000% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | posting dan unpust jurnal saldo tidak terbaca di januari | Fixing Bugs New GL | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4590800% | 4590800% | 4590800% | 0 | Project Existing | September, 2025
MDBA | MDBA Kasir - Fixing Bugs Saldo & Cover (Permanent Solution) |  | Fixing Bugs Saldo Kas & Cover untuk permanen solution | Fixing Bugs | Fixing Bugs | Teddy Juanda & Hariah | Complete | 100% | 4530600% | 4531000% | 4553800% | 232 | Project Existing | Januari
MDBA | MDBA Limit Kredit Pelanggan | Masih bisa buat DO ketika batasan limit kredit melebihi batas kredit |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587600% | 4587600% | 4591500% | 39 | Project Charter | Agustus, 2025
MDBA | MDBA Limit Kredit Pelanggan | Tipe penjualan PINJAM, TARIK JAMINAN, TARIK PINJAM tidak perlu validasi limit kredit |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587600% | 4587600% | 4591500% | 39 | Project Charter | Agustus, 2025
MDBA | MDBA Limit Kredit Pelanggan | SO pending masih bisa buat sales order dengan kondisi melebihi batas limit kredit |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587600% | 4587600% | 4591500% | 39 | Project Charter | Agustus, 2025
MDBA | MDBA Limit Kredit Pelanggan | Pelanggan luar rute masih bisa buat sales order dengan kondisi melebihi batas limit kredi |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587500% | 4587500% | 4591500% | 40 | Project Charter | Agustus, 2025
MDBA | MDBA Limit Kredit Pelanggan | Ketika ada kondisi do tunai di ubah ke kredit (inject), masih bisa lolos |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587500% | 4587500% | 4591500% | 40 | Project Charter | Agustus, 2025
MDBA | MDBA Limit Kredit Pelanggan | Ketika ada kondisi 2 so dibuat secara terpisah karena batasan limit kredit masih bisa lolos |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4587500% | 4587700% | 4591500% | 40 | Project Charter | Agustus, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Edit Delivery Order (DO Blank) |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4587500% | 4587700% | 4591500% | 40 | Project Charter | Juni, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Pembuatan Sales Order (Entry) |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4584600% | 4584800% | 4591500% | 69 | Project Charter | Juni, 2025
MDBA KINO | MDBA-NOVA - update patch SO penambahan nama sales | Penambahan nama sales pada tabel SO |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4588200% | 4588200% | 4588700% | 5 | Project Existing | Agustus, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | LINK NEW GL TAX DI SERVER KITA (NON AWS), USER LOGIN, SETTING MENU KHUSUS UNTUK TAX |  | Tunning | Addhock | Teddy Juanda | Complete | 100% | 4587600% | 4588700% | 4588400% | 8 | Project Existing | Agustus, 2025
MDBA | Update Feature MDBA - Hilangkan PPN dan DPP | 2. PINJAM |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587500% | 4587600% | 4587600% | 1 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query list detail so turunan |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by no so induk |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by no so turunan |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by tanggal so |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query grid so |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query list detail do turunan |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by no do induk |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by no do turunan |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query pencarian by tanggal do |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA-TVIP ADDHOOK | update query grid do |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4587100% | 4587100% | 4587100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | entry menjadi unposted) |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585900% | 4585900% | 4588700% | 28 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | Jurnal Temprary To Entry (TTE) ( fitur ini hanya merubah status Jurnal temporart to |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585900% | 4585900% | 4588700% | 28 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master Produk : membuat query dan set ke view Produk |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master Produk : membuat view list Produk |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master users : membuat query dan set ke view users |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master users : membuat view list users |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master segmengt : membuat query dan set ke view segment |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master segment : membuat view list segment |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585700% | 4585700% | 4588700% | 30 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master divisi : membuat query dan set ke view depo |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master divisi : membuat view list divisi |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master role : membuat query dan set ke view role |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master role : membuat view list role |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master depos : membuat query dan set ke view depo |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | master depos : membuat view list depo |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | setup datatable + exstensi yajra untuk performa query laravel |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585600% | 4585600% | 4588700% | 31 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | login : proses login simpan ke session laravel |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585500% | 4585500% | 4588700% | 32 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | login : membuat koneksi API login dengan login EIS |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585500% | 4585500% | 4588700% | 32 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | login : membuat routing login |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585500% | 4585500% | 4588700% | 32 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | login : membuat views login |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585500% | 4585500% | 4588700% | 32 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | setup laravel singel pages / SPA (only ajax) |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585400% | 4585400% | 4588700% | 33 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | templating admin dashboard |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585400% | 4585400% | 4588700% | 33 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | setup dan koneksi konection ke database aws |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585400% | 4585400% | 4588700% | 33 | Project Existing | Juli, 2025
MDBA | MDBA - aplikasi support new GL laravel 12 | install dan setup laravel |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4585400% | 4585400% | 4588700% | 33 | Project Existing | Juli, 2025
MDBA | MDBA - NEW FEATURE PO MT | 1 PO masih bisa deng |  | New Project | Fixing Bugs | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Upload dengan kondisi kode depo berbeda dengan session masih bisa tidak sesuai |  | New Project | Fixing Bugs | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Masih bisa upload no PO yang sama dari yang sebelumnya |  | New Project | Fixing Bugs | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | 1 PO masih bisa dengan kondisi JUAL & FOC, seharusnya tidak bisa |  | New Project | Fixing Bugs | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Tanggal pesan & tanggal expired tidak sesuai |  | New Project | Fixing Bugs | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | menampilkan data admin pusat untuk seluruh depo |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat tampilan detail data header dan detail |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi untuk depo pusat boleh hapus data by dokument upload depo lain |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi data header dan detail pada excel |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi untuk depo pusat boleh hapus data satuan depo lain |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi data excel tidak boleh ada data duplikat |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | tandai sudah diproses |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Validasi only header : Jika szNoFpp belum diproses, tambahkan ke header dan |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Validasi NoFpp -> hanya boleh 1 AccountId ( 1 po ¦ 1 do) |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583200% | 4586900% | 4588000% | 48 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Validasi type order hanya satu jenis |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi untuk depo pusat boleh input depo lain |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | convert tanggal order dan expaired data excel |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi semua NoFpp dari Excel dan cek ke database tidak boleh duplicate |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Cek apakah ada data kosong (null) selain baris header excel |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi file csv dan Xlsx |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4583100% | 4586900% | 4588000% | 49 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | validasi data excel sesuai dengan template yang sudah di sediakan |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat tabel header dan detail po mt |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat form upload po-mt |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat preview excel po-mt |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat download template excel po-mt |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat design grid list data po-mt |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | membuat hak akses admin pusat dan admin depo |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4582900% | 4586900% | 4588000% | 51 | Project Charter | Juni, 2025
GL | Task From Zoom GL 14 Juli 2025 | Pengecekan Harga Github |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585500% | 4591600% | 64 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | membuat simpan data multiple produk |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | membuat validasi data di input tidak boleh sama dengan produk yang sudah di input di list daftar input produk |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | auto migrasi ( langsung insert ke mdba) dan sebaliknya jika dms yang kosong dan mdba yang memiliki data (insert ke dms) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | membuat logic jika produk di databse mdba kosong tetapi di dms ada data produk itu |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | dengan data yang sudah ada di database foc berdasarkan customer dan id produk |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | membuat validasi input produk tidak boleh sama |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA - TVIP UPDATE FEATURE MULTIPLE FOC | membuat form data input produk multiple foc |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4585200% | 4585300% | 4585300% | 1 | Project Existing | Juli, 2025
MDBA | MDBA-ADDHOOK-BBM |  |  | Tunning | Addhock | Teddy Juanda | Complete | 100% | 4584800% | 4584800% | 4584800% | 0 | Project Existing | Juli, 2025
MDBA | MDBA ASA-TVIP ADHOOK-PERMINTAAN BBM NON BKB | perhitunggan bbm non bkb ada selisih 20 perak |  | Tunning | Addhock | Teddy Juanda | Complete | 100% | 4584900% | 4584900% | 4584900% | 0 | Project Existing | Juli, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 1. Seeding data ASA Jan-Apr 2025 to NEW GL Server 168 | ASA | Tunning | Addhock | Teddy Juanda | Complete | 100% | 4582800% | 4582800% | 4582800% | 0 | Project Existing | Juni, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 1. Seeding data TVIP Jan-Apr2025 to NEW GL Server 168 | TVIP | Tunning | Addhock | Teddy Juanda | Complete | 100% | 4582700% | 4582700% | 4582700% | 0 | Project Existing | Juni, 2025
MDBA KINO | MDBA-NOVA Bug fixing print validasi 1 x print |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4582900% | 4583100% | 4583200% | 3 | Project Existing | Juni, 2025
MDBA | MDBA - Retur DO degan type PINJAM, TARIK PINJAM dan TARIK JAMINAN | Retur DO(plus) type TARIK PINJAM akan insert atau update stok loan balance dan insert loan transaction (IN) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4581800% | 4582000% | 4581900% | 1 | Project Existing | Juni, 2025
MDBA | MDBA - Retur DO degan type PINJAM, TARIK PINJAM dan TARIK JAMINAN | Retur DO(plus) type PINJAM akan insert atau update stok loan balance dan insert loan transaction (out) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4581800% | 4582000% | 4581900% | 1 | Project Existing | Juni, 2025
MDBA | MDBA - Retur DO degan type PINJAM, TARIK PINJAM dan TARIK JAMINAN | Retur do (minus) type TARIK PINJAM akan menambah stok loan balance dan insert loan transaction (in) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4581800% | 4582000% | 4581800% | 0 | Project Existing | Juni, 2025
MDBA | MDBA - Retur DO degan type PINJAM, TARIK PINJAM dan TARIK JAMINAN | Retur do(minus) type PINJAM akan mengurangi stok loan balance dan insert loan transaction (out) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4581800% | 4582000% | 4581800% | 0 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | PRINT : DO reguler Range di tambahkan field text Harga jual tertera diatas |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | PRINT : DO reguler di tambahkan field text Harga jual tertera diatas termasuk PPN 11% |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : new fitur histori do pinjam dengan saldo dan in out |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO TERMIN : new fitur upload data dan set up termin |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : new fitur histori do pinjam - upload view |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : new fitur termin - upload view |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : void dan unvoid DO dengan tipe Tarik pinjam update stok loan balance dan insert ke history |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : void dan unvoid DO dengan tipe pinjam update stok loan balance dan insert ke history |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO: view edit Do all type |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : view Tambah Do reguler |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : updaet DO reguler dengan type pinjam |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | Validasi Counter DO - KLD, MNS | DO Input (teddy) | Validasi DO Counter | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | Validasi Counter DO - KLD, MNS | DO PB Risk (teddy) | Validasi DO Counter | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | Validasi Counter DO - KLD, MNS | DO Std (teddy) | Validasi DO Counter | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | Validasi Counter DO - KLD, MNS | DO Retur (teddy) | Validasi DO Counter | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | UPLOAD MINGGU - Buy n Sell to production | DO : Tambah DO reguler dengan type pinjam |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | STD PENDING : set full counter memisahkan item PB dengan type jual pada galon kosong |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | STD : menambahkan type order jual pada produk galon kosong |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | STD : menambahkan type order pinjam |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | Validasi Counter DO - KLD, MNS | Alert DO retur mines disamakan dengan alert DO bentrok (teddy) | Fixing Bugs | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | Validasi Counter DO - KLD, MNS | Pada saat submit DO retur baru, tidak tampil action jika DO bentrok | Fixing Bugs | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | MDBA - New Feature SO Retur Pabrikan |  | New Feature Retur SO Pabrikan Pembuatan Menu SO Manual ini diperuntukan apabila ada retur karena kesalahan dari depo (admin) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4530400% | 4530900% | 4530900% | 5 | Project Existing | Januari
MDBA | UPLOAD MINGGU - Buy n Sell to production | SO : menambahkan type order jual pada produk galon kosong |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | UPLOAD MINGGU - Buy n Sell to production | SO : menampahkan type order Pinjam |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4580800% | 4580900% | 4580900% | 1 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | Print Do & Invoice (Harga jual tertera diatas termasuk ppn 11%) |  | Tunning | Update Feature | Teddy Juanda, Della | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | New Feature Pinjam Galon (Tempo |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | STD Cancel & Pending |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | DO Reguler (Insert & Update) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | PB & BKB |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | STD |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | SO Manual Entry |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | Jaminan Di Hidden After 2 Juni |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Upload Data JM ke Database sql server |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Detail Description JM berdasarkan tabggal dan depo |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Reset JM berdasarkan tanggal dan depo |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Upload Data VB VT ke Database MDBA-Histori |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Detail description VB VT berdasarkan tanggal dan depo |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | Reset VB dan VT berdasarkan tanggal,dan depo |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | 5. backup ke git (error karan pakai windows 7 ) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4579700% | 4581800% | 4588200% | 85 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | sub detail jurnal | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579900% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | reset filter jurnal temporary | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579800% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | filter jurnal temporary by depo | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579800% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | filter jurnal temporary by type jurnal | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579800% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | filter jurnal temporary by tanggal range | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579700% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | reframe login gl | Fiture Gl | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Detail data Jurnal (JM) berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Upload data jurnal (JM) Gl berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Reset data jurnal (JM) GL berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Detail data history (JM) berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Upload data history (JM) berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Reset data history (JM) berdasarkan depo dan tanggal | Taks Jurnal (LA/JM) | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Detail data Jurnal (vb-vt) berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Upload data jurnal (vb-vt) Gl berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Reset data jurnal (vb-vt) GL berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Detail data history (vb-vt) berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Upload data history (vb-vt) berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | Reset data history (vb-vt) berdasarkan depo dan tanggal | Taks VB & VT | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4579100% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | cloning database gl tvip ke gl nova (history dan sqlserver) |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4580600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | cloning coding di gl tvip ke gl nova |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4579100% | 4580600% | 4588200% | 91 | Project Existing | Mei, 2025
MDBA | MDBA - DTC to Surat Jalan Pelanggan | BI Portal (DTC) | Update Query BI Portal tanpa ke Pool | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4578500% | 4578700% | 4578500% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - DTC to Surat Jalan Pelanggan | Surat Jalan Pelanggan (DTC) | Detail SJP | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4578500% | 4578700% | 4578500% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - DTC to Surat Jalan Pelanggan | Surat Jalan Pelanggan (DTC) | Print SJP | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4578500% | 4578700% | 4578500% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - DTC to Surat Jalan Pelanggan | Surat Jalan Pelanggan (DTC) | Input SJP | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4578500% | 4578700% | 4578500% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - DTC to Surat Jalan Pelanggan | Surat Jalan Pelanggan (DTC) | Input DO Surat Jalan Pelanggan | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4578500% | 4578700% | 4578500% | 0 | Project Existing | Mei, 2025
MDBA KINO | MDBA NOVA - Approval DO Retur (+) New Feature |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4577700% | 4577700% | 4577700% | 0 | Project Existing | April, 2025
GL | Devlop New GL Bahasa-golang |  |  | Tunning | Dokumentasi | Teddy Juanda | Complete | 100% | 4575600% | 4576600% | 4588700% | 131 | Project Existing | April, 2025
MDBA | MDBA - Permintaan BBM Armada Backup Reguler |  |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4574000% | 4575400% | 4574000% | 0 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Jika order kurang dari 5 jt setelah harga W tidak dapat submit di SFA tampil alert untuk memberikan informasi jika pelanggan tidak dapat harga W |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Cash Diskon / Diskon Distributor (Persentase) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Untuk STD di buatkan feature checklist SO DI MDBA Nova Kino |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA | MDBA - Permintaan BBM Detail |  |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4571000% | 4571000% | 4571000% | 0 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Applied DO Tunai | Invoice | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571400% | 4571400% | 12 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Mekanisme Promo Drop Size Delivery Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571400% | 4572600% | 24 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Mekanisme Promo Drop Size Sales Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571400% | 4572600% | 24 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | DO Pending | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4572300% | 4576200% | 60 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Cancel STD | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4572300% | 4576200% | 60 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Permintaan Barang | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4570800% | 4572600% | 24 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Edit Delivery Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571900% | 4572600% | 24 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Print DO | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571900% | 4572600% | 24 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Input Delivery Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4571900% | 4576200% | 60 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Surat Tugas Delivery (REG & STTO) | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4570700% | 4572600% | 24 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Sales Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4570900% | 4572600% | 24 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - Mekanisme diskon (New Feature) | Reg do kolom discount dimunculkan detail |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4572300% | 4572800% | 4575400% | 31 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Mekanisme diskon (New Feature) | Penambahan kolom diskon all untuk di split perproduk (Hitungan dalam % dari total) |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4572300% | 4572800% | 4575400% | 31 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Mekanisme Promo (Feature Baru) |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570200% | 4570200% | 4572700% | 25 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | cancel SRE |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | detail SRE |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | List Data & Detail Invoice Retur History MDBA |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | posting retur/ SRE to IDS |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | View tampilan detail SO |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - New Feature Retur Order | call api data retur dari api kino |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4570000% | 4570600% | 4570000% | 0 | Project Existing | Februari 2025
Gl | Fixing Bugs GL TVIP - ASA |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4569200% | 4570100% | 4570100% | 9 | Project Existing | Februari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | update fitur PB- BKB include item produk terdapat kolom BTK |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | update fitur std - DO include item produk terdapat kolom BTK |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | update fitur std - PB include item produk terdapat kolom BTK |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | update fitur shipment to so include item produk terdapat kolom BTK |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | adjust bkb distribusi tidak update counter dokument adjustnya **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Pada saat pengajuan DO Retur dan submit DO mines nya, terjadi stuck loading saja **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Edit DO terdapat validasi galon **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568800% | 3 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | BTB supplier terdapat null item setelah inputan row ke 2 **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568800% | 3 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Ketika input std do pending, terinsert PB Mix **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Validasi shipment retur **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Print Do Nova Di Update Menyesuaikan UOM |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Ketika melakukan adjusment, pada saat edit STD tidak terbuat new PB (Permintaan Barang) **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Ketika melakukan adjustment, pada saat submit bkb minusnya terjadi double item **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568500% | 0 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | STD Mengikuti QTY SO dari UOM **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Adjusment BTB distribusi terdapat null item setelah jika ada delete row **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | BTB distribusi terdapat null item jika ada delete row **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | BTB Depot terdapat null item jika ada delete row |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4569100% | 6 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | BKB Depot terdapat null item jika ada delete row |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4569100% | 6 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Adjusment BTB Supplier qty harusnya terbaca karton |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4569100% | 6 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Invoice To IDS Update shipment untuk produk yang tidak di jual (qty 0) **DONE** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4568700% | 2 | Project Existing | Januari 2025
MDBA KINO | New Feature dan Update MDBA NOVA | Request BTB distribusi automatis input SKU berdasarkan DO |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4568500% | 4569500% | 4569100% | 6 | Project Existing | Januari 2025
MDBA KINO | MDBA NOVA - API KINO | Config max send shipment by invoice |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4567100% | 4567400% | 4568100% | 10 | Project Existing | Januari 2025
MDBA KINO | MDBA NOVA - API KINO | Post Shipment Invoice |  | New Project | New Feature | Teddy Juanda | Complete | 100% | 4567100% | 4567400% | 4568100% | 10 | Project Existing | Januari 2025
MDBA | MDBA Kasir - Voucher Permintaan BBM Awal |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4566000% | 4566300% | 4566300% | 3 | Project Existing | Januari 2025
MDBA KINO | MDBA NOVA - KINO | BKB Auto by STD | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Permintaan Barang | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Delivery Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Surat Tugas Delivery | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Sales Order | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA NOVA - KINO | Shipment API | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Complete | 100% | 4565600% | 4569000% | 4569000% | 34 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | detail item shipment jadi item price dan item so | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | header shipment jadi header so | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | fitur filter shipment data to list grid data shipment | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | view list shipment data | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | save header shipment dan detail by shipment api kino | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | call api Shipment by validasi token | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA | MDBA BBM - Upload Data Excel BKB Ritase & Update Master KM | Data rekap BBM Ritase yang tidak bisa di input saat terjadi maintanance server | Fixing Bugs | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4530800% | 4530800% | 4530800% | 0 | Project Existing | Januari
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | membuat master tabel shipment detai produk dari api kino save ke DB | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | membuat master tabel shipment dari api kino save ke DB | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | membuat master tabel token dari api kino save ke DB | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | Get token dan save saat login di mdba | INTEGRASI MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | GET SHIPMENT KINO | API KINO | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA KINO | MDBA_KINO : API KINO DAN API MDBA | POST TOKEN KINO | API KINO | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4565400% | 4565600% | 4577000% | 116 | Project Existing | Desember
MDBA | MDBA All - Config PPN | DO (Reg & Non Rute) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4565600% | 4565900% | 4565900% | 3 | Project Existing | Desember
MDBA | MDBA All - Config PPN | CRL (SO & SO Pending) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4565600% | 4565900% | 4565900% | 3 | Project Existing | Desember
MDBA KINO | MDBA NOVA - Additional Feature | 5. Tambahkan shortcut untuk melakukan penambahan produk (SO, DO & BTB) |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4564200% | 4564400% | 4564400% | 2 | Project Existing | Desember
MDBA KINO | MDBA NOVA - Additional Feature | 4. Insert DO, jika diskon lebih besar dari harga, total harga tidak clear |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4564200% | 4564400% | 4564400% | 2 | Project Existing | Desember
MDBA KINO | MDBA NOVA - Additional Feature | 3. Insert SO, jika diskon lebih besar dari harga, total harga tidak clear |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4564200% | 4564400% | 4564400% | 2 | Project Existing | Desember
MDBA KINO | MDBA NOVA - Additional Feature | 2. Hilangkan config DO |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4564200% | 4564400% | 4564400% | 2 | Project Existing | Desember
MDBA KINO | MDBA NOVA - Additional Feature | 1. Hilangkan config SO |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4564200% | 4564400% | 4564400% | 2 | Project Existing | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Ubah nama gudang TVIP menjadi NOVA | Update MOM MDBA KINO | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563000% | 4563000% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Validasi tolak bkb sebelum BTU di hilangkan | Update MOM MDBA KINO | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563000% | 4563000% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | membuat validasi login dengan client dari kino | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | membuat validasi shimpent to ids berdasarkan tgl closing depo | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | membuat config expired shipment invoice to ids | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | New Scheduler untuk 1K, 1M, JM | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Perubahan PB & BKB | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4562100% | 4562500% | 4569400% | 73 | Project Charter | November
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Perubahan DO (CRUD) | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4562100% | 4562500% | 4569400% | 73 | Project Charter | November
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Perubahan STD | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4562100% | 4562500% | 4569400% | 73 | Project Charter | November
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Perubahan SO | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Teddy Juanda | Complete | 100% | 4562100% | 4562500% | 4569400% | 73 | Project Charter | November
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | DO Void masih bisa dilakukan pending, tambahkan validasi |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4563200% | 4563200% | 4563200% | 0 | Project Existing | Desember
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Tambahkan function jika input produk canvas delivery, jumlah qty include ke rincian produk **(DONE)** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4563200% | 4563200% | 4563200% | 0 | Project Existing | Desember
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Terjadi anomali data, SO blank tidak ada headernya, szPriceId "TVIP-C_00" yang membuat tampilan DO Blank menjadi ada qty SO di tarikan query **(DONE)** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4563200% | 4563200% | 4563200% | 0 | Project Existing | Desember
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Fitur DO pending per Driver |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4563200% | 4563200% | 4563200% | 0 | Project Existing | Desember
MDBA | MDBA - Persiapan MDBA All Depo (SRG, KDY, PLT, LDN) | Lock Voucher BBM masa pemakaian hanya H+3 |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4560700% | 4561100% | 4561100% | 4 | Project Existing | November
MDBA | MDBA - Persiapan MDBA All Depo (SRG, KDY, PLT, LDN) | Void PB STD Reguler (Kebutuhan AFH) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4560700% | 4561100% | 4561100% | 4 | Project Existing | November
MDBA | MDBA - Persiapan MDBA All Depo (SRG, KDY, PLT, LDN) | DO Retur config lock |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4560700% | 4561100% | 4561100% | 4 | Project Existing | November
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Jika ada penginputan FOC di menu DO SO dan Edit DO, tidak mengurangi stok konfigurasi FOC |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Edit DO Mix (Galon & SPS) bisa double SKU yang sama **(DONE)** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Tambahkan fitur input DO pending per driver |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Tambahkan detail diskon dan harga pada tampilan saat ceklist STD ***(DONE)*** |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
MDBA | MDBA - Fixing Bugs Print DO (Lebih dari 10 SKU) |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4558000% | 4558000% | 4558000% | 0 | Project Existing | Oktober
MDBA | MDBA Entry - STD auto jugrak PB |  |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4558600% | 4559300% | 4562100% | 35 | Project Existing | Oktober
MDBA | MDBA Entry - New Feature Config Edit DO (Mix Galon & SPS) | 1. Config DO dari STD |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557400% | 4557600% | 4557600% | 2 | Project Existing | Oktober
MDBA | MDBA Entry - New Feature Monitoring SO CRL |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557500% | 4557500% | 4557500% | 0 | Project Existing | Oktober
MDBA | MDBA Gudang - New Feature Config PB Risk |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557500% | 4557500% | 4557500% | 0 | Project Existing | Oktober
MDBA | MDBA BBM (New Feature) - Penambahan approval BBM | Approval untuk pengisian BBM kendaraan baru |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4558900% | 4556900% | 4565000% | 61 | Project Existing | Oktober
MDBA | MDBA Entry - Fixing Bugs STD | 2. Jika ada produk FOC (BOX), Error counter duplicate |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4555800% | 4556000% | 4555800% | 0 | Project Existing | September
MDBA | MDBA Entry - Fixing Bugs STD | 1. DO Pending bisa double dalam beberapa STD |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4555800% | 4556000% | 4555800% | 0 | Project Existing | September
MDBA | MDBA Support - New Feature Tools Support ICT | Config Do Retur Backdate ***(DONE)*** |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557800% | 4557800% | 4557800% | 0 | Project Existing | Oktober
MDBA | MDBA Support - New Feature Tools Support ICT | Salah menginput kilometer (update ke LHP) pada tool support WATEROUT |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557800% | 4557800% | 4557800% | 0 | Project Existing | Oktober
MDBA | MDBA Support - New Feature Tools Support ICT | Salah menginput kilometer (update ke LHP) pada tool support MDBA |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4557600% | 4557600% | 4557600% | 0 | Project Existing | Oktober
MDBA | MDBA Entry - SO Mix by Promo | Crud Config SO By SO Mix by Promo (ada di Tools Support) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA Kasir - Fixing Bugs Closing Voucher Saldo & Cover (Permanent Solution) |  | Fixing Bugs | Fixing Bugs | Fixing Bugs | Teddy Juanda & Hariah | Complete | 100% | 4530600% | 4531000% | 4553500% | 229 | Project Existing | Januari
MDBA | MDBA Entry - SO Mix by Promo | Create SO by Entry |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA - New Feature Config All (TVIP & ASA) | DO Canvas Issue Lebih Dari 5(60%) |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4551600% | 4553400% | 4552600% | 10 | Project Existing | Agustus
MDBA | MDBA - New Feature Config All (TVIP & ASA) | Maksimal input Qty DO CANVAS |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4551600% | 4553400% | 4552600% | 10 | Project Existing | Agustus
MDBA | MDBA - New Feature Config All (TVIP & ASA) | Maksimal input Qty SO CRL |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4551600% | 4553400% | 4552600% | 10 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 9. Update std delivery menjadi std delivery canvas jika ada do pending canvas disisipkan ke dalam std **(DONE)** |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550900% | 4551800% | 4551800% | 9 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 6. DO Pending dengan tipe MT/IOD atau kode D bisa lebih dari 5 **(DONE)** |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550900% | 4551700% | 4551700% | 8 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 4. Penambahan validasi DO Pending jika DO tersebut sudah ada di STD saat itu (dalam 1 std yang sama) |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550900% | 4551300% | 4551300% | 4 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 3. Penambahan field szmobilestatus untuk penanda depo tersebut hh atau non hh |  | Tunning | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550900% | 4551000% | 4551000% | 1 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 2. Penambahan DO Canvas Delivery by Tanggal pada saat input STD Delivery dan Edit |  | Tunning | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550900% | 4551000% | 4551000% | 1 | Project Existing | Agustus
MDBA | MDBA Entry - SO dengan tipe sku FOC, di STD (Fixing Bugs) | 1. Bugs STTO jika di masukan kedalam std bisa berkali-kali dan terjadi double SO |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4550500% | 4551900% | 4553800% | 33 | Project Existing | Agustus
MDBA | MDBA Cashier BBM - Lock Cancel BBM (Apabila sudah terbuat BTU) | 3. Ketika BKU di Void, bisa cancel permintaan BBM |  | Tunning | Update Feature | Teddy Juanda & Hariah | Complete | 100% | 4549500% | 4550200% | 4549700% | 2 | Project Existing | Juli
MDBA | MDBA Cashier BBM - Lock Cancel BBM (Apabila sudah terbuat BTU) | 2. Jika sudah ter BTU tidak bisa cancel permintaan BBM |  | Tunning | Update Feature | Teddy Juanda & Hariah | Complete | 100% | 4549500% | 4550200% | 4549700% | 2 | Project Existing | Juli
MDBA | MDBA Cashier BBM - Lock Cancel BBM (Apabila sudah terbuat BTU) | 1. Ketika BKU di Void, list BBM tidak tampil BKU nya lagi |  | Tunning | Update Feature | Teddy Juanda & Hariah | Complete | 100% | 4549500% | 4550200% | 4550000% | 5 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 6. New Feature Support ICT -> Update status BKB | Update Training MDBA | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4550200% | 4550400% | 4550200% | 0 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 5. Penambahan status depo menggunakan HH dan Non HH | Update Training MDBA | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4550200% | 4550400% | 4550200% | 0 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 4. Perubahan template hasil print dengan no whatsapp berdasarkan depo masing-masing | Update Training MDBA | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4550200% | 4550400% | 4550200% | 0 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 2. Ketika sudah BKB lalu backup driver, DO Canvas std tidak update driver dan nopolnya. | Update Training MDBA | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4550200% | 4550400% | 4550200% | 0 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 1. Bugs jika ada SO dengan tipe sku FOC, di std (detprodukstd double) dan PB tidak sesuai qtynya | Update Training MDBA | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4550200% | 4550400% | 4550500% | 3 | Project Existing | Juli
MDBA | MDBA Entry - Auto link detail DO Settlement | jika do sudah applied maka data hanya bisa melihat detail data |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4548800% | 4549000% | 4548900% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Auto link detail DO Settlement | bisa edit do jika gen closing open |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4548800% | 4549000% | 4548900% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Auto link detail DO Settlement | Detail kasir |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4548800% | 4549000% | 4548900% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Auto link detail DO Settlement | Detail Gudang |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4548800% | 4549000% | 4548900% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 7. DO Retur | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 6. Edit DO | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 5. DO Input | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 4. SO Induk | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 8. print di format DO di tambahkan (frm SO) ke production | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 7. meloloskan Kendaraan dengan id : ('INTERN', 'PRESELLER', 'SPV', 'MOTORIS','DRIVER JEMPUT','COUNTER') untuk seluruh depo | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 6. unlock kendaraan di master kilometer BBM | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 5. Unlock validasi kendraan jika kategori & status "Null" | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 4. Menambahkan validasi jika masterkilometer kendaraannya inactive | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 3. Menambahkan validasi jika tidak ada nopol di masterkilometer | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 2. Unlock validasi kendaraan dengan tipe nopol (INTERN, COUNTER EKSTERNAL, PRESELLER, SPV, PABRIKAN) | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA Kasir - Fixing Bugs After Implementasi Validasi BKB by Kendaraan | Fixing Bugs After Implementasi | 1. Kendaraan tidak sesuai dengan bkb | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4546800% | 4547100% | 4547100% | 3 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Pada saat pending status bisa dijadikan void | Permintaan dari Bu yuyun tetapi untuk saat ini masih bisa di handle task tersebut jarang terjadi | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4550400% | 4570200% | 239 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | STD DO Pending dibuat mandatori di saat closing ritase (Update DO Pending Tanggal Berikutnya) | Permintaan dari Bu yuyun tetapi untuk saat ini masih bisa di handle task tersebut jarang terjadi | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4550400% | 4570200% | 239 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Lock BKB selanjutnya tambahkan pengecekan BTB Distiribusi | Permintaan dari Bu yuyun tetapi untuk saat ini masih bisa di handle task tersebut jarang terjadi | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4550400% | 4570200% | 239 | Project Existing | Juni
MDBA | MDBA - DO Induk Duplicate (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4545500% | 4545500% | 4545500% | 0 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 25. Validasi DO Canvas dari STD berdasarkan segment |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 24. do canvas non-rute bisa di tambah ke std delivery canvas |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546400% | 4546400% | 4548100% | 17 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 23. memvalidasi segment ( D ) lebih dari max 5 do |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4546300% | 4548100% | 18 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 22. Validasi ketika pending DO Canvas tidak boleh > 5 berdasarkan segment |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4546300% | 4548100% | 18 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 21. Tambahkan alert jika klik button detail di menu std unceklist |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4546300% | 4548100% | 18 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 20. Tambah validasi untuk input SKU jika ada stok canvas |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546200% | 4546200% | 4548100% | 19 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 19. do canvas std terpending insert ke dokument std baru |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546200% | 4546200% | 4548100% | 19 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 18. Ketika STD di edit dari non mix menjadi mix, lalu ceklist DO Canvas, DO tersebut menghilang dari STD |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546300% | 4546300% | 4548100% | 18 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 17. DO canvas di pending s/d 1 bulan di tanggal 10 bulan berikutnya |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546200% | 4546400% | 4548100% | 19 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 16. do canvas to list history cancel |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4546200% | 4546300% | 4548100% | 19 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 15. penambahan form edit std |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 14. menampong do yang batal dari std ke History STD DO UN-Checklist |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 13. membuat menu view list std pendig khusus do std canvas |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 12. penambahan type do baru DO delivery -canvas pada do pending |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 11. menampung do canvas yang batal untuk bisa di add ke dalam list std pending |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 10. update type doccall jika merupakan std delivery canvas atau reguler |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 9. penambahan stock canvas jika ada penambahan canvas std |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 8. hapus stok canvas jika batal pembuatan canvas std |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 7. logic batal canvas pada edit std |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 10. perubahan status header STD / doccal menjadi type canvas (baik insert dan edit) |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 6. logic pada insert dan edit perubahan counter DO jika ada canvas dari std |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 5. view insert dan edit penambahan canvas dengan penginputan jumah do |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545800% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 4. validasi max do canvas non rute max 5 do / hari |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 3. internalnumber doccal item duplicate |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 2.proses crud std canvas |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 1. view canvas DO |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 3. Kendaraan inanctive masih bisa di simpan | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 2. Select option kendaraan tidak tampil data saat melakukan pencarian | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 1. Pada saat memilih driver, kendaraan dalam kondisi parkir menu pb risk hanya loading saja | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 8. BKB Non 1 Siklus | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 5. Adjusment BKB New (1 Siklus & Non 1 Siklus) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 4. Backup Driver (1 Siklus) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 3. Surat Tugas Delivery (1 Siklus) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 2. PB (Non 1 Siklus) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 1. PB Risk (1 Siklus) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Lock Proses pembuatan BKB (backup driver to std) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Lock Proses pembuatan BKB non satu siklus (pebuatan bkb pada pb) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Lock Proses pembuatan BKB satu siklus (pebuatan bkb pada std) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Lock Proses pembuatan BKB satu siklus (pebuatan bkb pada pb risk) | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Ditambahkan Note ** Catatan ** pada print cover | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA - Update Query Load Lama (Fixing Bugs) | List Data BKB - MDBA 1 Siklus |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | 2. Tambahkan reset qty pada saat produk tidak terdaftar di master agar tidak busa submit |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542600% | 1 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | 1. BKB Antar depo masih get data dari mdba, pindahkan ke dms untuk get data stok |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542600% | 1 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BKB Supplier |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Distribusi Penjualan - Print DO |  | Update Feature | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4533400% | 4533800% | 4533500% | 1 | Project Existing | Februari
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BTB Supplier |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BKB Distribusi |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BTB Distribusi |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BKB Depot |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Gudang - Validasi Stock BTB & BKB | BTB Depot |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4542500% | 4542900% | 4542900% | 4 | Project Existing | Mei
MDBA | MDBA Kasir - Data tidak sesuai saat submit (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4542600% | 4542800% | 4542800% | 2 | Project Existing | Mei
MDBA | MDBA Kasir - Rembes BBM | 4. Nominal uang reimburse masih belum sesuai |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4541200% | 4541100% | 4544300% | 31 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | 3. Pengajuan yang salah lalu di reject, bisa dilakukan pengajuan lagi kecuali approve |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4541200% | 4541100% | 4544300% | 31 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | 2. Jika ada notif ID permintaan telah dalam list, lalu tambahkan refresh halaman |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4541200% | 4541100% | 4544300% | 31 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | 1. Setelah melakukan pencarian lalu klik menu pengajuan reimburse, lalu back, data tidak ditemukan. |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4541200% | 4541100% | 4544300% | 31 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | Approval SPV Admin |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4540400% | 4541100% | 4544300% | 39 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | Pengajuan BBM oleh Kasir |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4540400% | 4541100% | 4544300% | 39 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | Pembuatan tabel untuk rembes bbm |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4540400% | 4541100% | 4544300% | 39 | Project Existing | April
MDBA | MDBA Gudang - Validasi Stock BKB Depot (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4539700% | 4539900% | 4539800% | 1 | Project Existing | April
MDBA | MDBA - Update History Reset ODO (Support ICT) |  |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4538600% | 4538700% | 4538600% | 0 | Project Existing | April
MDBA | MDBA - Integrasi Piutang FAR | Print baru muncul setelah di approval oleh kepala depo (bm) |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA BBM - Cetak Voucher |  | New Feature | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4533400% | 4533600% | 4544300% | 109 | Project Existing | Februari
MDBA | MDBA - Integrasi Piutang FAR | Form Preview Dokumen di tolak semua dan dibuatkan alert untuk mengetahui list mana yang salah (NIK yang tidak terdaftar) |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA BBM - Tunning Permintaan Kendaraan Baru |  | Update Feature | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4532900% | 4533400% | 4533400% | 5 | Project Existing | Februari
MDBA | MDBA - Integrasi Piutang FAR | List data karyawan yang muncul hanya yang aktif saja (1 bulan terakhir dari tanggal penggajian & Incentive) |  | New Project | Update Feature | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
GL | GL - Support GL |  | New Feature | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4532900% | 4533100% | 4533400% | 5 | Project Existing | Februari
MDBA | MDBA - Integrasi Piutang FAR | 9. Approval BM tidak ada di list FAR PB Risk (Auto) |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 8. Tambah FAR Auto pada saat tambah detail masih bisa double klik |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 7. Upload excel masih bisa double klik pada saat submit upload |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 6. Tambah detail masih bisa double klik |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 5. Jika detail masih kosong, BM tidak bisa melakukan approval. Tambahkan alert pada saat melakukan approval |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 4. Jika NIK tidak salah/terdaftar, tambahkan alert pada saat preview |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 3. Setelah upload namun gagal, clear choose file menjadi tampilan awal |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 2. Jika ada inputan far dan excel far dijadikan satu dalam pengajuan, nominal masih bisa melebihi piutang (manual) |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
MDBA | MDBA - Integrasi Piutang FAR | 1. Master Piutang Far, kolom masih bisa kosong (Tambahkan required yang dibutuhkan saja) |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4538400% | 4538600% | 4581100% | 427 | Project Charter | April
GL | GL - API Realtime LA1, LA2, LA3 |  |  | Tunning | Update Feature | Teddy Juanda & Hariah | Complete | 100% | 4537100% | 4537300% | 4537800% | 7 | Project Existing | Maret
GL | GL - Testing Zero One |  |  | Tunning | Update Feature | Teddy Juanda & Hariah | Complete | 100% | 4537100% | 4537800% | 4578300% | 412 | Project Existing | Maret
MDBA | MDBA Entry - Retur Tarik Jaminan (Fixing Bugs) |  |  | Fixing Bugs | Update Feature | Teddy Juanda | Complete | 100% | 4536300% | 4536500% | 4536500% | 2 | Project Existing | Maret
MDBA | MDBA - All Transaksi Hide Button |  |  | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4535100% | 4535900% | 4535900% | 8 | Project Existing | Februari
MDBA | MDBA Entry - Update Query Retur (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4535200% | 4535200% | 4535200% | 0 | Project Charter | Maret
MDBA | MDBA BBM - Update Query List Data (Fixing Bugs) |  | Update query pada list data yang menyababkan loading lama pada sisi user | Tunning | Update Feature | Teddy Juanda | Complete | 100% | 4533500% | 4533700% | 4533700% | 2 | Project Existing | Februari
MDBA | MDBA Support - Update Counter DO |  | Apabila ada ketidaksesuai counter DMS VS MDBA di tabel DocDo dan tabel Counter | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4534100% | 4534300% | 4534300% | 2 | Project Existing | Februari
MDBA | Issue MDBA - Surat Tugas Delivery |  | Bugs pada saat edit tanggal di surat tugas dan menambahkan so baru. DO lama tidak terupdate tanggalnya. | Fixing Bugs | Fixing Bugs | Teddy Juanda | Complete | 100% | 4533800% | 4534200% | 4534200% | 4 | Project Existing | Februari
MDBA | MDBA - Tools Update Counter DO (Support ICT) | Fitur support ict untuk update counter jika duplicate/bentrok |  | Tunning | New Feature | Teddy Juanda | Complete | 100% | 4534100% | 4534300% | 4534300% | 2 | Project Existing | Februari
MDBA | MDBA - New Feature Transaksi Claim | Jika tidak-gap/ya-gap tetap ada approval dari spv claim |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4592200% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Pada saat penginputan ID BP, jika ada spasi di hilangkan saja (TRIM) |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4592200% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Addendum bisa dilakukan sebelum atau sesudah diverifikasi oleh admin analis |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4592200% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Melakukan filter by tanggal, dok upload, no surat. Error szValidateClaim di tampilan kolom |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4591100% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Jika tidak target maka TIDAK-GAP, langsung closed tidak perlu approval spv claim |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4591100% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Jika status program full dalam 1 bulan, tidak perlu ada penambahan approval ccd |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4591100% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Pada saat approval spv claim, tambahkan validasi tidak bisa spasi jika input kolom credit note |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4591100% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Pada saat approval spv claim, jika credit note 0 tidak bisa submit |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4591000% | 4591100% | - | #VALUE! | Project Charter | September, 2025
MDBA | MDBA - New Feature Transaksi Claim | Jika sudah di approve, masih bisa di ubah rejected |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588900% | 4588900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Tambahkan validasi ccd tidak boleh > dari realisasi |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588900% | 4588900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Pada saat verifikasi, jika nominal approval ccd < realisasi, seharusnya masuk ke list spv claim |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588900% | 4588900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Kolom validasi CCD dibuat format nominal |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588900% | 4588900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Jika sudah di approve, masih bisa di ubah rejected |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4589400% | 4589600% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Tambahkan validasi ccd tidak boleh > dari realisasi |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4589200% | 4589400% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Pada saat verifikasi, jika nominal approval ccd < realisasi, seharusnya masuk ke list spv claim |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4589000% | 4589200% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Kolom validasi CCD dibuat format nominal |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588800% | 4589000% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Result Testing |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4588600% | 4588800% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Update Status Claim By No. Surat TIV |  | New Project | New Feature | Teddy Juanda | Need Review | 90% | 4584600% | 4584600% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - Config All Menu Akses User | modul master jabatan | Prority MDBA Monits | Tunning | New Feature | Teddy Juanda | On Hold | 90% | 4551800% | 4553200% | - | #VALUE! | Project Existing | Agustus
MDBA | MDBA - Config All Menu Akses User | modul hak akses menu | Prority MDBA Monits | Tunning | New Feature | Teddy Juanda | On Hold | 90% | 4551800% | 4553200% | - | #VALUE! | Project Existing | Agustus
MDBA | MDBA - Config All Menu Akses User | modul management menu | Prority MDBA Monits | Tunning | New Feature | Teddy Juanda | On Hold | 90% | 4551800% | 4553200% | - | #VALUE! | Project Existing | Agustus
MDBA | MDBA Gudang - Skenario Ritase Harian (SRH) | add menu list pb oleh spv delivery |  | Tunning | Update Feature | Teddy Juanda | On Hold | 95% | 4535600% | 4535700% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - Skenario Ritase Harian (SRH) | hak akses pb oleh spv delivery |  | Tunning | Update Feature | Teddy Juanda | On Hold | 95% | 4535600% | 4535700% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - Skenario Ritase Harian (SRH) | Draft PB untuk dijadikan BKB pada akses admin Gudang |  | Tunning | Update Feature | Teddy Juanda | On Hold | 95% | 4535600% | 4535700% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - Skenario Ritase Harian (SRH) | Pembuatan PB oleh SPV Delivery |  | Tunning | Update Feature | Teddy Juanda | On Hold | 95% | 4535600% | 4535700% | - | #VALUE! | Project Existing | Maret
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | PIisahkan beban internal dan yang bisa di claim |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4590400% | - | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Di menu admin sales bisa update tambahan IDBP jika terdapat revisi 1, revisi 2, revisi 3 |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4590400% | - | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Addendum terjadi pada saat di pertangahan bulan atau bisa pas closinan akhir bulan |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4590400% | - | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Mingguan, Bulanan, Kuartal (addendum) |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4590400% | - | - | #VALUE! | Project Existing | September, 2025
MDBA | Update MOM Meeting Review Digital Claim 2 September 2025 | Tambahkan total summary realisasi dan approval ccd pada patrial |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4590400% | - | - | #VALUE! | Project Existing | September, 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Retur DO | Distribusi & Penjualan | New Project | New Feature | Teddy Juanda | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA KINO | MDBA - Lock BKB sebelum BTB/BTU |  |  | Tunning | Update Feature | Teddy Juanda | Open | 0% | 4570000% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Cetak STD (Reguler & Canvasser) 1 Hari 1 STD |  | Tunning | Update Feature | Teddy Juanda | Open | 0% |  |  |  | 0 | Project Existing | -
MDBA | MDBA WaterOut - Exiting Task | Adjust pada waterout tidak muncul kembali di admin gudang |  | Tunning | Update Feature | Teddy Juanda | Open | 0% |  |  | - | #VALUE! | Project Existing | -
MDBA | MDBA WaterOut - Exiting Task | Tarik Jaminan tidak muncul di menu admin gudang |  | Tunning | Update Feature | Teddy Juanda | Open | 0% |  |  | - | #VALUE! | Project Existing | -
MDBA | MDBA - New Feature Transaksi Claim | Update Nominal CCD |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584400% | 4584600% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Verifikasi Data By Hasil Import Admin Sales/SPV MT |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584300% | 4584300% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | List Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584300% | 4584300% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Hak Akses (SPV Claim) |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584300% | 4584600% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Delete Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584200% | 4584200% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Re-Upload Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584100% | 4584100% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Verifikasi & Validasi Upload Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4584000% | 4584000% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Upload Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4583900% | 4583900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | List Data |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4583900% | 4583900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Hak Akses (Admin Sales/SPV MT) |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4583900% | 4583900% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Mockup UI/UX (Matrial Design) |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4583500% | 4583500% | - | #VALUE! | Project Charter | Agustus, 2025
MDBA | MDBA - New Feature Transaksi Claim | Mapping Matriks |  | New Project | New Feature | Teddy Juanda | Re Testing | 90% | 4583400% | 4583400% | - | #VALUE! | Project Charter | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | perluan 1 nik rangkap jabatan |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587400% | 1 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | penambahan di form login untuk menambahakan pilihan kategori untuk ke |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Ketika pengajuan dari QMS, pada saat di approve tidak menghasilkan no surat |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Ketika QMS SPV reject pengajuan, nomor surat seharusnya tidak terbuat |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | No Surat tidak sesuai dengan department pengajuan |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Approval QMS Staff dan QMS SPV tidak tampil |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Data detail revisi yang di tampilkan belum sesuai |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | kebutuhan testing |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Saat ini jabatan staff masih bisa melakukan pengajuan dan revisi untuk |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Format NIK sebagai username diganti menjadi text |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4587300% | 4587700% | 4587300% | 0 | Project Existing | Agustus, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | History Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586600% | 4586700% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Approval Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586500% | 4586600% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | List Data Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586400% | 4586500% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | QMS SPV |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586400% | 4586600% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | History Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586200% | 4586300% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Approval Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586100% | 4586200% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | List Data Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586000% | 4586100% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | QMS Staff |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4586000% | 4586300% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Form Pengajuan Revisi No. Lama |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585500% | 4585600% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | History Pengajuan |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585400% | 4585500% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Form Pengajuan No. Baru |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585300% | 4585400% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | List Data |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585300% | 4585300% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | All User |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585300% | 4585600% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Tampilan Awal |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585200% | 4585200% | - | #VALUE! | Project Charter | Juli, 2025
IM Digital (Number Latter) | IM Digital - Structur Coding | Login |  | New Project | New Feature | Teddy Juanda | Ready To Production | 95% | 4585200% | 4585200% | - | #VALUE! | Project Charter | Juli, 2025
Waterout | WaterOut - Exiting Task (finishing) | Di Cetakan BKB tambahkan No STD |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4539700% | 4540100% | - | #VALUE! | Project Existing | April
MDBA | MDBA FAR - QR Code User Update |  |  | Tunning | New Feature | Teddy Juanda | Ready To Production | 95% | 4537100% | 4537300% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 3. Upload BA jika BKB SPS |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 2. Perbesar view untuk upload BA |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 1. BTB Auto SPS error pada detail |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA FAR - QR Code User Update |  |  | Tunning | New Feature | Teddy Juanda | Ready To Production | 95% | 4537100% | 4537300% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 3. Upload BA jika BKB SPS |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 2. Perbesar view untuk upload BA |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret
MDBA | MDBA Gudang - BTB Distribusi Storing | 1. BTB Auto SPS error pada detail |  | Tunning | Update Feature | Teddy Juanda | Ready To Production | 95% | 4536600% | 4537100% | - | #VALUE! | Project Existing | Maret

## Komang Tri (hidden)
Details for TC - Assigned to: Komang Tri
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly | Column1
Mobile Stock Opname IA | New Mobile Stock Opname IA | API Draft Bulanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Validasi Stock Opname IA Bulanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | List Stock Opname IA Bulanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Menu Biodata |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Menu Awal |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | API Draft Harian |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Validasi Stock Opname Harian |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | List Stock Opname IA Harian |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Menu Login |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile Stock Opname IA | New Mobile Stock Opname IA | Splash |  | New Project | New Feature | Komang Tri | Complete | 100% | 4593800% | 4595200% | 4593900% | 1 | Project Charter | Oktober, 2025
Mobile EIS | Testing - Mobile EIS Daily Activity |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4593000% | 4593100% | 4593600% | 6 | Project Existing | Oktober, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Pembuatan Delivery Order Apss IOD MT (DO Blank) |  | New Project | New Feature | Komang Tri | Complete | 100% | 4584800% | 4583900% | 4591500% | 67 | Project Charter | Juni, 2025
Mobile Driver Management | Update MOM Meeting Koordinasi ICT, POOL, & SC 150825 | untuk status service parameternya di ambil pada saat pembuatan tiket |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4588700% | 4589900% | 4589100% | 4 | Project Existing | Agustus, 2025
Mobile Driver Management | Update MOM Meeting Koordinasi ICT, POOL, & SC 150825 | Jika ada in case kehadiran dapat di edit tetapi hanya 1x perubahan |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4588700% | 4589900% | 4589100% | 4 | Project Existing | Agustus, 2025
Mobile Driver Management | Update MOM Meeting Koordinasi ICT, POOL, & SC 150825 | 650 sps dan 600 CDD BOK sisanya dijadikan grouping menjadi varian WB |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4588700% | 4589900% | 4589100% | 4 | Project Existing | Agustus, 2025
Mobile Teknisi Dispenser | Teknisi Dispenser - Update jumlah galon otomatis VIA database |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4588100% | 4588200% | 4588300% | 2 | Project Existing | Agustus, 2025
Mobile Driver Management | Testing - Driver Management Apps | 6. Jumlah driver belum sesuai |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Testing - Driver Management Apps | 5. Rubah query untuk tampilkan semua driver di semua waktu |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Testing - Driver Management Apps | 4. Data yang di tampilkan seharusnya semua driver |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Testing - Driver Management Apps | 3. Data double saat backup armada |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Testing - Driver Management Apps | 2. Data double saat ada reset CO |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Testing - Driver Management Apps | 1. Loading lama saat load data |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587500% | 4588400% | 4593600% | 61 | Project Charter | Juli, 2025
Mobile Driver Management | Submit Driver |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4588000% | 4588200% | 4592900% | 49 | Project Charter | Juli, 2025
Mobile Driver Management | Edit Driver |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587600% | 4587800% | 4592900% | 53 | Project Charter | Juli, 2025
Mobile Driver Management | History Driver |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4587300% | 4587500% | 4592900% | 56 | Project Charter | Juli, 2025
Mobile Driver Management | Vehicle Variant |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586600% | 4586800% | 4592900% | 63 | Project Charter | Juli, 2025
Mobile Driver Management | Driver Variant | Pilih Driver |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586900% | 4587100% | 4592900% | 60 | Project Charter | Juli, 2025
Mobile Driver Management | Driver Variant | Api Driver Variant |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586900% | 4587100% | 4592900% | 60 | Project Charter | Juli, 2025
Mobile Driver Management | Home Page | Shift Sore |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586100% | 4586300% | 4592900% | 68 | Project Charter | Juli, 2025
Mobile Driver Management | Home Page | Shift Siang |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586100% | 4586300% | 4592900% | 68 | Project Charter | Juli, 2025
Mobile SFA Canvasser | Issue MDBA Mobile Canvasser - KLD, MNS |  | 1.Rollback insert 2.Pada saat input alih customer, loading lama lalu driver kill apps dan data sudah terupdate sehingga pada saat pilih BKB tidak tampil (Sudah di percepat dalam insert data) 3.Stock canvas tidak sesuai (sudah dilakukan perbaikan dari sisi coding) | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4529900% | 4529900% | 0 | Project Existing | Januari
Mobile GIGO TKBKM | Issue GIGO TKBM - All Depo |  | Foto Absen Checkin-Checkout Masih simpan dipenyimpanan TAB sehingga setiap 2 minggu sekali kadang harus hapus foto agar tidak full | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4530000% | 4530000% | 4530000% | 0 | Project Existing | Januari
Mobile Driver Management | Home Page | Shift Pagi |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586100% | 4586300% | 4592900% | 68 | Project Charter | Juli, 2025
Mobile Driver Management | Login |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4585900% | 4586000% | 4592900% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | Badge Cluster Pelanggan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | API STO AHS |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | Menu Selesai Perjalanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | Menu Istirahat |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | Menu Mulai Perjalanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile Preseller AHS & SPV Channel | New Apps - Mobile STO Segment AHS | Menu Persiapan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4586700% | 4586700% | 4593700% | 70 | Project Charter | Juli, 2025
Mobile SFA Canvasser | Limit kredit SFA Canvasser IOD/MT | Label Notifikasi |  | New Project | New Feature | Komang Tri | Complete | 100% | 4584600% | 4584700% | 4591600% | 70 | Project Charter | Juli, 2025
Mobile SFA Canvasser | Limit kredit SFA Canvasser IOD/MT | Validasi kredit |  | New Project | New Feature | Komang Tri | Complete | 100% | 4584600% | 4584700% | 4591600% | 70 | Project Charter | Juli, 2025
Mobile SFA Canvasser | Limit kredit SFA Canvasser IOD/MT | API |  | New Project | New Feature | Komang Tri | Complete | 100% | 4584600% | 4584700% | 4591600% | 70 | Project Charter | Juli, 2025
Mobile EIS | Issue Mobile EIS | Password EiS Tidak Bisa Login |  | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4530200% | 4530200% | 4530700% | 5 | Project Existing | Januari
Mobile Eis | Mobile EIS - Update Penambahan akses izin dan cuti by kode perusahaan | akses menu cuti |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4581800% | 4582500% | 4593600% | 118 | Project Existing | Juni, 2025
Mobile Eis | Mobile EIS - Update Penambahan akses izin dan cuti by kode perusahaan | akses menu izin |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4581800% | 4582500% | 4593600% | 118 | Project Existing | Juni, 2025
Mobile Eis | Mobile EIS - Update Penambahan akses izin dan cuti by kode perusahaan | API Perusahaan |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4581800% | 4582500% | 4593600% | 118 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | DO Retail Canvasser |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | SO SFA |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
Mobile Eis | Update Data Asset 1 Pintu di Mobile EIS | List Data Asset karyawan TVIP/ASA |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4579900% | 4579900% | 4579900% | 0 | Project Existing | Mei, 2025
Mobile Stock Opname ATK | List Validasi Stock ATK- Pass |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573500% | 4573500% | 4582600% | 91 | Project Charter | Maret 2025
Mobile Stock Opname ATK | List Validasi Stock ATK- Invalid |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573500% | 4573500% | 4582600% | 91 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Filter Data |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573500% | 4573500% | 4582600% | 91 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Filter Lokasi Gudang |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573500% | 4573500% | 4582600% | 91 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Validasi Stock ATK |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573500% | 4573500% | 4582600% | 91 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Info Profile |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573400% | 4573400% | 4582600% | 92 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Data Karyawan |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573400% | 4573400% | 4582600% | 92 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Profile |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573400% | 4573400% | 4582600% | 92 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Summary Stok Opname Bulanan & Harian |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | End Date |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Start Date |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Apply Stock |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | List Stok Fisik |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | List Outstanding |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573300% | 4573300% | 4582600% | 93 | Project Charter | Maret 2025
Mobile Stock Opname ATK | Stok Opname Bulanan & Harian |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4573000% | 4573200% | 4582600% | 96 | Project Charter | Maret 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Form Permintaan Tenaga Kerja |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Pengajuan Shifting On Off |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Pengajuan Shifting Biasa |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Pengajuan Mutasi Rotasi |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Pengajuan Seragam |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Izin Fullday |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Izin Non Fullday |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Dinas Non Fullday |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Dinas Fullday |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Cuti Khusus |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile Eis | Update Feature Mandatory - Mobile EIS | Approval Cuti Tahunan |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4575600% | 4576100% | 4577900% | 23 | Project Existing | April, 2025
Mobile EIS | New Feature (Take Photo EIS Daily Activity) | AutoCompleteTextView PSS |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4575100% | 4575400% | 4575100% | 0 | Project Existing | April, 2025
Mobile EIS | New Feature (Take Photo EIS Daily Activity) | API untuk PSS |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4575100% | 4575400% | 4575100% | 0 | Project Existing | April, 2025
Mobile EIS | New Feature (Take Photo EIS Daily Activity) | Fitur Foto Daily Activity |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4575100% | 4575400% | 4575100% | 0 | Project Existing | April, 2025
Mobile SFA Preseller | SFA Apps - Lock Apps Eksternal (Fake GPS) |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4573000% | 4573000% | 4573200% | 2 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Pembukaan bs dibuat 3 kolom: diskon principal (beban principal), diskon Nova (reguler yg 1-3), dan cash diskon Nova (isinya cash diskon) |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Mekanisme Promo Diskon Distributor + Diskon Principle (Drop Size) + Diskon Bundling Qty | SFA Apps | New Project | New Feature | Komang Tri | Complete | 100% | 4570200% | 4570800% | 4571600% | 14 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Mekanisme Auto Promo Bundling Qty Sales Order (FOC) | SFA Apps | New Project | New Feature | Komang Tri | Complete | 100% | 4570200% | 4570800% | 4571600% | 14 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Mekanisme Promo Drop Size Sales Order | SFA Apps | New Project | New Feature | Komang Tri | Complete | 100% | 4570200% | 4570600% | 4571600% | 14 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - Mekanisme Promo (Feature Baru) |  |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4570200% | 4570200% | 4572700% | 25 | Project Existing | Februari 2025
Mobile SFA Canvasser | Mobile Apps - API Linux |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4564900% | 4597100% | 4567000% | 21 | Project Existing | Desember
Mobile SFA Preseller | Mobile Apps - API Linux |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4564900% | 4597100% | 4567000% | 21 | Project Existing | Desember
Mobile SFA Canvasser | MDBA All - Config PPN | Driver Apps Canvasser |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4565600% | 4565900% | 4565900% | 3 | Project Existing | Desember
Mobile SFA Preseller | MDBA All - Config PPN | SFA PSS |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4565600% | 4565900% | 4565900% | 3 | Project Existing | Desember
Mobile SFA Canvasser | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | 3. Jika tidak ada penjualan, jangan tampilkan SO di summary kunjungan **(DONE)** |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4561600% | 4561600% | 4561600% | 0 | Project Existing | November
Mobile SFA Canvasser | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | 2. Tambahkan mark nearby untuk mengetahui antara titik hh dengan titik toko **(DONE)** |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4561600% | 4561600% | 4561600% | 0 | Project Existing | November
Mobile SFA Canvasser | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | 1. DO tampil di akhiri ritase tapi tidak tampil di detail LHP **(DONE)** |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4561400% | 4561400% | 4561400% | 0 | Project Existing | November
Mobile Teknisi Dispenser | Detail Kunjungan | PDF / BERITA ACARA VERIFIKASI & STOK OPNAME GALON |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Detail Kunjungan | Detail Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Detail Kunjungan | Detail Dispenser Accordion |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Detail Kunjungan | List Dispenser dengan Catatan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Detail Kunjungan | List Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Histori Kunjungan |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Perhatian |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Isi Keterangan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Berhasil |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Apakah Anda yakin? |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Belum Isi |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Selesai |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Berhasil Disimpan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Cek Fisik Dispenser Dengan Catatan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Cek Fisik Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser TIDAK |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser ADA / Manual Input Seri |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser ADA |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | PDF / BERITA ACARA VERIFIKASI & STOK OPNAME GALON |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Beranda | List Kunjungan Terisi |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Detail Kunjungan | Verifikasi Galon |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Histori Kunjungan | Histori Kunjungan / Filter |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan | Verifikasi Galon / Berhasil Disimpan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan | Verifikasi Galon / Galon Pinjam Kosong |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan | Verifikasi Galon |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Form Kunjungan | Verifikasi Galon/Dispenser |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Authentication | Logout |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
Mobile Teknisi Dispenser | Authentication | Login |  | New Project | New Feature | Komang Tri | Complete | 100% | 4557600% | 4560500% | 4564900% | 73 | Project Charter | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Validasi penginputan Kilometer di Menu Persiapan dan LHP Min & Max 6 Digit ***(DONE)*** |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4558200% | 4558200% | 4558200% | 0 | Project Existing | Oktober
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Penjualan Kompetitor dibandingkan dengan minggu lalu (Naik, Stabil, Turun) 1. Kategori alasan turun : konsumen beralih ke Air isi ulang, stok kosong, permintaan end user / anak outlet menurun |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Penjualan AQUA/VIT dibandingkan dengan minggu lalu (Naik, Stabil, Turun) 1. Kategori alasan naik : permintaan meningkat, promo menarik |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Promo dan Harga, 1.Mekanisme program terlalu rumit 2.Target terlalu besar 3.Kompetitor lebih menguntungkan |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Feedback permintaan & Pelayanan 1. Sering adanya pergantian sales 2.Produk kotor / ada benda asing 3.Pembayaran tempo |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Harga Jual(unit) = harga jual per unit / box |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Harga beli normal (unit) = harga beli normal per unit/box |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Qty per week = Penjualan toko per minggu |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | •Segmen intern dihapus karena tidak dibutuhkan |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile EIS | Update MOM Meeting Mobile Daily Activity 12 Agustus 2024 | Update Mobile Eis Penambahan Feature In Outlat Time (untuk mengetahui waktu di dalam Outlat) |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4551700% | 4553000% | 4553500% | 18 | Project Charter | Agustus
Mobile Opname Sparepart Bulanan | Validasi Stock Sparepart | List Validasi Stock Sparepart - Pass |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Validasi Stock Sparepart | List Validasi Stock Sparepart - Invalid |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Validasi Stock Sparepart | Filter Data |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Validasi Stock Sparepart | Filter Lokasi Gudang |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Profile | Info Profile |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Profile | Data Karyawan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | Summary Stok Opname Bulanan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | End Date |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | Start Date |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | Apply Stock |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | List Stok Fisik |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Opname Sparepart Bulanan | Stok Opname Bulanan | List Outstanding |  | New Project | New Feature | Komang Tri | Complete | 100% | 4534200% | 4534800% | 4534800% | 6 | Project Charter | Februari
Mobile Preseller AHS & SPV Channel | API | Produk |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | API | Harga |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | API | Geotree |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | API | Data Pelanggan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | API | Data Karyawan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | MDBA Master Rute STO | List Data Master Surat Tugas |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | MDBA Master Rute STO | Upload Master Surat Tugas |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | MDBA Surat Tugas STO | Proses Surat Tugas |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Profile | Detail Profile |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Konfigurasi | Konfigurasi Pengiriman |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Konfigurasi | Informasi Device |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Konfigurasi | Realisasi Pengiriman |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Selesai Perjalanan |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Istirahat |  |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Mulai Perjalanan | Laporan Penjualan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Mulai Perjalanan | Summary Kunjungan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Mulai Perjalanan | Scan Barcode |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Mulai Perjalanan | Form Biodata Pelanggan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Menu Persiapan | Surat Tugas |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543900% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Authentication | Logout |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543100% | 4586600% | 436 | Project Charter | Mei
Mobile Preseller AHS & SPV Channel | Authentication | Login |  | New Project | New Feature | Komang Tri | Complete | 100% | 4543000% | 4543100% | 4586600% | 436 | Project Charter | Mei
Mobile EIS | Mobile Daily Activity SND | Produk |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Harga |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Geotree |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Data Pelanggan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Data Karyawan |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Input Market Insight (Market Activity, Competitor Activity, FeedBack Outlet ) |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Listing Toko |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Pilih Segment |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Pilih Depo |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4532000% | 4532000% | 5 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Detail Profile |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4531500% | 4531500% | 0 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Logout |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4531500% | 4531500% | 0 | Project Charter | Januari
Mobile EIS | Mobile Daily Activity SND | Login |  | New Project | New Feature | Komang Tri | Complete | 100% | 4531500% | 4531500% | 4531500% | 0 | Project Charter | Januari
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Simbol bintang merah sesudah tanda tanya | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Alamat margin kanan | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Pindahkan kolom input qty stok setelah label pertanyaan | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Non White Chiller dihapus pertanyaan chiller di point reguler | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tambahan form update untuk memasukan bahwa pelanggan itu masuk kategori non white ciller/white chiller | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Question label Ya/Tidak dipindahkan sebelum foto di inputan SPV | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Upload foto POSM dijadikan 1 antara, A600, A1500, A5Gln, Vit Gln | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | upload foto Reguler dijadikan 1 antara A600, A1500, V550 | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Upload foto Chiller dijadikan 1 antara A600, V550 | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile SFA Preseller | Pengecekan HH Depo Manis |  |  | Tunning | Addhock | Yudistira, Komang, Pandu, Afrizal | Complete | 100% | 4530300% | 4531400% | 4531400% | 11 | Project Existing | Januari
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Label deskripsi pindahkan sesudah label point di atas upload foto di inputan Driver | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tampilkan alamat pelanggan saat pilih pelanggan | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile Garuda Perfect Store (Marchandise) | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Menu ditampilkan berdasarkan privillege (Driver dan SPV) | Update Garuda Perfect Store (Marchandise) | New Project | Update Feature | Komang Tri | Complete | 100% | 4549300% | 4549500% | 4560000% | 107 | Project Charter | Juli
Mobile SFA Canvasser | All Mobile MDBA - Upgrade API berdasarkan Login | Update Api Login |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4549100% | 4550400% | 4550200% | 11 | Project Existing | Juli
Mobile SFA Preseller | All Mobile MDBA - Upgrade API berdasarkan Login | Update Api Login |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4549100% | 4550400% | 4550200% | 11 | Project Existing | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 7. Tambahkan refresh background untuk get longlat |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
MDBA | Validasi Counter DO - KLD, MNS | Driver Canvasser Apps Luar Rute (komang) | Validasi DO Counter | Tunning | Update Feature | Komang Tri | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 6. Penambahan kolom qty penjualan per week |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 5. Akses jabatan IOD/MT di beri all depo, dan akhiri kunjungan cuma bisa di depo |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 4. Promo & Harga |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 3. Pelayanan |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 2. Issue Market |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Mobile EIS - Update Feature Daily Activity | 1. Akhiri kunjungan wajib minimal 100m di dalam radius dari depo start, kecuali IOD/MT, AM/CM dan STE |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4548200% | 4548900% | 4549500% | 13 | Project Charter | Juli
Mobile Eis | Addhock - Form Gratifikasi |  |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4547900% | 4548500% | 4582600% | 347 | Project Existing | Juli
Mobile EIS | Mobile EIS - Daily Activity SND (Penambahan Kategori Feedback Header dan Footer) | Penambahan kategori feedback header dan footer |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4546300% | 4546400% | 4546300% | 0 | Project Existing | Juni
Mobile EIS | Mobile EIS - Daily Activity SND (Pergantian Keterangan Feedback Outlet) |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4546100% | 4546100% | 4546100% | 0 | Project Existing | Juni
Mobile Stock Opname Sparepart | Stock Opname Sparepart Bulanan - Apply all Opname (Request User) | 3. Jika melakukan pencarian sparepart, qty yang sudah ter isi sebelumnya ter reset |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4548500% | 31 | Project Charter | Juni
Mobile Stock Opname Sparepart | Stock Opname Sparepart Bulanan - Apply all Opname (Request User) | 2. Update 200 Row, yang terupdate hanya 110 Row |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4548500% | 31 | Project Charter | Juni
Mobile Stock Opname Sparepart | Stock Opname Sparepart Bulanan - Apply all Opname (Request User) | 1. Force close saat scroll stok yang sudah di update (Stok Fisik) |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4548500% | 31 | Project Charter | Juni
Mobile Stock Opname Sparepart | Mobile Stock Opname - Apply all Opname (Request User) | 3. Jika melakukan pencarian, qty yang sudah ter isi sebelumnya ter reset |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4546000% | 6 | Project Charter | Juni
Mobile Stock Opname Sparepart | Mobile Stock Opname - Apply all Opname (Request User) | 2. Update 200 Row, yang terupdate hanya 110 Row |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4546000% | 6 | Project Charter | Juni
Mobile Stock Opname Sparepart | Mobile Stock Opname - Apply all Opname (Request User) | 1. Force close saat scroll stok yang sudah di update (Stok Fisik) |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4545400% | 4546000% | 4546000% | 6 | Project Charter | Juni
HRIS - EIS | HRIS EiS - No Urut setiap tabel | Data Biodata Diri |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4545300% | 4546000% | 4546300% | 10 | Project Existing | Juni
HRIS - EIS | HRIS EiS - No Urut setiap tabel | Karyawan Project |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4545300% | 4546000% | 4546300% | 10 | Project Existing | Juni
HRIS - EIS | HRIS EiS - No Urut setiap tabel | Mutasi Rotasi |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4545300% | 4546000% | 4546300% | 10 | Project Existing | Juni
Mobile Stock Opname Sparepart | Stok Opname Sparepart Bulanan - MOM 20 Mei 2024 | 4. Jika edit/mengurangi qty menggunakan button minus, button tidak berfungsi |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4543300% | 4544300% | 4546100% | 28 | Project Charter | Mei
Mobile Stock Opname Sparepart | Stok Opname Sparepart Bulanan - MOM 20 Mei 2024 | 3. Jika edit qty melalui kolom edit text, tidak terupdate otomatis datanya |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4543300% | 4544300% | 4546100% | 28 | Project Charter | Mei
Mobile Stock Opname Sparepart | Stok Opname Sparepart Bulanan - MOM 20 Mei 2024 | 2. Update otomatis opname bulanan ketika ada update dari opname harian |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4543300% | 4544300% | 4546100% | 28 | Project Charter | Mei
Mobile Stock Opname Sparepart | Stok Opname Sparepart Bulanan - MOM 20 Mei 2024 | 1. Tambahkan kategori All (Urutkan berdasarkan nama barang ascending) |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4543300% | 4544300% | 4546100% | 28 | Project Charter | Mei
Mobile Surviellance | Mobile Surveilance - MOM Koordinasi Pengkinian Data | Tanggal Lahir tidak mandatori |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4542700% | 4542800% | 4542800% | 1 | Project Existing | Mei
Mobile Surviellance | Mobile Surveilance - MOM Koordinasi Pengkinian Data | Upload NPPKP |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4542700% | 4542800% | 4542800% | 1 | Project Existing | Mei
HRIS - EIS | HRIS EiS - MOM Koordinasi HRD & ICT 07 Mei 2024 | API PTK Perjabatan status Progress |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4542000% | 4542700% | 4544600% | 26 | Project Charter | Mei
Mobile EIS | Mobile EiS - MOM Evaluasi Daily Activity 03 Mei 2024 | Nik pusat bisa memilih depo seperti AM, CM |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4541800% | 4542300% | 4541800% | 0 | Project Charter | Mei
Mobile EIS | Mobile EiS - MOM Evaluasi Daily Activity 03 Mei 2024 | Diberikan akses ke All STE |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4541800% | 4542300% | 4541800% | 0 | Project Charter | Mei
Mobile EIS | Mobile EiS - MOM Evaluasi Daily Activity 19 April 2024 | Pengecekan inputan longlat menjadi 0 |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4540600% | 4541100% | 4541400% | 8 | Project Charter | April
Mobile EIS | Mobile EiS - MOM Evaluasi Daily Activity 19 April 2024 | Saat Tidak ada kompetitor Pilihan market Insightnya di buat blank hanya input feedback outlet |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4540600% | 4541100% | 4541400% | 8 | Project Charter | April
Mobile EIS | Mobile EiS - MOM Evaluasi Daily Activity 19 April 2024 | Tambahkan Button Start dan finish Depo |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4540600% | 4541100% | 4541400% | 8 | Project Charter | April
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | 2. Listing pengajuan PTK hanya loading saja |  | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4541800% | 4542200% | 4542200% | 4 | Project Existing | Mei
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | 1. Select Option pengajuan PTK ketika double klik force close |  | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4541800% | 4542200% | 4542200% | 4 | Project Existing | Mei
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | Approval Cuti Team HR sampai dengan HR Manager |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4539700% | 4540100% | 4540100% | 4 | Project Existing | April
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | Approval Mutasi Rotasi sampai dengan HR Manager |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4539700% | 4540100% | 4540100% | 4 | Project Existing | April
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | Approval PTK sampai dengan HR Manager |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4539700% | 4540100% | 4540100% | 4 | Project Existing | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Pagination 15 per halaman |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Tampilan Tab Outstanding di buat pagination di tampilkan semua stok yang ada sesuai kategori |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Tampilkan data stok yang tidak **"0"** |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Tampilkan semua data memakai pagination |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Update query ditampilkan semua data hanya yang ada fisiknya saja (rudy) |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Stok opname di ubah tanggal 20 sampai akhir bulan |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile Stock Opname Sparepart | Stock Opname Sparepart - MOM 27 Maret 2024 | Tambahkan Summary Data Sparepart yang belum di update (tambahkan di menu depan) |  | New Project | Update Feature | Komang Tri | Complete | 100% | 4538300% | 4539000% | 4543200% | 49 | Project Charter | April
Mobile EIS | Mobile EiS - Pembuatan kontak EiS |  |  | Tunning | New Feature | Komang Tri | Complete | 100% | 4538400% | 4538600% | 4541800% | 34 | Project Existing | April
Mobile SFA Preseller | SFA Apps - History mulai perjalan terupdate (Fixing Bugs) |  |  | Tunning | Update Feature | Komang Tri | Complete | 100% | 4537700% | 4537900% | 4537800% | 1 | Project Existing | Maret
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 12. BKB Mix Canvasser Ritase belum sesuai | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559600% | 254 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 11. Delivery Order | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559600% | 254 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 10. Sales Order | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 9. Backup Driver di Take Out (Route Type CAN), Apabila ada kesalahan maka lakukan adjustment BKB | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 8. Validasi LHP jika belum terinput di Kasir di Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 7. Pembuatan DO Retail Galon / IOD input by Admin (Jika sudah di input di HH / Admin button DO Disable) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4556100% | 219 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 6. Validasi PB untuk BKB to DO Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 5. DO Pending di input by Admin (DEL, CAN & CAN NON RUTE) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 4. Validasi BKB di Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 3. Orderan CAN IOD - MT (Input By Admin & PO) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 2. Orderan PSS | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 1. Orderan CRL | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 6. Ubah koneksi ke Dummy link mdba-v2-cashier-new (Development) -> **23 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 5. Plan Testing QA Menyesuaikan -> **Minimal 01 Mar 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 4. Plan Update Page Development -> **23 - 29 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 3. Ubah koneksi ke Dummy (Development) -> **22 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 2. Migrasi ke Server Testing -> **21 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 1. Cloning APK Versi Production (Delete Image) -> ** 21 Feb 2024** | Tunning | Addhock | Pandu & Komang | Complete | 100% | 4534300% | 4535100% | 4535100% | 8 | Project Existing | Februari
Mobile SFA Canvasser | Canvasser Apps - Merger APK IOD-MT dan Retail Galon |  | New Feature | Tunning | New Feature | Komang Tri | Complete | 100% | 4531600% | 4532300% | 4544300% | 127 | Project Existing | Januari
Mobile SFA Preseller | Automation Update Version APK |  | New Feature | Tunning | New Feature | Komang Tri | Complete | 100% | 4531600% | 4532300% | 4544300% | 127 | Project Existing | Januari
Mobile SFA Canvasser | Automation Update Version APK |  | New Feature | Tunning | New Feature | Komang Tri | Complete | 100% | 4531600% | 4532300% | 4544300% | 127 | Project Existing | Januari
Driver Apps | Mobile Driver Apps - RollBack Alih Customer |  | Penginputan tidak sesuai karena jaringan, apps di kill | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4530700% | 4530900% | 4530800% | 1 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Perbaikan Bugs di shifting | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Validasi tanggal all pengajuan | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Update status di table karyawan struktur (lokasi_hrd, jabatan_hrd, dan status HRD jadi 3) | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | precepat longlat setiap pengajuan dengan metode sfa | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Karyawan Project Datanya tidak Update | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Upload Foto Cuti Tahunan Force Close | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Penutupan Akses Menu Pengajuan Resign (Website) | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile EIS | Issue EIS Mobile Apps | Penutupan Akses Menu Pengajuan Resign (Apps Android) | Fixing Bugs | Fixing Bugs | Fixing Bugs | Komang Tri | Complete | 100% | 4529900% | 4530300% | 4530700% | 8 | Project Existing | Januari
Mobile Garuda Perfect Store (Marchandise) | API | Question |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | API | Geotree |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | API | Data Pelanggan |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | API | Data Karyawan |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Profile | Detail Profile |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | History | List History |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Standar Display |  |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Survei Produk | Survei Produk |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Survei Produk | Pilih Outlet |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Survei Produk | Display Produk |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Survei Produk | Pilih Segmen |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Display Produk | Foto Produk |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Display Produk | Pilih Outlet |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Display Produk | Display Produk |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Display Produk | Pilih Segmen |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4541100% | 4542400% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Authentication | Logout |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4540600% | 4541000% | - | #VALUE! | Project Charter | April
Mobile Garuda Perfect Store (Marchandise) | Authentication | Login |  | New Project | New Feature | Komang Tri | Need Review | 90% | 4540600% | 4541000% | - | #VALUE! | Project Charter | April
Mobile EIS | HRIS EiS - Exiting Task (Finishing) | Approval Perubahan shifting (Tentatif) |  | Tunning | Update Feature | Komang Tri | On Hold | 0% |  |  | - | #VALUE! | Project Existing | -
Waterin | Waterin Transporter - Safety Checklist Armada (Testing) | Checklist Safety Juga dapat dilakukan di aplikasi Driver Management |  | Tunning | New Feature | Komang Tri | Open | 0% | - | - | - | #VALUE! | Project Existing | April, 2025

## Haeriah (hidden)
Details for TC - Assigned to: Siti Haeriah
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly
GL | FIXING CASE GL | SALDO AWAL JANUARI BEBERAPA TIDAK NYAMBUNG |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | 4597800% | 108 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - PAJAK PENGHASILAN PASAL 29 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | 4586900% | -1 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - TOL |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | 4586900% | -1 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - BBM |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | 4586900% | -1 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - HUTANG PPh PASAL 25/29 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4586800% | 4587800% | 4586900% | 1 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - HUTANG PPH FINAL |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4586800% | 4587800% | 4586800% | 0 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - AKTIVA DALAM PENYELESAIAN |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4586800% | 4587800% | 4586800% | 0 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - PPN MASUKAN |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4586800% | 4587800% | 4586800% | 0 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP- SELISIH BCA PUSAT |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4586800% | 4587800% | 4586800% | 0 | Project Existing | Agustus, 2025
GL | FIXING CASE GL | TVIP - SELISIH R/K DEPO |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report LRD | FIXING GL NOVA (MARET) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report LR | FIXING GL NOVA (MARET) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report NRD | FIXING GL NOVA (MARET) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report NR | FIXING GL NOVA (MARET) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report Trial | FIXING GL NOVA (MARET) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report LR detail Juni | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587600% | 4587600% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report LR rekap Juni | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587600% | 4587600% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report NR detail Juni | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587600% | 4587600% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report NR rekap Juni | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587600% | 4587600% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Report Trial Balance Juni All Depo | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587300% | 4587300% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Error Journal Posting | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
GL | FIXING CASE GL | Saldo subledger tidak nyambung dari Januari ke Februari Dst... | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
MDBA | FIXING BUGS MDBA | 3. Summary bawah settlement distribusi tidak sesuai terutama yang product 74559G dan 74560G (karena ada RETUR & TARIK JAMINAN) |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Closed | 90% | 4584000% | 4584500% | - | #VALUE! | Project Existing | Juli, 2025
MDBA | Issue MDBA Kasir | Issue MDBA Kasir - Kedoya | Sudah Closing Voucher tetapi tidak semuanya tervoucher, saldo masih tidak sesuai (tersisa) - belum di bikin vocer terima setoran uang putih dr tgl 28, baru disetorin ke bank tanggal 2 kemaren | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529400% | 4529500% | 4529400% | 0 | Project Existing | Januari
GL | FIXING CASE NEWGL TAX | 5. Update query LR NR YTD untuk case BTT | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4594800% | 4594800% | 4594800% | 0 | Project Existing | Oktober, 2025
MDBA | Issue MDBA Kasir | Continue Issue MDBA Kasir - Depok | 1.Rit di BTU masih ada yang terbaca undefined 2.323-0072860 No BKU tidak ditemukan 1. 3..tetapi masuk settlement (DONE) 2.Kas Besar Minus (DONE) - Tanggal 2 Sudah Done 3.Kas Besar Minus - Tanggal 3 ( Setelah Closing Voucher) ini closing voucer tgl 02 depok kas kecilnya sudah benar,tp kas besarnya saldo awal tgl 2 benar 29.700 tp saldo akhirnya 34.000, jadi untuk closing voucer tgl 03 saldo awal kas besar 34.000 dan saldo akhirnya 43450 (DONE) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
MDBA | Issue MDBA Kasir | Issue - MDBA Cashier Depo Cirendeu | 1.Bank KK Cirendeu Berbeda (Saldo Awal Dan Akhir) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529400% | 4529400% | 4529500% | 1 | Project Existing | Januari
GL | FIXING CASE NEWGL TAX | 4. Retesting unpost-posting | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4594800% | 4594800% | 4594800% | 0 | Project Existing | Oktober, 2025
MDBA | Issue MDBA Kasir | Issue MDBA Kasir - Bintaro | 1.Saldo KK Belum Sesuai | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529500% | 4529500% | 4529500% | 0 | Project Existing | Januari
GL | FIXING CASE NEWGL TAX | 3. Cek logic unpost-posting | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4594800% | 4594800% | 4594800% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | 2. Testing unpost-posting selain bulan Januari. Jika ternyata angka saldo masih bergerak maka next point 3 | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4594800% | 4594800% | 4594800% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | 1. Link stagging untuk NEW GL TAX dan new GL TVIP-ASA | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4594800% | 4594800% | 4594800% | 0 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | 14. Pendapatan Galon Kosong belum masuk di report LR bawaan zog | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592700% | 4592700% | 4592700% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 13. Saldo Akhir Trial Balance TVIP - Juni belum bala | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592500% | 4592500% | 4592500% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 12. Saldo Akhir Juni ASA 2025 selisih | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592700% | 4592700% | 4593100% | 4 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 11. Query report LRD | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592400% | 4592400% | 4592400% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 10. Query report LR (rekap) | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592400% | 4592400% | 4592400% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 9. Query report NRD | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592300% | 4592300% | 4592300% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 8. Query report NR (rekap) | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4592300% | 4592300% | 4592300% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 7. Fiscal Period ASA 2025 belum ada | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591700% | 4591700% | 4591700% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 6. Saldo Awal ASA 2025 | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591900% | 4591900% | 4591900% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 5. Saldo AKhir Trial Balance Mei Selisih | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | akun | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591600% | 4591600% | 4591600% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 4. Nama akun di Report Account Subledger masih ada bbrp yg tidak sesuai nama | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591600% | 4591500% | 4592900% | 13 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 3. Tidak bisa save data failed pada saat edit | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591500% | 4591500% | 4591500% | 0 | Project Existing | September, 2025
MDBA | Update Kartu Driver Mesin Setor Depo Cikokol |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4529600% | 4529900% | 4529700% | 1 | Project Existing | Januari
MDBA | Issue BTU Double - MBDA - Tarikan Query Depo Pluit |  |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529700% | 4530200% | 4529700% | 0 | Project Existing | Januari
GL | FIXING CASE NEWGL TAX | 2. Tampilan Account Subledger YTD MTD, saldo awal all depo tidak sesuai | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591600% | 4591600% | 4591600% | 0 | Project Existing | September, 2025
GL | FIXING CASE NEWGL TAX | 1. Saldo Awal Trial Balance selisih | LIST CASE | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4591900% | 4591600% | 4591600% | -3 | Project Existing | September, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | CEK SEMUA REPORT-REPORT (KETERSAMBUNGAN SALDO) |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4587600% | 4588700% | 4589100% | 15 | Project Existing | Agustus, 2025
MDBA | Continue Issue MDBA Depo Daan Mogot |  | tolong dibantu saldo kas kecil harusnya 7.338.824 | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529500% | 4529600% | 4529900% | 4 | Project Existing | Januari
GL | TIMELINE NEW GL - FIXING CASE GL | RESTORE & CEK DATA DB 2025 (JAN-APR), DIPASTIKAN BALANCE TB NR LR |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4588000% | 4588000% | 4588000% | 0 | Project Existing | Agustus, 2025
MDBA | Issue MDBA Kasir | Continue Issue MBDA Kasir - Balaraja | 1.Penarikan ump tgl 2 Januari 2024 kode bank sama sub account nya masih salah seharusnya kode bank 100252 , sub account 52999999 [DONE] 2.Saldo masih belum settle 600 di mdba | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4529400% | 4529500% | 4529500% | 1 | Project Existing | Januari
MDBA | Issue MBDA Kasir - Cikokol |  | kasir hari ini upload FAR tapi kenapa di querynya no BKUnya sama semua dengan no BTU 311-0122092 | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4530000% | 4530300% | 4530100% | 1 | Project Existing | Januari
MDBA | Update Kartu Mesin Setor Depo Depok |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4529900% | 4529900% | 4530100% | 2 | Project Existing | Januari
MDBA | Issue MDBA Kasir | Issue MDBA Kasir - Alam Sutera | saldo piutang usaha tunai di MDBA dan query berbeda | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4530100% | 4530200% | 4530200% | 1 | Project Existing | Januari
GL | GL BTT | URUTIN TVIP (10 & 11) & ASA (KB) |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4586000% | 4586600% | 4586600% | 6 | Project Existing | Juli, 2025
GL | GL BTT | DATA AFTER |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4586000% | 4586600% | 4586600% | 6 | Project Existing | Juli, 2025
GL | GL BTT | TARIK REPORT |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4586000% | 4586600% | 4586600% | 6 | Project Existing | Juli, 2025
GL | GL BTT | RESTORE LOCAL |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4586000% | 4586600% | 4586600% | 6 | Project Existing | Juli, 2025
GL | Task From Zoom GL 14 Juli 2025 | GL Nova setelah pengerjaan GL TVIP |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4585200% | 4585500% | 4591600% | 64 | Project Existing | Juli, 2025
GL | Task From Zoom GL 14 Juli 2025 | Kamis selesaikan report untuk yang TVIP ASA New GL |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4585200% | 4585500% | 4591600% | 64 | Project Existing | Juli, 2025
GL | V&V NEWGL VS GL FOXPRO | SALDO MEI 2025 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4584500% | 4585600% | 4586700% | 22 | Project Existing | Juli, 2025
GL | GL NOVA GABUNG PRINCIPLE | IV. Migrasi Data Pusat |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4584100% | 4585300% | 4584300% | 2 | Project Existing | Juli, 2025
GL | GL NOVA GABUNG PRINCIPLE | III. Account GL NOVA |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4584100% | 4585300% | 4584000% | -1 | Project Existing | Juli, 2025
GL | GL NOVA GABUNG PRINCIPLE | II. Template Report GL NOVA |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4584100% | 4585300% | 4584200% | 1 | Project Existing | Juli, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 3. Cek Selisih saldo dan tanem saldo awal JAN - APR 2025 | ASA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4583100% | 4583100% | 4583100% | 0 | Project Existing | Juni, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 6. Cek selisih FEB s/d APRIL 2025 | TVIP | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4582900% | 4582900% | 4582900% | 0 | Project Existing | Juni, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 4. Tarik data kembali setelah disesuaikan saldo awal Jan 2025 | TVIP | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4582900% | 4582900% | 4582900% | 0 | Project Existing | Juni, 2025
GL | SEEDING DATA NEW GL TVIP-ASA-TAX | 3. Cek selisih saldo awal , tanem saldo awal Jan 2025 | TVIP | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4582800% | 4582800% | 4582800% | 0 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 11. update query JM LA3 pada saat upload GL ke GL-NOVA-1 | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 10. update query JM LA2 pada saat upload GL ke GL-NOVA-1 | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 9. update query JM LA1 pada saat upload GL ke GL-NOVA-1 | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 8. update query LA3 pada saat upload ke history_principle_gl | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 7. update query LA2 pada saat upload ke history_principle_gl | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 6. update query LA1 pada saat upload ke history_principle_gl | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4583200% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 5. update query di coding tools http://192.168.15.90/gl_kino/support/supportAutoGL | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582500% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 4. penambahan account 333 di tools | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582500% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 3. update query 1K 1M pada saat upload GL ke GL-NOVA-1 | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582500% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 2. update query VB VT pada saat upload ke history_principle_gl | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582500% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 1. add new id depo 333 - NOVA LENTENG AGUNG 2 | PENAMBAHAN ID BARU UNTUK BEKASI MDBA TO GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582500% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 10. Update / Tarik ulang data JM (random case by Nisa AR) |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 9. Cost Center dgn Kode 17 untuk BKS (LTA-2) |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 8. Template NOVA-LRC2024 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 7. Template NOVA-LRDC2024 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 6. Template NOVA-NRDC2024 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 5. Template NOVA-NRC2024 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 4. Template NOVA-TRIAL2024 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 2. Create ulang DB untuk mamasuka : GL_NOVA-2 |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
GL | FIXING BUGS GL NOVA | 1. Create ulang DB untuk tax : GL_NOVA_TAX |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581200% | 4582100% | 4583200% | 20 | Project Existing | Juni, 2025
MDBA | FIXING BUGS MDBA NOVA KASIR | Submit payment aauto BTU/BKU |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581900% | 4581900% | 4582500% | 6 | Project Existing | Juni, 2025
MDBA | FIXING BUGS MDBA NOVA KASIR | Masih menunggu inputan BBM |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581900% | 4582500% | 4582500% | 6 | Project Existing | Juni, 2025
MDBA | FIXING BUGS MDBA NOVA KASIR | Submit pada saat penarikan uang muka |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581900% | 4581900% | 4582500% | 6 | Project Existing | Juni, 2025
MDBA | FIXING BUGS MDBA NOVA KASIR | yang menyebabkan selisih itu karena : (cintia kasir SRG said _"bagian sales ga pake bkb, nah otomatis di settlement deposit kan ga muncul dan kita ga bisa input UMP by system tapi kalau driver itu kan ada bkb kita bisa input ump by system, waktu pengeluaran ump sales di settlement withdrawl jadinya selisih mba"_ ) ¦¦ sehingga solvingnya : narik uang muka(UMP) bagi driver/sales yang tidak punya bkb itu input manual saja. |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581900% | 4582000% | 4582500% | 6 | Project Existing | Juni, 2025
MDBA | FIXING BUGS MDBA NOVA KASIR | Submit settlement deposit |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4581900% | 4581900% | 4582500% | 6 | Project Existing | Juni, 2025
MDBA | MDBA - KASIR PDG (Penyesuaian Saldo Kas Kecil & Kas Besar) |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4581700% | 4582100% | 4581700% | 0 | Project Existing | Juni, 2025
MDBA | MDBA CASHIER NOVA LTA (BEKASI) | 1. Munculkan nominal KAS KECIL Bekasi dengan cost center 17999999 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4581700% | 4582000% | 4581700% | 0 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | QUERY API NEW GL LA3 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4581000% | 4581000% | 4581000% | 0 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | QUERY API NEW GL LA2 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4581000% | 4581000% | 4581000% | 0 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | QUERY API NEW GL LA1 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4581000% | 4581000% | 4581000% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | MAPING PRODUCT 74560G (JUAL & RETUR) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580800% | 4580800% | 4580800% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | MAPING PRODUCT 74559G (JUAL & RETUR) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580800% | 4580800% | 4580800% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | CREATE ACCOUNT HPP GALON KOSONG |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580700% | 4580700% | 4580700% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | CREATE ACCOUNT PENDAPATAN GALON KOSONG |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580700% | 4580700% | 4580700% | 0 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | CREATE ACCOUNT PERSEDIAAN GALON KOSONG |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580700% | 4580700% | 4580700% | 0 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | 3. Duplikat folder CI |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580300% | 4580300% | 4588200% | 79 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | 2. Create NEW DB di history (SQLYOG) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4580300% | 4580300% | 4588200% | 79 | Project Existing | Mei, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | 1. Create New DB **GL_NOVA-2** (SQL SERVER) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4579700% | 4580300% | 4588200% | 85 | Project Existing | Mei, 2025
GL | REPORT GL FOXPRO |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4579900% | 4580000% | 4579900% | 0 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA3 MMS VS TARIKAN QUERY | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA3 KINO VS TARIKAN QUERY | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA2 MMS VS TARIKAN QUERY REG DO TUNAI | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA2 KINO VS TARIKAN QUERY REG DO TUNAI | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA1 MMS VS TARIKAN QUERY REG DO KREDIT | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | LA1 KINO VS TARIKAN QUERY REG DO KREDIT | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580100% | 4580100% | 4588200% | 81 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 1M MMS VS TARIKAN QUERY DMS VT | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580000% | 4580000% | 4588200% | 82 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 1M KINO VS TARIKAN QUERY DMS VT | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580000% | 4580000% | 4588200% | 82 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 1K MMS VS TARIKAN QUERY DMS VB | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580000% | 4580000% | 4588200% | 82 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 1K KINO VS TARIKAN QUERY DMS VB | TESTING TOOLS GL-NOVA | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4580000% | 4580000% | 4588200% | 82 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 6. NEW TEMPLATE REPORT NOVA-NRDC | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 5. NEW TEMPLATE REPORT NOVA-NRC | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 4. NEW TEMPLATE REPORT NOVA-LR-C | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 3. NEW TEMPLATE REPORT NOVA-LRD-C | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 2. NEW TEMPLATE REPORT NOVA-TRIAL | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | GL-NOVA TOOLS & REPORT GL | 1. PENAMBAHAN & UPDATE NEW ACCOUNT NOVA DI DB GL-NOVA | REPORT GL NOVA | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4579100% | 4579600% | 4588200% | 91 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 8. PENAMBAHAN ACCOUNT BARU DI TEMPLATE REPORT TRIA |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 7. REPORT NOVA-NRC2024 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 6. REPORT NOVA-NRDC2024 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 5. REPORT NOVA-LR-C |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 4. REPORT NOVA-LR-D-C |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 3. SELISIH (383) SALDO AWAL 2025 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 2. REPORT NOVA-TRIAL2024 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | SALDO & REPORT GL-NOVA | 1. TANAM SALDO AWAL 2025 GL-NOVA-1 |  | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 3. VB VT 3 FEB BELUM MUNCUL | V&V GL KINO - LTA | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 6. 2. Kelebihan nilai payment ketimbang nilai invoice sehingga di UMP minus | V&V GL KINO - LTA | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 1. JM tgl 20,21,28,30,31/01 TIDAK SAMA DENGAN TARIKAN DASHBOARD | V&V GL KINO - LTA | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 4. VB VT TGL 10 FEB BELUM MUNCUL | V&V GL KINO - LTA | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 3. TGL 13 14 15 17 18 19 20 21 JM TIDAK MUNCUL | V&V GL KINO - KLD | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 2. Saldo bank kld januari masih 0 harusnya 365.000 | V&V GL KINO - KLD | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 1. Saldo awal KAS BESAR Jan 2025 harusnya 378,449 | V&V GL KINO - KLD | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 5. SRG - JM tgl 15 Maret TIDAK SAMA DENGAN TARIKAN DASHBOARD | V&V GL KINO - SRG | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 4. SALDO BANK 100231 bln Feb HARUSNYA SESUAI DENGAN SALDO AKHIR JANUARI | V&V GL KINO - SRG | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 3. Saldo bank SRG tgl 01/01 masih 0 blm ikutin saldo akhir Des | V&V GL KINO - SRG | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 2. SRG - LA3 belum muncul 31/01/2025 | V&V GL KINO - SRG | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | V&V GL NOVA - KINO | 1. SRG - LA2 nominal beda 31/01/2025 | V&V GL KINO - SRG | Tunning | Validasi | Siti Haeriah | Complete | 100% | 4578200% | 4579000% | 4579000% | 8 | Project Existing | Mei, 2025
GL | GL - DB GL_NOVA_TAX |  | 1. DB baru untuk TAX (GL NOVA TAX) | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582500% | 43 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 2. Query API VT |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582700% | 45 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 1. Query API VT |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582700% | 45 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 9. Selisih. BKU/BTU yang memiliki 2 row item terbaca di 1K & 1M nya hanya 1 row |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582700% | 45 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 8. Salah Journal JM |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582700% | 45 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 7. terdapat voucher yg tidak muncul sama sekali di NEW GL |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4582700% | 45 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 6. Account PIUTANG USAHA TUNAI antara GL dan tarikan VBVT DMS tidak sesuai |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4581100% | 29 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 5. Data VB VT JM tgl kemarin belum masuk secara otomatis ke Journal Temporary |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4578400% | 2 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 4. Data Indicator Mei 2025 belum masuk ke NEW GL J. Temporary |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4578400% | 2 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 3. Setting Print Journal |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4578400% | 2 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 2. Data Fiscal Period ASA 2025 tidak ada |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4578400% | 2 | Project Existing | Mei, 2025
GL | IMPLEMENTASI NEW GL (TVIP & ASA) | 1. User Login untuk hak akses company ASA tidak bisa login |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4578200% | 4583800% | 4578400% | 2 | Project Existing | Mei, 2025
GL | Call JM NOVA Periode Jan - April |  |  | Tunning | Addhock | Siti Haeriah & Teddy | Complete | 100% | 4577900% | 4578200% | 4578200% | 3 | Project Existing | April, 2025
GL | Addhock- Support GL Foxpro (TVIP & NOVA & KONSULTAN) | GL NOVA |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4575500% | 4575800% | 4578400% | 29 | Project Existing | April, 2025
GL | Addhock- Support GL Foxpro (TVIP & NOVA & KONSULTAN) | Saldo Double (GL Konsultan) |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4575500% | 4575800% | 4578400% | 29 | Project Existing | April, 2025
GL | Addhock- Support GL Foxpro (TVIP & NOVA & KONSULTAN) | Penambahan Account di Excel Template GL (Konsultan) |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4575500% | 4575800% | 4578400% | 29 | Project Existing | April, 2025
GL | Addhock- Support GL Foxpro (TVIP & NOVA & KONSULTAN) | Template Report GL NOVA |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4575500% | 4575800% | 4578400% | 29 | Project Existing | April, 2025
GL | Addhock- Support GL Foxpro (TVIP & NOVA & KONSULTAN) | Masalah GL Poxpro TVIP |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4575500% | 4575800% | 4578400% | 29 | Project Existing | April, 2025
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Mapping Product di GL untuk Account Persediaan, HPP dan Pendapatan | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | New Scheduler untuk 1K, 1M, JM | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Migrasi Account dan Cost Center (asa+tvip) ke GL_NOVA | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Tambahkan Rollback di menu Voucher Pengeluaran | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563500% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Tambahkan Rollback di menu Voucher Penerimaan | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563500% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Tambahkan Rollback di menu BKU | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Tambahkan Rollback di menu BTU | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563100% | 4563100% | 4569400% | 63 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | New Scheduler untuk 1K, 1M, JM | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Migrasi data Account & CostCenter SRG, BRJ, PDG ke DB **mdba_product** | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Update Patch input KM di menu BTU | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | NEW DB di 15.90 (GL_NOVA) | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Closing Voucher Kasir | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Applied All Settlement DO Kredit Langsung & Akhir Bulan | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA KINO | Update Kebutuhan MDBA PT. NOVA (KINO) | Applied All Settlement DO Tunai | Update Kebutuhan MDBA PT. NOVA (KINO) | New Project | New Feature | Siti Haeriah | Complete | 100% | 4563000% | 4563100% | 4569400% | 64 | Project Charter | Desember
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | 2. Tambahkan KM Ritase terakhir pada saat penginputan BTU **(DONE)** |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4561500% | 4561500% | 4561500% | 0 | Project Existing | November
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | 1. Tambahkan validasi jika ada penginputan BTU terdapat driver dan batangan berbeda atau mobil tidak ada di master kilometer tidak dapat di input BTU **(DONE)** |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4561500% | 4561500% | 4561500% | 0 | Project Existing | November
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | Setor Transfer dari Toko |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 2. Input Rincian Setoran ADVANTAGE | MENU INPUT | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 1. Input Pecahan uang Tunai 100.000, 75.000, 50.000, 20.000, 10.000, 5.000, 2.000, 1.000, 500, 100 | MENU INPUT | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 2. Jumlah Penjualan (Setor Manual) | JUMLAH PENJUALAN | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 3. Pelunasan Piutang Pelanggan (BTU) >> RK Piutang Depo & RK Piutang Pusat | PENDAPATAN NON TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 2. Pengeluaran (Biaya) | PENDAPATAN NON TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 1. Pelunasan Piutang Pelanggan (BTU) >> Kas Besar & Bank | PENDAPATAN NON TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 5. Pembulatan Mesin | PENJUALAN TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 4. Penerimaan Lain (Cash) | PENJUALAN TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 3. Penerimaan Piutang Pelanggan | PENJUALAN TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 2. Penerimaan Uang Muka | PENJUALAN TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | MDBA - Digitalisasi Report Harian Kasir (Cash Flow) | 1. Hasil Penjualan Tunai | PENJUALAN TUNAI | New Project | New Feature | Siti Haeriah | Complete | 100% | 4581900% | 3107/2025 | 4589900% | 80 | Project Charter | Juni, 2025
MDBA | Fixing Bugs Closing Voucher MDBA Kasir Depo |  |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4560100% | 4560100% | 4560100% | 0 | Project Existing | November
GL | Addhock - Dokumentasi NEW GL | 2. Scheduler / API |  | Tunning | Dokumentasi | Siti Haeriah | Complete | 100% | 4558100% | 4559600% | 4579700% | 216 | Project Existing | Oktober
GL | Addhock - Dokumentasi NEW GL | 1. Database & Table |  | Tunning | Dokumentasi | Siti Haeriah | Complete | 100% | 4558100% | 4559600% | 4579700% | 216 | Project Existing | Oktober
MDBA | MDBA Settlement - Kode Driver tidak terbaca (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4558000% | 4558300% | 4558300% | 3 | Project Existing | Oktober
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 6. RK All depo dibuatkan umum berdasarkan kategori depo |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 5. Tools Support Auto GL vb vt belum sesuai cost center |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 4. Ketidaksesuaian VB VT saat auto GL pada header (Cost center) |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 3. Script Auto VB, VT, LA123 dijalankan H-1 |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 2. Pada saat submit closing, angka saldo akhir kas besar berbeda dengan yang di view closing voucher |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Ketidaksesuaian auto VB VT Query (Fixing Bugs) | 1. Auto Debet sebagai pengurang saldo BANK BCA |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4553700% | 4554100% | 4556500% | 28 | Project Existing | September
MDBA | MDBA Kasir - Void BTU BKU by Closing |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552400% | 4552600% | 4553500% | 11 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | tambahkan voucher pengeluaran di print cover |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4552200% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Tambahkan Rollback pada saat submit closing voucher |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4552100% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Masih bisa buat BKB sebelum buat BTU (CNK,CRD,XBT) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Jika ada do tf dan tunai jika sudah BTU tidak bisa BTU lagi, harus pilih type lain-lain (ASA) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Saat BTU manual tambahkan inputan KM |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | BKU piutang usaha tunai tidak masuk settlement seharusnya masuk (kredit dan tunai) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | uang muka penjualan tidak masuk setlement (input manual) |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Tambahkan notif jika upload excel no urut tidak sesuai |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Tambahkan bank kas kecil di closing voucher walaupun tidak ada transaksi |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
MDBA | MDBA Kasir - Training Cashier Tahap 1 & 2 (Noted) | Voucher penerimaan bisa di buat H+1 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4552600% | 4551700% | 4559500% | 69 | Project Existing | Agustus
GL | Addhock - Backup database GL Tahap 2 |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4550400% | 4550900% | 4556500% | 61 | Project Existing | Juli
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | 2. ketika rubah harga secara view total harga dll masih 0 |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | 1. dtmlastupdate tidak update yang di MDBA |  | Tunning | Fixing Bugs | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | Stop Jual |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | Stop Sewa |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | Pasang Tarik |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Invoice - DO Dispenser Edit (New Feature) | Pasang Baru |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4554100% | 4553100% | 4558300% | 42 | Project Existing | September
MDBA | MDBA Entry - Update Fixing Bugs | 8. Applied by settlement tidak merubah status FDE menjadi ACT **(DONE)** |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4550900% | 4551800% | 4551800% | 9 | Project Existing | Agustus
GL | Modul Inventory - Arus Barang + Auto Billing | 6. Tambahkan filter pilih bulan, jika user ingin melihat data bln lalu yg sudah bayar | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 5. Listing nama ekspedisi lalu muncul nomor faktur yang siap dibayar | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 4. Masih ada selisih buat yang ppn 11% | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 3. Dibuat multiple faktur dalam print rekap | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 2. Print PT. ASA bank masih belum sesuai (masih bank TVIP) | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 1. Hide sementara bukti pembayaran saat payment | Tambahan Note Auto Billing (dari Team FA) 22 Juli 2024 | New Project | Update Feature | Oka & Haeriah | Complete | 100% | 4549600% | 4549800% | 4549900% | 3 | Project Charter | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 4. Auto Billing History List (Not Yet Paid) | Modul Finance - Auto Billing | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4545600% | 4546700% | 4549900% | 43 | Project Existing | Juni
GL | Modul Inventory - Arus Barang + Auto Billing | 2. Auto Billing History List | Modul Finance - Auto Billing | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4545600% | 4546700% | 4549700% | 41 | Project Existing | Juni
GL | Modul Inventory - Arus Barang + Auto Billing | 1. Auto Billing Draft | Modul Finance - Auto Billing | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4545600% | 4546700% | 4545600% | 0 | Project Existing | Juni
GL | Addhock - Grouping report aktiva dan pasiva GL |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4549500% | 4549900% | 4549900% | 4 | Project Existing | Juli
GL | Addhock - API GL voucher username |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4549200% | 4549600% | 4549600% | 4 | Project Existing | Juli
GL | Addhock - Membuat query subledger overview |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4548800% | 4549300% | 4550300% | 15 | Project Existing | Juli
GL | Addhock - API GL Voucher |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4549000% | 4549100% | 4549100% | 1 | Project Existing | Juli
MDBA | MDBA Invoice - Stop sewa dispenser (Fixing bugs) |  |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4548200% | 4548800% | 4550300% | 21 | Project Existing | Juli
GL | Addhock GL - GL From Consultant |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4545700% | 4547100% | 4547900% | 22 | Project Existing | Juni
GL | Issue GL - Automatic Schedule Running | Pengecekan integrasi 1K, 1M, dan LA 123 |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4529900% | 4530100% | 4530100% | 2 | Project Existing | Januari
MDBA | MDBA Cashier - Auto BKU BTU BBM (Fixing Bugs) | Pilihan cash dan langganan tidak mandatori apabila tidak di pilih salah satu maka data yang di input kosong accountnya |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | MDBA Cashier - Auto BKU BTU BBM (Fixing Bugs) | Status masih Not BKU (ketika disubmit beda tgl antara Tgl Permintaan dengan Tgl BKU) => contoh depo CRD (cek capture image.png) |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | MDBA Cashier - Auto BKU BTU BBM (Fixing Bugs) | Load lama saat submit |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | MDBA Cashier - Auto BKU BTU BBM (Fixing Bugs) | Data masih muncul apabila sudah submit langganan |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Pilihan Pada Alasan Permohon di samakan dengan bu ina (Nopol, KM Awal-KM Akhir, Type (Langganan/Cash)) | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4544400% | 4544800% | 4544600% | 2 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Transfer Bank di ganti Cheklist Langganan | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4544400% | 4544800% | 4544600% | 2 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Di buatkan cheklist Langganan pada Modal Input BKU BTU | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4544400% | 4544800% | 4544600% | 2 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Task MOM | Untuk langganan di buatkan range tanggal start date dan end date | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4544400% | 4544800% | 4544600% | 2 | Project Existing | Juni
MDBA | MDBA Kasir - Reimburse BBM | 5. Validasi apabila sudah dibuat BKU tidak bisa mengajukan reimburse |  | Fixing Bugs | Fixing Bugs | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | 4. Nominal uang reimburse masih belum sesuai |  | Fixing Bugs | Fixing Bugs | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | 3. Pengajuan yang salah lalu di reject, bisa dilakukan pengajuan lagi kecuali approve |  | Fixing Bugs | Fixing Bugs | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | 2. Jika ada notif ID permintaan telah dalam list, lalu tambahkan refresh halaman |  | Fixing Bugs | Fixing Bugs | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | 1. Setelah melakukan pencarian lalu klik menu pengajuan reimburse, lalu back, data tidak ditemukan. |  | Fixing Bugs | Fixing Bugs | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | BTU BBM rembes (Jika nominal permintaan lebih besar dari struk) |  | Tunning | New Feature | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | List Draft nominal rembes BBM |  | Tunning | New Feature | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | Approval SPV Admin |  | Tunning | New Feature | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | Pengajuan BBM oleh Kasir |  | Tunning | New Feature | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
MDBA | MDBA Kasir - Reimburse BBM | Pembuatan tabel untuk rembes bbm |  | Tunning | New Feature | Siti Haeriah & Teddy | Complete | 100% | 4540400% | 4541200% | 4541200% | 8 | Project Existing | April
GL | GL - API Header Deskripsi |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4543900% | 4543900% | 4543900% | 0 | Project Existing | Mei
MDBA | MDBA - Fixing Bugs Settlement | Insert saat closing settlement tidak semua data masuk |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4542500% | 4542700% | 4543600% | 11 | Project Existing | Mei
MDBA | MDBA - Fixing Bugs Settlement | Pada saat Tarik Jambot tampilan di settlement tidak muncul merah |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4542500% | 4542700% | 4543600% | 11 | Project Existing | Mei
GL | GL - Dokumentasi Backup Konsultan | GL - Dokumentasi Backup Konsultan |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4542700% | 4543200% | 4543200% | 5 | Project Existing | Mei
MDBA | Update MOM Meeting Koordinasi Auto Billing Ekspedisi 08 Mei 2024 | 1. Di menu FA sebelum bayar harus upload foto bukti pembayarannya (buat mandatory) => [ IN PROGRESS ] |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4542000% | 4542900% | 4542900% | 9 | Project Existing | Mei
MDBA | MDBA Kasir - Draft auto billing | Selisih 1 perak pada tampilan view GL |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541100% | 4542200% | 18 | Project Charter | April
MDBA | MDBA Kasir - Draft auto billing | CO yang beda NO faktur ikut masuk sehingga pembayaran jadi lebih besar dari yang seharusnya |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541100% | 4542200% | 18 | Project Charter | April
MDBA | MDBA Kasir - Draft auto billing | Penambahan Status Sudah Bayar / Belum (Perubahan status Sudah Bayar ketika di Applied) |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541100% | 4542200% | 18 | Project Charter | April
MDBA | MDBA Kasir - Draft auto billing | Submit Draft |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541100% | 4542200% | 18 | Project Charter | April
MDBA | MDBA Kasir - Draft auto billing | List Draft nominal auto billing dari waterin |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541100% | 4542200% | 18 | Project Charter | April
MDBA | MDBA Kasir - Rembes BBM | BTU BBM rembes |  | New Project | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541200% | 4544300% | 39 | Project Existing | April
MDBA | MDBA Kasir - Rembes BBM | List Draft nominal rembes BBM |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4540400% | 4541200% | 4544300% | 39 | Project Existing | April
MDBA | MDBA Kasir - Revisi BTU BKU (Update Patch) | 3. Hilangkan form revisi |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4539800% | 4540000% | 4543200% | 34 | Project Existing | April
MDBA | MDBA Kasir - Revisi BTU BKU (Update Patch) | 2. Jika pengajuan di not approve , bisa mengajukan lagi dengan no yang sama |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4539800% | 4540000% | 4543200% | 34 | Project Existing | April
MDBA | MDBA Kasir - Revisi BTU BKU (Update Patch) | 1. Buat akses untuk kasir bisa buat revisi tanpa approve |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4539800% | 4540000% | 4543200% | 34 | Project Existing | April
MDBA | MDBA Kasir - Revisi BTU BKU (Update Patch) | BKU Benar |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4539800% | 4540000% | 4543200% | 34 | Project Existing | April
MDBA | MDBA Kasir - Revisi BTU BKU (Update Patch) | BTU Benar |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4539800% | 4540000% | 4543200% | 34 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Submit BTU menu Ritase History List |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Auto BTU dan ceklis Submit di menu Not Transferred |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Submit Ceklist Payment VA |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Submit Ceklist Payment Reguler |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Submit Upload Excel |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Input BKU Manual |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Lock transaksi belum closing H+3 (Fixing Bugs) | Input BTU Manual |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4538600% | 4539000% | 4541400% | 28 | Project Existing | April
MDBA | MDBA Kasir - Pergantian Mesin Depos (CKL & XBT) |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4537200% | 4537900% | 4537900% | 7 | Project Existing | Maret
GL | GL - Template Report |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4535100% | 4535700% | 4537600% | 25 | Project Existing | Februari
MDBA | MDBA Invoice - Update Trouble MDBA | Tarikan banding DO Invoice Faktur Pajak dengan Reg Do All masih tidak sesuai totalnya |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4535100% | 4535700% | 4538700% | 36 | Project Existing | Februari
MDBA | MDBA Invoice - Update Trouble MDBA | Tarikan stop dispenser di reg do all masih minus seharusnya plus karena untuk penagihan |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4535100% | 4535700% | 4538700% | 36 | Project Existing | Februari
MDBA | MDBA Cashier - MOM 13 Februari 2024 | Inject Data Saldo Akhir Kasir Depo, kasir akan membuat berita acara dahulu. | Update Mom | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534200% | 4534800% | 4556100% | 219 | Project Existing | Februari
MDBA | MDBA Cashier - MOM 13 Februari 2024 | Ditambahkan Pengunci jika Saldo Akhir Minus, maka tidak dapat closing (Kas Besar, Kecil, BCA) | Update Mom | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534300% | 4534800% | 4534800% | 5 | Project Existing | Februari
MDBA | MDBA Cashier - MOM 13 Februari 2024 | Ditambahkan Pengunci agar tidak dapat closing sebelum dibuat voucher. | Update Mom | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534300% | 4534800% | 4534800% | 5 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 12. BKB Mix Canvasser Ritase belum sesuai | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559600% | 254 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 11. Delivery Order | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559600% | 254 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 10. Sales Order | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 9. Backup Driver di Take Out (Route Type CAN), Apabila ada kesalahan maka lakukan adjustment BKB | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 8. Validasi LHP jika belum terinput di Kasir di Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4559500% | 253 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 7. Pembuatan DO Retail Galon / IOD input by Admin (Jika sudah di input di HH / Admin button DO Disable) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4556100% | 219 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 6. Validasi PB untuk BKB to DO Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 5. DO Pending di input by Admin (DEL, CAN & CAN NON RUTE) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 4. Validasi BKB di Take Out | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA Kasir - Kartu Mesin Setor Cinangka |  | Penambahan user kartu mesin setor cinangka dan cetak dilakukan pengiriman ke depo | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531000% | 4531000% | 1 | Project Existing | Januari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 3. Orderan CAN IOD - MT (Input By Admin & PO) | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 2. Orderan PSS | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Testing | 1. Orderan CRL | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 6. Ubah koneksi ke Dummy link mdba-v2-cashier-new (Development) -> **23 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 5. Plan Testing QA Menyesuaikan -> **Minimal 01 Mar 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 4. Plan Update Page Development -> **23 - 29 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 3. Ubah koneksi ke Dummy (Development) -> **22 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA - Plan & Testing Tanpa HH | Plan Upload Server Dummy | 2. Migrasi ke Server Testing -> **21 Feb 2024** | Tunning | Addhock | Komang, Pandu, Same, Haeriah, Suryana, Teddy | Complete | 100% | 4534200% | 4535100% | 4535100% | 9 | Project Existing | Februari
MDBA | MDBA Entry - Update Query PB BKB |  | Validasi apabila ada adjust BKB | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534100% | 4534300% | 4534300% | 2 | Project Existing | Februari
MDBA | MDBA Cashier - Kotak Saran MDBA |  | By Kotak Saran | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4533700% | 4534300% | 4534300% | 6 | Project Existing | Februari
GL | GL - Tarikan Privilege (Hak Akses) |  | Tarikan excel untuk diberikan ke ZOT (Previlage FoxPro GL) | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534100% | 4534200% | 4534200% | 1 | Project Existing | Februari
MDBA | MDBA Cashier - Update query auto mesin |  | Menampilkan BKB yang hanya dilakukan ritase (exclude BKB yang sudah di Adjust) | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4534100% | 4534300% | 4534300% | 2 | Project Existing | Februari
MDBA | MDBA Cashier - List Data Saldo (New Feature) |  | Pembuatan menu list data history saldo untuk depo yang sudah melakukan closing (Tambahkan filter) | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4533700% | 4533800% | 4533800% | 1 | Project Existing | Februari
GL | GL - Update Saldo GL |  | update saldo GL untuk re-setting database SQL Server | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4533800% | 4534400% | 4534400% | 6 | Project Existing | Februari
MDBA | Issue MDBA Kasir - KLD & MNS |  | Fixing Bugs | Fixing Bugs | Fixing Bugs | Siti Haeriah | Complete | 100% | 4533200% | 4533900% | 4534800% | 16 | Project Existing | Februari
GL | Progress API GL | 3. API Revisi BTU BKU pada kasir untuk menjadi VB VT |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4532200% | 4532900% | 4543600% | 114 | Project Existing | Januari
GL | Progress API GL | 2. Login NEW GL menggunakan nik EIS |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4532200% | 4532900% | 4532900% | 7 | Project Existing | Januari
MDBA | Kartu Mesin Setor Depo Cinangka |  |  | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4530900% | 4530900% | 0 | Project Existing | Januari
GL | GL - Query Sub Subledger |  |  | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4531000% | 4531000% | 4531000% | 0 | Project Existing | Januari
GL | Progress API GL | 1. API Depo Closing Settlement |  | Tunning | New Feature | Siti Haeriah | Complete | 100% | 4532200% | 4532900% | 4532900% | 7 | Project Existing | Januari
MDBA | Update Cost Center by Departement |  | Update Feature | Tunning | Update Feature | Siti Haeriah | Complete | 100% | 4532100% | 4533700% | 4533700% | 16 | Project Existing | Januari
MDBA | Persiapan Mesin Setor Depos (Depo CNK) | 5. Update Kartu Mesin Setor driver, preseller CNK | Script Coding | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531700% | 4532100% | 12 | Project Existing | Januari
MDBA | Persiapan Mesin Setor Depos (Depo CNK) | 4. Submit ceklis dari menu Not Transfered (API) | Script Coding | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531700% | 4532100% | 12 | Project Existing | Januari
MDBA | Persiapan Mesin Setor Depos (Depo CNK) | 3. Menu Transfered - MDBA | Script Coding | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531700% | 4532100% | 12 | Project Existing | Januari
MDBA | Persiapan Mesin Setor Depos (Depo CNK) | 2. Menu Not Transfered (API) - MDBA (perhatikan idLocAPI nya) | Script Coding | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531700% | 4532100% | 12 | Project Existing | Januari
MDBA | Persiapan Mesin Setor Depos (Depo CNK) | 1. Auto Transfer di folder WO cashier new | Script Coding | Tunning | Addhock | Siti Haeriah | Complete | 100% | 4530900% | 4531700% | 4532100% | 12 | Project Existing | Januari
MDBA | Issue MDBA Kasir | Issue Auto Kasir KM Ritase - All Depo | Rit sekarang terinput rit sebelumnya di km_ritase | Fixing Bugs | Fixing Bugs | Siti Haeriah | On Hold | 50% | 4529500% | 4530100% | - | #VALUE! | Project Existing | Januari
MDBA | Issue MDBA Kasir | Issue Auto Kasir KM Ritase - All Depo | BTU Full mesin belum ter insert ke table km ritase | Fixing Bugs | Fixing Bugs | Siti Haeriah | On Hold | 50% | 4529500% | 4530100% | - | #VALUE! | Project Existing | Januari
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 7. buatkan report TB di link GL web old (Persediaan, Pendapatan, HPP) => kebutuhan GL NOVA principle untuk dilihat team accounting detail2 produknya |  | Tunning | New Feature | Siti Haeriah | On Hold | 0% | 4573300% | 4576500% | - | #VALUE! | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 6. Penggabungan account Persediaan, Pendapatan & HPP Mama Suka |  | Tunning | New Feature | Siti Haeriah | On Hold | 0% | 4573300% | 4576500% | - | #VALUE! | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 5. Penggabungan account Persediaan, Pendapatan & HPP Kino |  | Tunning | New Feature | Siti Haeriah | On Hold | 0% | 4573300% | 4576500% | - | #VALUE! | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 4. Penambahan **Jenis Principle** pada menu Voucher Pengeluaran |  | Tunning | New Feature | Siti Haeriah | On Hold | 0% | 4573300% | 4576500% | - | #VALUE! | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 3. Penambahan **Jenis Principle** pada menu Voucher Penerimaan |  | Tunning | New Feature | Siti Haeriah | On Hold | 0% | 4573300% | 4576500% | - | #VALUE! | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 2. Penambahan **Jenis Principle** pada menu BKU & View List BKU |  | Tunning | New Feature | Siti Haeriah | On Hold | 90% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA - Cashier NOVA All Principle | 1. Penambahan **Jenis Principle** pada menu BTU & View List BTU |  | Tunning | New Feature | Siti Haeriah | On Hold | 90% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA | MDBA - Settlement Distribusi Lengkap |  |  | Tunning | New Feature | Siti Haeriah | On Hold | 80% | 4537000% | 4537600% | - | #VALUE! | Project Existing | Maret
GL | FIXING CASE NEWGL TAX | 6. Update query NR YTD untuk case BTT | STAGGING NEW GL TAX | Tunning | Update Feature | Siti Haeriah | Open | 0% | 4594800% |  |  | -45948 | Project Existing | Oktober, 2025
GL | FIXING CASE NEWGL TAX | 15. Persediaan Galon Kosong Belum masuk di NR bawaan zog | LIST CASE | Tunning | Update Feature | Siti Haeriah | Open | 0% | 4592700% | 4592700% | - | #VALUE! | Project Existing | September, 2025
GL | FIXING CASE GL | Tidak ada validasi pada saat Posting dengan posisi masih Difference/selisih | FIXING BUG NEW GL | Fixing Bugs | Fixing Bugs | Siti Haeriah | Open | 0% | 4587000% | 4587800% | - | #VALUE! | Project Existing | Agustus, 2025
MDBA | FIXING BUGS MDBA | 2. Dispenser stop sewa harusnya hapus data di tabel rental product. Selama ini hanya dihapus INS nya aja |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Open | 0% | 4584000% | 4584500% | - | #VALUE! | Project Existing | Juli, 2025
MDBA | FIXING BUGS MDBA | 1. Disepenser input 54 qty, pada saat save jadi 5 qty (pasang baru) |  | Fixing Bugs | Fixing Bugs | Siti Haeriah | Open | 0% | 4584000% | 4584500% | - | #VALUE! | Project Existing | Juli, 2025
GL | GL NOVA (MAMASUKA) by TOOLS SUPPORT | 4. Template Report GL MAMASUKA (foxpro) |  | Tunning | Update Feature | Siti Haeriah | Open | 0% | 4580300% | 4580300% | - | #VALUE! | Project Existing | Mei, 2025
MDBA | MDBA - CASHIER Piutang Karyawan (FAR) |  |  | Tunning | New Feature | Siti Haeriah | Open | 0% | 4579000% | - | - | #VALUE! | Project Existing | Mei, 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | LA3 | GL Mama Suka | New Project | New Feature | Siti Haeriah | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | LA2 | GL Mama Suka | New Project | New Feature | Siti Haeriah | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | LA1 | GL Mama Suka | New Project | New Feature | Siti Haeriah | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | 1M | GL Mama Suka | New Project | New Feature | Siti Haeriah | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | 1K | GL Mama Suka | New Project | New Feature | Siti Haeriah | Open | 0% | 4570200% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA | MDBA - Get nomor BKB pada menu Not Transfered (untuk depo yang pakai mesin setor) | 3. Get nomor BKB pada menu Not Transfered (untuk depo yang pakai mesin setor) |  | Tunning | Update Feature | Siti Haeriah | Open | 0% |  |  |  | 0 | Project Existing | -
GL | Modul Inventory - Arus Barang + Auto Billing | 3. To Journal (Formula Debet Credit) | Modul Finance - Arus Barang | Tunning | New Feature | Oka & Haeriah | Open | 0% | 4550300% | 4553500% | - | #VALUE! | Project Existing | Juli
GL | Modul Inventory - Arus Barang + Auto Billing | 5. To Journal (Formula Debet Credit) | Modul Finance - Auto Billing | Tunning | New Feature | Oka & Haeriah | Open | 0% | 4550300% | 4553500% | - | #VALUE! | Project Existing | Juli

## Suryana (hidden)
Details for TC - Assigned to: Suryana Saputra
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly | Column1
Repot & Dashboard | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Untuk data yang determinet perlu di cek terlebih dahulu agar tidak masuk kedalam penilaian |  | Tunning | Update Feature | Suryana Saputra | Closed | 90% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
Repot & Dashboard | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Untuk bintang pada hasil psikogram tidak tampil |  | Tunning | Update Feature | Suryana Saputra | Closed | 90% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Validasi revisi tidak bisa dilakukan ketika sudah ada no surat |  | Tunning | Update Feature | Suryana Saputra | Closed | 90% | 13/010/2025 | - | - | #VALUE! | Project Existing | Oktober, 2025
WBS | WBS - Desk Audit | Choose Category and PIC |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4583800% | Sel 7/01/25 | 4583900% | 1 | Project Charter | Juni, 2025
WBS | WBS - Desk Audit | Investigasi Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4580200% | Jum 6/27/25 | 4580400% | 2 | Project Charter | Juni, 2025
WBS | WBS - Desk Audit | List Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4579900% | Jum 5/23/25 | 4580000% | 1 | Project Charter | Mei, 2025
WBS | WBS - Desk Audit | Form Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4579900% | Kam 5/22/25 | 4579900% | 0 | Project Charter | Mei, 2025
WBS | WBS - Desk Audit | Login |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4579800% | Kam 5/22/25 | 4579900% | 1 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | Investigasi Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4579100% | Rab 5/14/25 | 4579100% | 0 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | List Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578600% | Jum 5/09/25 | 4578600% | 0 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | Form Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578600% | Jum 5/09/25 | 4578600% | 0 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | Login |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578500% | Jum 5/09/25 | 4578600% | 1 | Project Charter | Mei, 2025
WBS | WBS - Informant | Timeline Tracking Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578400% | Rab 5/07/25 | 4578400% | 0 | Project Charter | Mei, 2025
WBS | WBS - Informant | List Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578400% | Rab 5/07/25 | 4578400% | 0 | Project Charter | Mei, 2025
WBS | WBS - Informant | Form Pelaporan |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578300% | Rab 5/07/25 | 4578400% | 1 | Project Charter | Mei, 2025
WBS | WBS - Informant | Login |  | New Project | New Feature | Suryana Saputra | Closed | 90% | 4578200% | Sel 5/06/25 | 4578200% | 0 | Project Charter | Mei, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | IN | Unpost | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4574100% | 4574200% | - | #VALUE! | Project Existing | September, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | IN SCR |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4593000% | 4593000% | - | #VALUE! | Project Existing | September, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | OUT SCR |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4592900% | 4592900% | - | #VALUE! | Project Existing | September, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | perbaikan ritase dan mengambil data dari bkb | Sps | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4574100% | 4574200% | - | #VALUE! | Project Existing | September, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | Out | Sps | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4573000% | 4573300% | - | #VALUE! | Project Existing | Maret 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | In | Gallon | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4573000% | 4573300% | - | #VALUE! | Project Existing | Maret 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | Out | Gallon | Fixing Bugs | Fixing Bugs | Suryana Saputra | Closed | 90% | 4573000% | 4573300% | - | #VALUE! | Project Existing | Maret 2025
HRIS - EIS | Fixing Bugs Recruitment - HRD | PTK Manual |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4591100% | 4591100% | 4593900% | 28 | Project Existing | September, 2025
HRIS - EIS | Fixing Bugs Recruitment - HRD | Fixing bugs recruitment |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4591100% | 4591100% | 4593900% | 28 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Detail Penilaian per indikator belum masuk ke dalam E-KPI |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4590900% | 4590900% | 4590900% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Untuk Penilaian Point 4. Disiplin karyawan belum auto ke GET |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4590900% | 4590900% | 4590900% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Untuk Menu Penilaian di buat 1 page 1 Menu (Penilaian Per Bulan, Penilaian Mid Year, Penialain End Year) tidak perlu di buat ceklist |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4591000% | 4591800% | 4591800% | 8 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Jika PTK manual, tambahkan tombol + (row baru) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4591200% | 4591200% | 4591200% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Hasil repot psikogram di buat pdf dengan hasil keseluruhan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4591200% | 4591200% | 4591200% | 0 | Project Existing | September, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 090925 | Psikogram di buat menjadi 1 view pada saat di print preview |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4591200% | 4591200% | 4591200% | 0 | Project Existing | September, 2025
MDBA | MBDA - Update Feature CRL Colombo | Update tipe transaksi PO DO Blank menjadi auto kredit |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4590800% | 4591200% | 4590900% | 1 | Project Existing | September, 2025
MDBA | MBDA - Update Feature CRL Colombo | Penambahan tipe transaksi Tunai/Kredit di Dalam Rute, Luar Rute, SO Pending |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4590800% | 4591200% | 4590900% | 1 | Project Existing | September, 2025
Waterout | Issue WaterOut Depo Alam Sutera |  | 1.Produk BS Vit Tidak Muncul Di Menu IN gallon (Checker) tampilan view karena secara data sudah masuk | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4529400% | 4529600% | 4529600% | 2 | Project Existing | Januari
HRIS - EIS | List Case Penilaian Mid Year | Total nilai keseluruhan (total nilai I + II + III + IV) masih belum sesuai |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4589100% | 4589000% | 4589100% | 0 | Project Existing | Agustus, 2025
HRIS - EIS | List Case Penilaian Mid Year | Point 4 Disiplin Karyawan total nilai belum sesuai |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4589100% | 4589000% | 4589100% | 0 | Project Existing | Agustus, 2025
HRIS - EIS | List Case Penilaian Mid Year | Point 3 Soft Kompetensi tidak ada nilai total |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4589100% | 4589000% | 4589100% | 0 | Project Existing | Agustus, 2025
HRIS - EIS | List Case Penilaian Mid Year | Perhitungan total rekap bulan januari - juni belum sesuai |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4589100% | 4589000% | 4589100% | 0 | Project Existing | Agustus, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Pembuatan Delivery Order (DO Blank) |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4584300% | 4584500% | 4591500% | 72 | Project Charter | Juni, 2025
MDBA | MDBA - Limit Kredit Pelanggan | Pembuatan Sales Order (CRL) |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4584000% | 4584200% | 4591500% | 75 | Project Charter | Juni, 2025
MDBA KINO | MDBA NOVA - New Feature DO Blank |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4588700% | 4588800% | 4588800% | 1 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Untuk kolom aktif 1 di ganti jadi status (aktif / tidak aktif) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588100% | 4591200% | 34 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Tambahkan kolom jabatan yang di lamar |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588000% | 4591200% | 34 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Tambahkan Master Data pada Psikogram |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588400% | 4591200% | 34 | Project Existing | Agustus, 2025
E-Learning | Meeting Be Weekly Coordination HRD & ICT 080825 | Tambahkan kolom pembanding antara niltai pretest dan postest dalam bentuk percetage (%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588100% | 4591200% | 34 | Project Existing | Agustus, 2025
E-Learning | Meeting Be Weekly Coordination HRD & ICT 080825 | Pada kolom nilai pretest dan postest angka di buat 2 angka saja |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588100% | 4591200% | 34 | Project Existing | Agustus, 2025
HRIS - EIS | Meeting Be Weekly Coordination HRD & ICT 080825 | Untuk Core value sikap di ganti super data akan di kirim oleh mas umri |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587800% | 4588000% | 4591200% | 34 | Project Existing | Agustus, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk kolom target pada master KPI dan dashboard di buat menjadi (%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586900% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk Template Inject detail perindikator KPI Bulanan Januari - Maret di ambil dari bulan april datanya oleh ict |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586900% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk Task Update Tambahan E-Learning di buatkan timelinenya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586900% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Data yang akan dikirim dari mbk mala 1. Listing Case Psikotes 2. Template report Psikotes 3. Template Psikogram |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586300% | 4593000% | 70 | Project Existing | Juli, 2025
Waterout | Issue WaterOut - All Depo | Unpost IN Galon |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4529600% | 4530000% | 4531400% | 18 | Project Existing | Januari
Waterout | Issue WaterOut - All Depo | Unpost IN SPS |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4529600% | 4530000% | 4531400% | 18 | Project Existing | Januari
Waterout | Issue WaterOut - All Depo | Unpost OUT SPS |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4529600% | 4530000% | 4531400% | 18 | Project Existing | Januari
Waterout | Issue WaterOut - All Depo | Unpost IN Antar Depo |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4529600% | 4530000% | 4531400% | 18 | Project Existing | Januari
Waterout | Issue WaterOut - All Depo | Unpost OUT Antar Depo |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4529600% | 4530000% | 4531400% | 18 | Project Existing | Januari
Waterout | Issue WaterOut - All Depo |  | pengecekan data inputan waterout (Data sudah di input tetapi BKB masih muncul ) sehingga menyebabkan user input berkali-kali dan data menjadi doubel di Report dashboard | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4531000% | 4531600% | 4531400% | 4 | Project Existing | Januari
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Tambakan Psikogram pada hasil E-Recruitment |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586300% | 4593000% | 70 | Project Existing | Juli, 2025
HRIS - EIS | Update MOM Meeting Be Weekly Coordination HRD & ICT 170725 | Untuk data karyawan resign pada E-KPI dan dashboard di hilangkan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4586000% | 4586000% | 4593000% | 70 | Project Existing | Juli, 2025
MDBA | Update Feature MDBA - Hilangkan PPN dan DPP | 3. TARIK JAMINAN |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587500% | 4587600% | 4587600% | 1 | Project Existing | Agustus, 2025
MDBA | Update Feature MDBA - Hilangkan PPN dan DPP | 1. TARIK PINJAM |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4587500% | 4587600% | 4587600% | 1 | Project Existing | Agustus, 2025
WBS | New Application IA - WBS (Wisthle Blowing System) |  |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4584500% | 4585900% | 4587300% | 28 | Project Charter | Juli, 2025
Waterout | Penambahan Menu Unpost Tarikan Gallon - Waterout All Depo | In Tarikan Gallon |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4530100% | 4530600% | 4531400% | 13 | Project Existing | Januari
MDBA | MDBA - NEW FEATURE PO MT | Pengurang Sisa Saldo PO By DO Submit |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4585200% | 4586900% | 4588000% | 28 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Penginputan Qty Lock Sisa Saldo By PO |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4585200% | 4586900% | 4588000% | 28 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | Get Data PO Berdasarkan Customer |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4585200% | 4586900% | 4588000% | 28 | Project Charter | Juni, 2025
MDBA | MDBA - NEW FEATURE PO MT | DO Blank Integrate PO MT |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4585200% | 4586900% | 4588000% | 28 | Project Charter | Juni, 2025
HRIS - EIS | Addhock - Support Case HRD | inject KPI helper & driver |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4584000% | 4584000% | 4585900% | 19 | Project Existing | Juli, 2025
HRIS - EIS | Addhock - Support Case HRD | inject KPI penilaian BM |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4584000% | 4584000% | 4584000% | 0 | Project Existing | Juli, 2025
HRIS - EIS | Addhock - Support Case HRD | Inject KPI dept fleet |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4584000% | 4585900% | 4585900% | 19 | Project Existing | Juli, 2025
HRIS - EIS | Addhock - Support Case HRD | Inject KPI dept GA |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4584000% | 4584000% | 4584000% | 0 | Project Existing | Juli, 2025
MDBA | MDBA - Fixing bugs - Tarik jaminan depo ASA |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4584000% | 4584000% | 4584000% | 0 | Project Existing | Juli, 2025
Waterout | WATEROUT - ADDHOOK |  |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4584100% | 4584100% | 4584100% | 0 | Project Existing | Juli, 2025
MDBA | MDBA Buy and Sell - Fixing Bugs | 3. Penginputan DO Blank dengan tipe TARIK JAMINAN, harga masih belum sesuai |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4582400% | 4582700% | 4582800% | 4 | Project Existing | Juni, 2025
MDBA | MDBA Buy and Sell - Fixing Bugs | 2. Penginputan DO Blank dengan tipe TARIK JAMINAN dan kondisi tidak ada saldo, masih bisa ter submit |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4582400% | 4582700% | 4582800% | 4 | Project Existing | Juni, 2025
MDBA | MDBA Buy and Sell - Fixing Bugs | 1. Penginputan DO Blank dengan tipe TARIK JAMINAN harganya masih tidak mines (-), Depo ASA |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4582400% | 4582700% | 4582800% | 4 | Project Existing | Juni, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | BI Portal |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | DO Blank (Tarik Pinjam & Retur) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | SO CRL (2x Penginputan & Luar Rute) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | Retur SO Pabrikan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | Logic View Pelanggan Bisa melihat history |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | PJ & TPJ |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA - Buy and Sell (Perubahan Galon Jaminan ke Jual) | Jaminan Muncul Saat Tarik Jaminan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579800% | 4580500% | 4580800% | 10 | Project Existing | Mei, 2025
MDBA | MDBA NOO - TVIP | 1. Pada saat update, masih tervalidasi KTP |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4579600% | 4580000% | 4579600% | 0 | Project Existing | Mei, 2025
Waterout | Update MOM Waterout (New Feature) | 5. Hilangkan penginputan KM |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4576800% | 4577000% | 4592900% | 161 | Project Existing | April, 2025
Waterout | Update MOM Waterout (New Feature) | 4. Jam di lock otomatis |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4576800% | 4577000% | 4592900% | 161 | Project Existing | April, 2025
Waterout | Update MOM Waterout (New Feature) | 3. Tambahkan detail armada berdasarkan BKB |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4576800% | 4577000% | 4592900% | 161 | Project Existing | April, 2025
Waterout | Update MOM Waterout (New Feature) | 2. Hilangkan list produk, hanya fokus in out |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4576800% | 4577000% | 4592900% | 161 | Project Existing | April, 2025
Waterout | Update MOM Waterout (New Feature) | 1. Scan BKB |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4576800% | 4577000% | 4592900% | 161 | Project Existing | April, 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA Mama Suka - Config Segment (New Feature) |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4572300% | 4573300% | 4573300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | pemotongan stock po ketika input btb supplier |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | History data insert supplier dan adjustment supplier |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | automatis btb supplier dari po di upload |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Upload PO |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | List data PO |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Untuk Prubahan Status Closed Pada PO di pastikan setiap di awal bulan dari Inv |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MOM Koordinasi ICT & ACC 12 Maret 2025 | Di buatkan feature untuk upload Po pada MBDA untuk view draft di admin nova.. dan di buatkan pilihan ""Jaksel / Jaktim"" untuk MDBA Nova Mama Suka, Setalah di lakukan Upload PO admin dapat cheklist PO yang sudah di kirim (Untuk diterimakan) |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4573300% | 4574300% | 4574300% | 10 | Project Existing | Maret 2025
MDBA KINO | MDBA NOVA Mama Suka - Config Segment (New Feature) |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4572300% | 4572300% | 4572300% | 0 | Project Existing | Maret 2025
MDBA | Update - MDBA NOO Grouping customer (aqua) |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4571900% | 4571900% | 4571900% | 0 | Project Existing | Maret 2025
HRIS - EIS | Recruitment Online - Tahap 2 | Proses PKWT |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4571200% | 4571200% | 12 | Project Charter | Februari 2025 | Susulan
HRIS - EIS | Recruitment Online - Tahap 2 | Interview User |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4571200% | 4571200% | 12 | Project Charter | Februari 2025 | Susulan
HRIS - EIS | Recruitment Online - Tahap 2 | Interface Biodata Diri |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4571200% | 4571200% | 12 | Project Charter | Februari 2025 | Susulan
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Master Promo Drop Size | Data Master Mama Suka | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570600% | 4570600% | 4 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Master Promo Qty (Bundling) | Data Master Mama Suka | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570600% | 4570600% | 4 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Master NOO | Data Master Mama Suka | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4571000% | 4571000% | 8 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Master Rute | Data Master Mama Suka | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570600% | 4570600% | 4 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Upload Excel PO BTB Supplier | Inventory | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570800% | 4570800% | 6 | Project Charter | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BTB Depot | Inventory | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Adjustment BKB Depot | Inventory | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BKB Depot | Inventory | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | BTB Depot | Inventory | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570200% | 4572800% | 26 | Project Existing | Februari 2025
MDBA NOVA - MAMA SUKA | MDBA NOVA - MAMA SUKA | Proses Surat Tugas | Distribusi & Penjualan | New Project | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570600% | 4570600% | 4 | Project Existing | Februari 2025
MDBA | Update MOM Meeting Review Loading Sore 16 Januari 2025 - OPR | 4. Validasi Kompres Foto Jika Kurang Dari 1 MB Tidak di kompres |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4570900% | 4573500% | 35 | Project Existing | Februari 2025
MDBA | Update MOM Meeting Review Loading Sore 16 Januari 2025 - OPR | 3. Input Nominal & Foto Far dll Setelah Pengerjaan Selesai |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4570900% | 4573500% | 35 | Project Existing | Februari 2025
MDBA | Update MOM Meeting Review Loading Sore 16 Januari 2025 - OPR | 2. Input Nama Bengkel External, |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4570900% | 4573500% | 35 | Project Existing | Februari 2025
MDBA | Update MOM Meeting Review Loading Sore 16 Januari 2025 - OPR | 1. Tambahkan Alamat Bengkel External |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4570000% | 4570900% | 4573500% | 35 | Project Existing | Februari 2025
MDBA KINO | MDBA NOVA - Mekanisme Promo (Feature Baru) |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4570200% | 4570200% | 4572700% | 25 | Project Existing | Februari 2025
HRIS - EIS | HRIS EiS - Penilaian Karyawan (Fixing Bugs) | Detail Penialain Karyawan (Excel) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4567000% | 4567100% | 4567100% | 1 | Project Existing | Januari 2025
HRIS - EIS | HRIS EiS - Penilaian Karyawan (Fixing Bugs) | Detail Penialain Karyawan (Pop Up) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4567000% | 4567100% | 4567100% | 1 | Project Existing | Januari 2025
E-Learning | HRIS EiS - E-Learning | User test masih bisa test, padahal di setting tidak sesuai semester |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4569100% | 4569100% | 4579600% | 105 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan edit untuk menambahkan user test dengan kondisi hanya bisa edit di semester berjalan |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4569100% | 4569100% | 4579600% | 105 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Validasi start date & end date tidak bisa sama dalam 1 semester |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4569100% | 4569100% | 4579600% | 105 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Penambahan Video |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Session soal materi essay dan pg jadi satu sehingga test tidak sesuai |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Waktu tidak sesuai |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Jika username atau password tidak sesuai, tambahkan alert |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan sweet alert jika data sudah di simpan (Menu User Test) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan button back/kembali jika ada inputan form page selanjutnya |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Pada saat import excel lalu submit, direct halaman tidak sesuai ke form yang di tuju |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan sweet alert jika data sudah di simpan |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | List exam tampilkan berdasarkan data terbaru/desc |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan *(merah) jika wajib di isi |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Upload soal pada saat browse folder difilter berdasarkan excel saja |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Input title dengan kondisi text panjang terpotong |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan sweet alert jika data sudah di simpan |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | List content tampilkan berdasarkan data terbaru/desc |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Upload materi pada saat browse folder difilter bedasarkan dokumen pdf dan jpg saja |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Kolom time dibuat berdasarkan menit seperti pada saat penginputan time |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tambahkan sweet alert jika data sudah di simpan |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tahun dibuat select option, tambahkan beberapa tahun saja |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4566700% | 4567300% | 4579600% | 129 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Penambahan fiture interaktif tutorial |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Cover Materi dibuatkan fitur upload(minor) |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Max Untuk reset waktu hanya di perbolehkan 1x dalam case - case tertentu |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Tanggal submit di masukan pada export excel |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Standar kelulusan per materi dari mas umri |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
E-Learning | HRIS EiS - E-Learning | Pada Saat Selesai membuka materi button tidak auto ke buka harus di refresh terlebih dahulu |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4566500% | 4567400% | 4579600% | 131 | Project Charter | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | encript delivery order **DONE** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | validasi kendaraan yang tidak ada di master kendaraan dari kendaraan batangan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | fixing bugs ( customer blank) **DONE** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Config tanggal PB Canvas mengikuti gen closing |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Jika input do non rute dengan kondisi buka 2 tab, do terinput double **DONE** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Validasi SO induk double pada saat input SO Pending |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Validasi jika tidak ada rute tidak bisa proses surat tugas |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Tambahkan nama pelanggan saat transaksi CRL (transaksi ke 2 dan luar rute) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4565900% | 4566900% | 4579600% | 137 | Project Existing | Januari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Disable button PB Canvas (1x klik) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | Desember
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Saat pembuatan Canvas Non rute, validasi jika kendaraan tidak terdaftar di master kendaraan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | -
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Tambahkan end call semua toko yang belum sudah transaksi (Validasi harus mulai terlebih dahulu baru bisa endcall) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | -
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Saat pembuatan can non rute button dapat di double klik, output menjadi double karna button tidak disable setelah klik pertama |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | -
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Kode KIT di (Sales Order, Delivery Order, DO Canvas) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | -
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Ketika ada double KTP, tambahkan keterangan double di depo mana saja |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562800% | 4562800% | 4562800% | 0 | Project Existing | Desember
MDBA | Update MOM Meeting Review Loading Sore 28 November 2024 | Tambahkan Timeline pada saat Perbaikan Internal / Eskternal pada status sebelum Closed |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562400% | 4563300% | 4570000% | 76 | Project Existing | November
MDBA | Update MOM Meeting Review Loading Sore 28 November 2024 | Jika spv delivery sudah upload hasil foto perbaikan maka statusnya Done, Setelah di verifikasi oleh fleet maka statusnya jadi Closed |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562400% | 4563300% | 4570000% | 76 | Project Existing | November
MDBA | Update MOM Meeting Review Loading Sore 28 November 2024 | Master Bengkel Eksternal di kirim dari Fleet |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562400% | 4563300% | 4570000% | 76 | Project Existing | November
MDBA | Update MOM Meeting Review Loading Sore 28 November 2024 | Change Name MDBA RTG Kendaraan jadi RTG Perbaikan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562400% | 4563300% | 4570000% | 76 | Project Existing | November
MDBA | Update MOM Meeting Review Loading Sore 28 November 2024 | Penambahan Kolom untuk input nama bengkel Eksternal, Input Nominal FAR, Upload Foto FAR, Upload Foto Kuitansi, Upload Foto After |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4562400% | 4563300% | 4570000% | 76 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Re frame online rec |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4568900% | 82 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Export excel per user di psikotest manual |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Tutorial Penilaain Karyawan Video |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Re Frame tampilan penilaian karyawan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Re Frame tampilan penilaian karyawan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Menu Interview 1. Hasil Interview User di tambahkan jabatan yang di lamar 2. Kolom Pendidikan & Usia di Hide 3. Kolom Kelebihan & Kekurang di Hide 4. Untuk kolom cetak hasil interview di pindah sebelum kolom undangan PKWT |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4568900% | 82 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Menu Jadwal Interview 1. Setelah user approve baru bisa aksi kirim untuk mengirim jadwal itu by email 2. bisa send direct ke whatsapp pada saat klik button kirim |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Menu Hasil Psikotes 1. View Hasil Psikotes di buat Freeze pada pojok kanan agar fitur search nya next page nya tidak perlu di geser 2. Hasil download bisa di standarisasi dengan format terbaru deri team HR 3. Untuk button aksi interview tidak bisa di akses 4. Pada saat psikotes manual pendaftaran di tambahkan NIK KTP, Email, No Handpone |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Screening CV : 1. Menu Filter Dept & tanggal Belum bisa 2. Nilai CV Sudah tidak bisa di akses 3. Untuk hasil screening cv hasil outputnya tambahkan rekap dan detail untuk hasil exportnya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Timeline di menu E-Recruitment di hide dulu untuk menunya karna belum ada isi contenyanya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Tambahkan list jabatan di list account |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Export list account di buatkan tanggal di buat |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Hanya Dept Aktif yang di tampilkan sesaui HRIS pada pilihan Kategori departmen |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Di tambahkan contact person untuk pic trainer pada bagian bawah Footer |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4569600% | 89 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Di buatkan Master Bobot Grading Per tahun |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | SPV UP 85 Ke atas & Staff 80 Ke atas, di bawah minimal nilai di berikan warna merah per point yang ada pada pencapaian KPI |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Pada menu penilaian keryawan tertukar dengan penilain end year |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Penilaian Karyawan di ganti jadi penilaian Bulanan Penilaian End Year di ganti jadi Penilaian End Year |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
MDBA | Validasi Counter DO - KLD, MNS | Surat Tugas Canvasser / Non Rute (suryana) | Validasi DO Counter | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
MDBA | Validasi Counter DO - KLD, MNS | DO Pabrikan (suryana) | Validasi DO Counter | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4530200% | 4530900% | 4530900% | 7 | Project Existing | Januari
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 05 November 2024 | Untuk Point Uji Kopetensi di buat N/A dan untuk point 90 = 100 (50%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4560700% | 4561800% | 4564300% | 36 | Project Existing | November
MDBA | Update MOM Meeting Review Loading Sore 301024 | Tambah rekap yang sudah closed (perbaikan internal/eksternal) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4559500% | 4561800% | 4561800% | 23 | Project Existing | Oktober
MDBA | Update MOM Meeting Review Loading Sore 301024 | Tambah 1 kolom count day (outstanding) di menu progress/kendaraan approve |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4559500% | 4561800% | 4561800% | 23 | Project Existing | Oktober
MDBA | Update MOM Meeting Review Loading Sore 301024 | Button close di hapus |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4559500% | 4561800% | 4561800% | 23 | Project Existing | Oktober
MDBA | Update MOM Meeting Review Loading Sore 301024 | Not approved diganti closed & tambah keterangan saat closed |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4559500% | 4561800% | 4561800% | 23 | Project Existing | Oktober
MDBA | Update MOM Meeting Review Loading Sore 301024 | Approval di ganti pengajuan perbaikan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4559500% | 4561800% | 4561800% | 23 | Project Existing | Oktober
Waterin | WaterOut - Produk reguler + NJ tidak sum (Fixing Bugs) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4530200% | 4530600% | 4530900% | 7 | Project Existing | Januari
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Validasi SO jika sudah terinput di DO ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558800% | 4558800% | 4558800% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Tambahkan loading ketika insert SO pending ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558800% | 4558800% | 4558800% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Total harga tidak sesuai dengan qty yang di input |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558800% | 4558800% | 4558800% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Jika ada produk FOC, tidak mengurangi stok konfigurasi FOC (SO : All SO Colombo, DO : Surat Tugas Non Rute & SO Pending) ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558600% | 4558600% | 4558600% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Add Driver Di keterangan ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558800% | 4558800% | 4558800% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Fitur cari DO masih bisa di input 2x, tambahkan alert atau tampilkan detail DO ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558600% | 4558600% | 4558600% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Fitur cari DO di List Surat Tugas Non Rute ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558300% | 4558300% | 4558300% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | Input DO belum bisa FOC ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558600% | 4558600% | 4558600% | 0 | Project Existing | Oktober
MDBA | MDBA - Note Implementasi (BRJ, LTA, BTR, CKL) | DO Blank ketika nama customer panjang hasil printnya menutupi kolom SK ***(DONE)*** |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558600% | 4558600% | 4558600% | 0 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Get nik atasan dan generate ke barcode |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Validasi NIK sesuai atau tidak |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Export Excel by Jabatan & KPI |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Pada Menu Contet di buatkan tarikan nilai by excel , format akan di kirimkan Mas Bisyri |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Di buatkan link dummy untuk test team HR |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Di buatkan Menu terpisah untuk upload excel KPI Grouping |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Untuk Format Template akan di kirimkan mas umri" |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | "Untuk Format BOBOT KPI dan Target KPI Mengacu pada Target yang sudah ada dat master |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Hide Nilai Point Keseleurahan jika di pilih KPI Bulanan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Buat Bobot KPI dari Tinggi ke renda (Viewnya) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558300% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Untuk KPI CRL Di buatkan mekanisme Upload sambil di evaluasi untuk mekanisme kedepanya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 25 September 2024 | Untuk Jabatan Sales Operational Staff (CRL Depo) di buatkaan detail untuk KPI Inbound & Outbound |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4558100% | 4558200% | 4564300% | 62 | Project Existing | Oktober
MDBA | MDBA - New Feature Monitoring Stock On Hand SO |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4557400% | 4557600% | 4557600% | 2 | Project Existing | Oktober
Repot & Dashboard | MDBA Entry - New Feature Config Edit DO (Mix Galon & SPS) | 2. Config DO dari Canvas |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4557400% | 4557600% | 4557600% | 2 | Project Existing | Oktober
MDBA | MDBA Entry - Config DO Blank Per Driver |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4557500% | 4557500% | 4557500% | 0 | Project Existing | Oktober
HRIS - EIS | addhock - Import kpi dept |  |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4554500% | 4554500% | 4554500% | 0 | Project Existing | September
MDBA | Validasi customer hold |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552800% | 4552800% | 4566400% | 136 | Project Existing | Agustus
MDBA | MDBA Entry - SO Mix by Promo | Trigger update status on menjadi off |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA Entry - SO Mix by Promo | Create SO transaksi kedua dan selanjutnya (di dalam dan luar rute) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA Entry - SO Mix by Promo | Create Sales order Pending |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA Entry - SO Mix by Promo | Crud Config SO By SO Mix by Promo (ada di Tools Support) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
MDBA | MDBA Entry - SO Mix by Promo | Create SO by CRL Colombo |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552500% | 4556000% | 4556000% | 35 | Project Existing | Agustus
Waterout | WaterOut - Penambahan intItemnumber pada tarik jaminan |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552600% | 4552700% | 4560100% | 75 | Project Existing | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Hide total penilaian jika memilih penilaian per bulan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | penambahan menu user exam |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | reframe template |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Import soal by excel(20%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | list psikotest online |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | configurasi semester |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | configurasi materi by database |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | configurasi posttest & pretest by database |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Belum ada button simpan setelah kolom Catatan atasan dan tanggapan karyawan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Untuk kolom bobot & target KPI bisa di lock dan disesuaikan dengan master KPI yang telah dikirim |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Belum ada pilihan list bulan untuk menentukan data pencapaian KPI yang akan di input |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Penambahan bulan di penilaian Perbulan |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Matriks Materi kurikulum perjabatan untuk konfigurasi di E-learning |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Dibuatkan konfigurasi (Pre Test / Post Test) Untuk E - Learning |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Format penamaan Menu Di samaratakan huruf besar kecilnya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Penambahan kategori KPI perjabatan berdasarkan 1 jabatan lebih dari 2 KPI |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4564300% | 119 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Format Email Otomatis Reminder PKWT format dari Mas Umri |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 16 Agustus 2024 | Pada saat di klik aksi perpanjangan akan tampil view modal kontrak terdapat pilihan (dengan catatan (3 atau 6 bulan) / tanpa catatan (Langsung input Kontrak)) , dan tampil notifikasi ke email atasan terkait pada saat evaluasi di penilaian karayawan. |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4552400% | 4553800% | 4566500% | 141 | Project Charter | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 7. Penambahan fitur print di cetakan DO Blank tampil ID Customer **(DONE)** |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4550900% | 4551800% | 4551800% | 9 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 5. Approval NOO ditampilkan listnya berdasarkan depo masing-masing **(DONE)** |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4550900% | 4551300% | 4551300% | 4 | Project Existing | Agustus
MDBA | MDBA Entry - Update Fixing Bugs | 1. Pembuatan DO Canvas Delivery by Tanggal (DEL CAN, NON RUTE) |  | Tunning | Fixing Bugs | Suryana Saputra | Complete | 100% | 4550900% | 4551000% | 4551000% | 1 | Project Existing | Agustus
E-Learning | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 (E-Learning) | 3. penambahan fiture materi (50%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4549900% | 4550400% | 4567000% | 171 | Project Existing | Juli
E-Learning | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 (E-Learning) | 2. penambahan master waktu (85%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4549900% | 4550400% | 4567000% | 171 | Project Existing | Juli
E-Learning | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 (E-Learning) | 1. penambahan kategori soal (PG atau essay)(80%) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4549900% | 4550400% | 4567000% | 171 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 7. Validasi submit DO agar tidak double pada saat penginputan | Update Training MDBA | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4550200% | 4550400% | 4550400% | 2 | Project Existing | Juli
MDBA | MDBA - Update & Fixing Bugs Training MDBA | 3. Button pengajuan backup driver hanya tampil di driver saja | Update Training MDBA | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4550200% | 4550400% | 4550200% | 0 | Project Existing | Juli
HRIS Recruitment - Psikotes | Addhock - Import master KPI |  |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4549200% | 4549600% | 4551000% | 18 | Project Existing | Juli
MDBA | MDBA Entry - Update Feature STD Non Rute |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4549000% | 4549200% | 4549000% | 0 | Project Existing | Juli
Waterout | Addhock Tanggal 16-07-2024 | 3. support waterout selisih dms vs waterout |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4548900% | 4548900% | 4548900% | 0 | Project Existing | Juli
Waterout | Addhock Tanggal 16-07-2024 | 2.support pembuatan acount psikotest untuk tanggal 18-07-2024 |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4548900% | 4548900% | 4548900% | 0 | Project Existing | Juli
Waterout | Addhock Tanggal 16-07-2024 | 1.support assesment wop perubahan waktu kwartal menjadi 31-07-2024 |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4548900% | 4548900% | 4548900% | 0 | Project Existing | Juli
MDBA | Update MDBA - Menambahkan filter Can Non Rute |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4548400% | 4548500% | 4548500% | 1 | Project Existing | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | Kandidat Job Street & Portal menjadi 1 Alur (Psikotes -> Interview) |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | Login - Data Diri - Rangkaian Test (Portal Job TVIP) |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | Form Pendidikan Terakhir Hanya Menampilkan Tingkatan nya (Diploma, Strata 1, Strata2) |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | Memperbaiki Lama Waktu OTP / Konfirmasi Email Portal Job TVIP |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | HR akan Membuat Username dan Password untuk Kandidat yang akan Melamar melalui Jobstreet. |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | HRIS EiS - MOM Koordinasi ICT & HRD 09 Juli 2024 | E-Learning akan dilakukan Adopsi dari Aplikasi Assetment WOP |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4548300% | 4549600% | 4549600% | 13 | Project Charter | Juli
HRIS - EIS | New Feature - Form Gratifikasi |  |  | Tunning | New Feature | Suryana Saputra | Complete | 100% | 4547900% | 4548500% | 4582600% | 347 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 3. List Input DO CAN NON RUTE | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 2. List Input DO CAN | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | MDBA Entry - Unlock Input Qty | List validasi inputan qty 352 | 1. SO CRL | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4547500% | 4547600% | 4547600% | 1 | Project Existing | Juli
MDBA | Addhock - Persiapan Blitz DO Blank |  |  | Tunning | Addhock | Suryana Saputra | Complete | 100% | 4546900% | 4547100% | 4547100% | 2 | Project Existing | Juni
MDBA | Update - Mdba Colombo Pabrikan |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4547000% | 4547700% | 4548900% | 19 | Project Existing | Juni
MDBA | MDBA - MOM Koordinasi ICT & ACC 18 Juni 2024 | Hari minggu otomatis terbuka rute semuanya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4546300% | 4547700% | 4547700% | 14 | Project Existing | Juni
HRIS - EIS | HRIS E-KPI - MOM Finalisasi 13 Juni 2024 | Tambahan untuk pilihan upload data pencapaian KPI |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4546200% | 4547700% | 4548300% | 21 | Project Existing | Juni
HRIS - EIS | HRIS E-KPI - MOM Finalisasi 13 Juni 2024 | Penambahan 1 kategori penilaian untuk Submit Pencapaian KPI Bulanan (Hanya Point Objectivenya saja) |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4546200% | 4547700% | 4548300% | 21 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 1. Layout Delivery bisa Canvas |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 7. Validasi DO Non Rute Berdasarkan Segment Driver |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 6. Surat Tugas Non Rute dan add DO STD Canvas field szStatusCanvas otomatis 1 di tbl doccallitem |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 5. Tampilkan ID Customer dan Nama Customer jika sudah di input |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 4. Print Range masih lebih 1 |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 3. Add DO tambahan dan Validasi tidak boleh melebih 5 DO / Hari |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 2. DO Canvas STD Input Admin |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
MDBA | MDBA Entry - DO Canvas Merge STD (Delivery Bisa Can) | 1. Penambahan Type DEL Di print range & List std canvas |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544800% | 4545600% | 4548100% | 33 | Project Existing | Juni
Assesment Wop | Assessment WOP - Data tidak masuk saat submit (Fixing Bugs) |  |  | Tunning | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544700% | 4544900% | 4545300% | 6 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 7. Pada saat approval backup, kendaraan lama tidak sesuai dengan PB dan detail kendaraan lama blank | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 6. Sweet Alert disamakan dengan template std delivery | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 5. Error pada saat simpan PB Canvas | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Fixing Bugs Before Implementasi | 4. Kendaraan status inanctive masih bisa di simpan PB Canvas | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 9. Backup Drivr Canvas | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 7. PB Canvas Non Rute | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
MDBA | MDBA Kasir - MOM Finalisasi BBM 1 Siklus & Non 1 Siklus | Listing Validasi BKB Dengan Kendaraan | 6. PB Canvas Retail Galon & IOD | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544400% | 4544800% | 4546400% | 20 | Project Existing | Juni
Assesment Wop | Assessment WOP - Fixing Bugs |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4543900% | 4544200% | 4544200% | 3 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | out antar depo sps |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | In antar depo sps |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | Out SPS |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | In SPS |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | Out Antar Depo |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | In Antar Depo |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | Out Gallon |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
Waterout | WaterOut Security - Proses hide alur security | In Gallon |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4544200% | 4545000% | 4577000% | 328 | Project Existing | Mei
MDBA | MDBA - Update Query Load Lama (Fixing Bugs) | Input permintaan barang canvas ( saat mix tambah lama ) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
MDBA | Issue MDBA Canvasser - KLD, MNS | 1. Tambahkan validasi alert jika do sudah habis di submit di HH pada saat sebelum buat pb. | Fixing Bugs | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4530100% | 4530300% | 4530700% | 6 | Project Existing | Januari
MDBA | Issue MDBA Canvasser - KLD, MNS | 2. BKB non mix tampil validasi alert, namun masih bisa submit. | Fixing Bugs | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4529900% | 4530700% | 4530700% | 8 | Project Existing | Januari
MDBA | MDBA - Update Query Load Lama (Fixing Bugs) | Masuk menu permintaan barang canvas - pb canvas |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4544800% | 4545400% | 4545400% | 6 | Project Existing | Juni
Waterout | Update MOM Meeting Koordinasi IOPR dan All Ka.Dept - 16 Mei 2024 | 3. Waterout security new implementasi secepatnya | Update MOM | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4543600% | 4544300% | 4543600% | 0 | Project Existing | Mei
Waterout | Update MOM Meeting Koordinasi IOPR dan All Ka.Dept - 16 Mei 2024 | 2. Tambahkan QTY New Jugs pada Kosongan | Update MOM | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4543600% | 4544300% | 4543600% | 0 | Project Existing | Mei
Waterout | Update MOM Meeting Koordinasi IOPR dan All Ka.Dept - 16 Mei 2024 | 1. PET diganti dengan New Jugs | Update MOM | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4543600% | 4544300% | 4543600% | 0 | Project Existing | Mei
MDBA | MOM Meeting Update Progress Dept OPR 26 April 2029 | MDBA Fleet : Update Status Perbaikan dari ticket pengadaan spv delivery berdasarkan BA yang sudah di verifikasi oleh SPV Delivery |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4540800% | 4542200% | 4542200% | 14 | Project Existing | April
MDBA | MOM Meeting Update Progress Dept OPR 26 April 2029 | MDBA SPV Delivery : Penambahan Kolom Foto Kerusakan, Keterangan Kerusakan, PIC Spv Delivery Memverifikasi BA Dari hasil Upload Security ketika di proses akan masuk ke MDBA Fleet Untuk Proses Selanjutnya, Pengajuan Tiket dan Progress Perbaikanya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4540800% | 4542200% | 4542200% | 14 | Project Existing | April
Waterout | MOM Meeting Update Progress Dept OPR 26 April 2024 | 2. Update responsif Web Waterout, di versi saat ini tidak responsif tampilan webnya |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4540800% | 4542200% | 4542200% | 14 | Project Existing | April
Waterout | MOM Meeting Update Progress Dept OPR 26 April 2024 | 1. Senin 29 April Upload Ke Production Waterout Batch Number Update Terakhir dan Launcing All Depo | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4540800% | 4542200% | 4542200% | 14 | Project Existing | April
HRIS - EIS | HRIS EiS - MOM Koordinasi HRD & ICT 07 Mei 2024 | Pencapaian Bulanan Belum tercapture di penilaian - **New Feature** |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4542000% | 4542700% | 4544600% | 26 | Project Charter | Mei
HRIS - EIS | HRIS EiS - MOM Koordinasi HRD & ICT 07 Mei 2024 | Integrasi Nomor PTK di Web Recruitment agar terhubung dari proses Approval PTK sampai ke Recruitment => Noted: 1 PTK Bisa tercover untuk semua Lowongan |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4542000% | 4542700% | 4544600% | 26 | Project Charter | Mei
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
HRIS - EIS | HRIS EIS - Penilaian Karyawan Kerja (1-3) |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532000% | 4532200% | 4532700% | 7 | Project Charter | Januari
Waterout | WaterOut Cheker - MOM Update Project OPR 03 April 2024 | 2. SPS In checker ketika sudah di input masih tampil bkb nya. | Update Mom | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4539700% | 4540100% | 4541500% | 18 | Project Existing | April
Waterout | WaterOut Cheker - MOM Update Project OPR 03 April 2024 | 1. Disable select option di menu sps checker out (khusus untuk karton) | Update Mom | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4539700% | 4540100% | 4541500% | 18 | Project Existing | April
Waterout | WaterOut Cheker - MOM Update Project OPR 03 April 2024 | Kolom Product Name di waterout batch number viewnya terlalu kecil | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4539700% | 4540100% | 4541500% | 18 | Project Existing | April
Waterout | WaterOut Cheker - MOM Update Project OPR 03 April 2024 | Penginputan Batch Number antar depo belum ada | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4539700% | 4540100% | 4541500% | 18 | Project Existing | April
Waterout | Issue Waterout - Alam Sutera |  |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4531500% | 4531800% | 4531500% | 0 | Project Existing | Januari
Waterout | WaterOut Cheker - MOM Update Project OPR 03 April 2024 | Exclude Batch number jika ada karton / jika produk karton tidak tampil inputan batch number | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4539700% | 4540100% | 4541500% | 18 | Project Existing | April
MDBA | MDBA Entry - Update NOO (Approval Segment by ICT) |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4539700% | 4539900% | 4540400% | 7 | Project Existing | April
MDBA | MDBA BI Portal - Tampilan detail retur kosong |  |  | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4537900% | 4538100% | 4539900% | 20 | Project Existing | Maret
MDBA | MDBA RTG - BA SPV Delivery | 2. View Status hanya ada di MDBA Spv Delivery dan RTG Security |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4554400% | 4554700% | 4538700% | -157 | Project Charter | September
MDBA | MDBA RTG - BA SPV Delivery | 1. DI MDBA RTG Spv tampilkan History Armada Rusak yang sudah upload BA |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4554400% | 4554700% | 4538700% | -157 | Project Charter | September
MDBA | MDBA RTG - BA SPV Delivery | 8. Validasi semua upload foto wajib format jpeg/jpg |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 7. Filter by tanggal error page di menu list RTG |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 6. Filter by tanggal error page di menu list RTG Fleet |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 5. Fitur search tidak bisa |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 4. Title belum sesuai |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 3. Pada saat melakukan pengajuan perbaikan, data tidak sesuai di list approval |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA BI Portal - Fix BI Portal |  | Update Feature | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4532900% | 4532900% | 4532900% | 0 | Project Existing | Februari
MDBA | MDBA RTG - BA SPV Delivery | 2. Button tidak perlu tidak bisa di klik |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | 1. Gambar/foto hasil upload sama semua |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | Tambahkan filter (Start Date & End Date) & (Depo untuk pusat) |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | Selesai pengerjaan perbaikan armada (After Perbaikan) Upload Gambar |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | Pengajuan proses perbaikan armada (Before Perbaikan) Upload BA & Upload Gambar |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
MDBA | MDBA RTG - BA SPV Delivery | List kerusakan armada RTG oleh security |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4538300% | 4538700% | 4538700% | 4 | Project Charter | April
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 6. Hasil print belum sesuai (Bobot KPI dan Realisasi blank) |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536600% | 4536900% | 4536600% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 5. Poin Pelanggaran belum sesuai |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536600% | 4536900% | 4536600% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 4. Data sudah lengkap, namun tidak bisa di submit |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536600% | 4536900% | 4536600% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 3. Tambahkan loading pada saat get data point 4 |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536600% | 4536900% | 4536600% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 2. Mandatory penginputan point 5 |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536300% | 4536900% | 4536600% | 3 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS Assessment - Penilaian Karyawan Point 1-5 | 1. Collapse Chekclist Penilaian Tidak Sesuai |  | New Project | Update Feature | Suryana Saputra | Complete | 100% | 4536300% | 4536900% | 4536600% | 3 | Project Charter | Maret
MDBA | MDBA Entry - Update NOO | 8. Metode Update NOO jika KTP sama |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 7. Pada saat update dan data lengkap, menampilkan alert "Harap lengkapi struktur pelanggan" |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 6. Pada saat update dan data lengkap, menampilkan alert "Harap isi kategori pelanggan" |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 5. List approval yang sudah dilakukan approve/non approve masih tampil |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 4. Table struktur pelanggan field shiptoid blank di dms |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
Waterout | WaterOut Checker - Batch Number | Out Gallon | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4534200% | 4534500% | 4536900% | 27 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Out SPS | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Penambahan batchnumber di setiap SKU | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Format input batchnumber diganti tipe date | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Penambahan kolom asal pabrik | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Penambahan input batchnumber di fitur IN SPS | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Penambahan input batchnumber di fitur Antardepo SPS (Pengirim & Penerima) | New Feature | New Project | New Feature | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Required field di setiap multiple batchnumber (Galon) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Tambahkan alert jika ada kolom multiple batchnumber yang kosong |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Required field di setiap multiple (SPS IN) |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Sesuaikan format insert jika lebih dari 1 batchnumber di kolom batchnumber |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Tambahkan intitemnumber di tabel tbl_det_bkbsps |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Redirect jika gagal di simpan, di menu OUT SPS AntarDepo dan IN SPS AntarDepo |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Produk id di tbl outbatchnumber tidak sesuai dengan intnumber produk |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Intnumber produk di tbl inbatchnumber tidak sesuai dengan |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Multiple tidak bisa lebih dari 2 |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
Waterout | WaterOut Checker - Batch Number | Dropdown text menggunakan A-Z pada batch number |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4532900% | 4534500% | 4536900% | 40 | Project Charter | Februari
MDBA | MDBA Entry - Update NOO | 3. Saat Approval NOO "error page" |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 2. Saat update NOO loading, bugs di alamat tagih |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
MDBA | MDBA Entry - Update NOO | 1. Pengajuan sudah di approve namun masih tampil alert "Perubahan belum disetujui" |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4535100% | 4535700% | 4539800% | 47 | Project Existing | Februari
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Tambahkan satuan pada target KPI | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534500% | 4559600% | 255 | Project Existing | Februari
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Point Disiplin (Surat Peringatan) Coaching diubah menjadi Surat Teguran | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534500% | 4559600% | 255 | Project Existing | Februari
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Point setiap kolom | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534500% | 4559600% | 255 | Project Existing | Februari
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Untuk tujuan penilaian perpanjangan kontrak karyawan di tambahkan select option (3, 6, 12 Bulan) | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534500% | 4559500% | 254 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 7. Tampilkan kolom start date & end date di admin |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 6. Jika end date lebih dari tanggal yang di tetapkan masih tampil job di company profile |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 5. Chart dibuatkan 1 page saja ketika print |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 4. Sweet alert setelah isi test kemampuan verbal tidak ada |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 3. List hasil psikotest descending berdasarkan yang terbaru |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 2. Test kemampuan verbal belum ada hasil reportnya di menu HRD |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | 1. Redirect di setiap test setelah pengerjaan belum sesuai |  | Fixing Bugs | Fixing Bugs | Suryana Saputra | Complete | 100% | 4537000% | 4537000% | 4537000% | 0 | Project Charter | Maret
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Untuk Upload Design Poster bisa di buat setting tanggal masa berlaku poster tesebut | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4560100% | 260 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Untuk Line Chart DISC di buat pdf tarikan reportnya | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4560200% | 261 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Hasil DISC hanya di munculkan CHGnya saja Dan di tambahkan detail chart nya | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4560100% | 260 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Waktu pengerjaan Test IV Kemampuan Verbal 15 Menit | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4559600% | 255 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Untuk Soal Benar & Salah di ganti dengan soal Aritmatika | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4559600% | 255 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Test IV Kemampuan Verbal di buat Pilihan Ganda yang di buatkan oleh team HR | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4559800% | 257 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS EiS - MOM Meeting HR 16 Feb 2024 | Untuk Soal ketelitian 2 terkait aritmatika di rubah menjadi ketelitian 1 | Update Mom | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4534100% | 4534600% | 4562700% | 286 | Project Existing | Februari
MDBA | MDBA SO Pabrikan - Proses Pembuatan DO (Fixing Bugs) |  | decAmount tidak terbaca apabila ada produk Jambot pada DO | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4533700% | 4533700% | 4533700% | 0 | Project Existing | Februari
HRIS Recruitment - Psikotes | HRIS Recruitment - Psikotes | Detail Hasil Pisikotes |  | New Project | New Feature | Suryana Saputra | Complete | 100% | 4533800% | 4534200% | 4534200% | 4 | Project Charter | Februari
Waterout | WaterOut Checker - BKB Mix Produk |  | Update Feature | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4533100% | 4533100% | 4533100% | 0 | Project Existing | Februari
MDBA | MDBA Canvasser - Tunning Proses Surat Tugas (Non Rute) |  | Update Feature | Tunning | Update Feature | Suryana Saputra | Complete | 100% | 4533400% | 4533500% | 4533400% | 0 | Project Existing | Februari
WBS | WBS - Desk Audit | Timeline Tracking Pelaporan |  | New Project | New Feature | Suryana Saputra | In Progress | 80% | 4580000% | Rab 6/25/25 | 4580200% | 2 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | Choose Category and PIC |  | New Project | New Feature | Suryana Saputra | In Progress | 80% | 4579200% | Kam 5/15/25 | 4579200% | 0 | Project Charter | Mei, 2025
WBS | WBS - SPV / ASMAN IA | Timeline Tracking Pelaporan |  | New Project | New Feature | Suryana Saputra | In Progress | 80% | 4579000% | Rab 5/14/25 | 4579100% | 1 | Project Charter | Mei, 2025
MDBA | MDBA Entry - Print DO Blank |  |  | Tunning | Update Feature | Suryana Saputra | In Progress | 50% | 4565700% | - | - | #VALUE! | Project Existing | Februari 2025
MDBA | MDBA CRL - Penambahan produk KIT |  |  | Tunning | Update Feature | Suryana Saputra | In Progress | 80% | 4551600% | 4552200% | - | #VALUE! | Project Existing | Agustus
HRIS - EIS | Interview online - Tahap 2 | hasil interview |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | seting interview |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | hasil interview |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | form interview |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | jadwal interview |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | rekomendasi kandidat |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | Interview online - Tahap 2 | login |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4571200% | 4571300% | - | #VALUE! | Project Charter | Februari 2025
MDBA | MDBA RTG - BA SPV Delivery | 3. backend update status to hh rtg |  | New Project | Update Feature | Suryana Saputra | Need Review | 90% | 4554400% | 4554700% | - | #VALUE! | Project Charter | September
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Approval penilaian karyawan dilakukan 2 layer mengikuti struktur approval HRD | Update Mom | Tunning | Update Feature | Suryana Saputra | On Hold | 0% | 4534100% | - | - | #VALUE! | Project Existing | Februari
HRIS - EIS | Penilaian Karyawan - MOM Meeting | Data tahun 2023 penilaian di import untuk menjadi data history dari mbk dian | Update Mom | Tunning | Update Feature | Suryana Saputra | On Hold | 0% | 4534100% | - | - | #VALUE! | Project Existing | Februari
Repot & Dashboard | Update MOM Meeting Be Weekly Coordination HRD & ICT 011025 | Pada penilaian end year setiap point I-V dibuat disable, jika point sebelumnya belum di simpan maka point berikutnya tidak dapat di isi atau disable, Agar akumulasi nilai tidak bisa di edit |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 4593200% | 4594700% | - | #VALUE! | Project Existing | Oktober, 2025
Mobile RTG Security | RTG Security - New Feature BA Digital | API view dan Download BA |  | Tunning | New Feature | Suryana Saputra | Open | 0% | 4590900% | 4594100% | - | #VALUE! | Project Existing | September, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | SPV QMS & QMS Staff cuma bisa lihat detail aja |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 13/010/2025 | - | - | #VALUE! | Project Existing | Oktober, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Hilangin button revisi di login (Kepala Dept, SPV QMS, QMS Staff, GM |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 13/010/2025 | - | - | #VALUE! | Project Existing | Oktober, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Tambahkan jenis internal dan external |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 13/010/2025 | - | - | #VALUE! | Project Existing | Oktober, 2025
IM Digital (Number Latter) | New Apps QMS - Number Letter | Hilangkan privillege SPV Dept, Pengajuan langsung melakui KADEPT |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 13/010/2025 | - | - | #VALUE! | Project Existing | Oktober, 2025
MDBA | MDBA - Tambahkan alamat pada hasil cetakan DO Blank dengan Customer(on hold) |  |  | Tunning | Update Feature | Suryana Saputra | Open | 0% | 4581100% | - | - | #VALUE! | Project Existing | Juni, 2025
Waterout | WATEROUT - Fixing bugs waterout Checker & SCR | In | Sps | Fixing Bugs | Fixing Bugs | Suryana Saputra | Open | 0% | 4573000% | 4573300% | - | #VALUE! | Project Existing | Maret 2025
E-Learning | E-Learning - Tahap 2 | Standarisasi kompetensi VS pelatihan (Template dari HR) |  | New Project | Update Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
E-Learning | E-Learning - Tahap 2 | Auto history data pelatihan jika lulus ke EiS |  | New Project | Update Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
E-Learning | E-Learning - Tahap 2 | Detail perjabatan (NIK) jika jabatan tertentu (dibagi bertahap) |  | New Project | Update Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | E-KPI Form Penilaian Karyawan (Form-07 HRD) | Download hasil form penilaian (Format dari HR) |  | New Project | New Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | E-KPI Form Penilaian Karyawan (Form-07 HRD) | Approval 6 Tingkat |  | New Project | New Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | E-KPI Form Penilaian Karyawan (Form-07 HRD) | Form penilaian PKWT |  | New Project | New Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
HRIS - EIS | E-KPI Form Penilaian Karyawan (Form-07 HRD) | Form penilaian Mutasi & Rotasi |  | New Project | New Feature | Suryana Saputra | Open | 0% | - | - | - | #VALUE! | Project Charter | Februari 2025
MDBA | MDBA - Note Implementasi (SRG, PLT, LDN, KDY) | Tambahkan alamat pada hasil cetakan DO Blank dengan Customer |  | Tunning | Update Feature | Suryana Saputra | Open | 0% |  |  |  | 0 | Project Existing | -
Waterout | WaterOut - Exiting Task (finishing) | Next Update New Feature Mobile Driver Apps Scan Barcode By Driver pada saat **IN/OUT** |  | Tunning | New Feature | Suryana Saputra | Ready To Production | 95% | 4539700% | 4540100% | - | #VALUE! | Project Existing | April
Waterout | WaterOut - Exiting Task (finishing) | Pengerluaran NON STD hanya BKB saja |  | Tunning | Update Feature | Suryana Saputra | Ready To Production | 95% | 4539700% | 4540100% | - | #VALUE! | Project Existing | April
Waterout | WaterOut - Exiting Task (finishing) | MDBA Depo 1 siklus parametermya wateroutnya diambil dari STD |  | Tunning | Update Feature | Suryana Saputra | Ready To Production | 95% | 4539700% | 4540100% | - | #VALUE! | Project Existing | April
Waterout | WaterOut - Exiting Task (finishing) | Transaksi Waterout Security di Hilangkan all depo |  | Tunning | Update Feature | Suryana Saputra | Ready To Production | 95% | 4539700% | 4539700% | - | #VALUE! | Project Existing | April

## Hafidz (hidden)
Details for TC - Assigned to: Hafid Bachtiar
Module | Milestone Card | Feature / Task | Description | Category | Category Feature | Assigned to | Status | Progress | Start Date | Due Date | Complete Date | Days | Type Project | Monthly
Design Graphic | Material Design UI & UX - Kurir Versi Web | Overlay Detail Items Received |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | Items Received |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | Overlay Detail History Request |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | History Request |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | On Progress |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | Overlay Success New Request |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | New Request |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Material Design UI & UX - Kurir Versi Web | Homepage |  |  |  | Hafidz Bachtiar | Complete | 100% | 4593800% | 4594000% | 4594000% | 2 | Project Existing | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Update Status Armada Distribusi | Dashboard Distribution Secondary Cycle | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4594000% | 4594000% | 4594000% | 0 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Laporan Ritase dan Volume | Dashboard Distribution Secondary Cycle | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4594000% | 4594000% | 4594000% | 0 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Report Loading Sore Group Team | Dashboard Distribution Secondary Cycle | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4594000% | 4594000% | 4594000% | 0 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Report Loading Sore | Dashboard Distribution Secondary Cycle | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4594000% | 4594000% | 4594000% | 0 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Produktifitas Armada Distribusi | Dashboard Distribution Secondary Cycle | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4594000% | 4594000% | 4594000% | 0 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Pengajuan Perbaikan | List RTG | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Foto BA | List RTG | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Foto Kerusakan | List RTG | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | List RTG Perbaikan | List RTG | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Login | List RTG | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Penyelesaian Repair | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | After Repair | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Before Repair | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | List Perbaikan / Status Progress | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | List Perbaikan | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595200% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface Distribution Secondary Cycle (DSC) | Login | List Perbaikan | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4592200% | 4595500% | 4593900% | 17 | Project Charter | Oktober, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Cashier Financial Report / Detail |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Cashier Financial Report / History |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Cashier Financial Report / Preview |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Cashier Financial Report |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Print Report |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design - User Interface MDBA Cash Flow | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4591800% | 4591800% | 4591800% | 0 | Project Charter | September, 2025
Design Graphic | Design September | 21 September : Hari Perdamaian Internasional |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4590200% | 4590200% | 4590200% | 0 | Project Existing | September, 2025
Design Graphic | Design September | 9 September : Hari Olah Raga Nasional |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4590100% | 4590100% | 4590100% | 0 | Project Existing | September, 2025
Design Graphic | Design September | 5 September : Maulid Nabi Muhammad SAW |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4588100% | 4588100% | 4588100% | 0 | Project Existing | Agustus, 2025
Design Graphic | Design Agustus | 17 Agustus : Proklamasi Kemerdekaan |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4588000% | 4588000% | 4588000% | 0 | Project Existing | Agustus, 2025
Design Graphic | Design Agustus | 14 Agustus : Hari Pramuka |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4587700% | 4587700% | 4587700% | 0 | Project Existing | Agustus, 2025
Design Graphic | Design Agustus | 8 Agustus : HUT ASEAN |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4587400% | 4587400% | 4587400% | 0 | Project Existing | Agustus, 2025
Design Graphic | Design Juli | 23 Juli : Hari Anak Nasional |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4586000% | 4586000% | 4586000% | 0 | Project Existing | Juli, 2025
Design Graphic | Design Juli | 17 Juli : Hari Keadilan Internasional |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4584100% | 4584100% | 4584100% | 0 | Project Existing | Juli, 2025
Design Graphic | Design Juli | 12 Juli : Hari Koperasi Nasional |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4584100% | 4584100% | 4584100% | 0 | Project Existing | Juli, 2025
Design Graphic | Design Graphic | 1 Juli : Hari Bhayangkara |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4583200% | 4583200% | 4583200% | 0 | Project Existing | Juni, 2025
Design Graphic | Design Juni | 27 Juni : 1 Muharam Tahun Baru Islam 1447 Hijriah |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4582000% | 4582000% | 4582000% | 0 | Project Existing | Juni, 2025
Design Graphic | Design Juni | 6 Juni : Iduladha 1446 Hijriah |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4581300% | 4581300% | 4581300% | 0 | Project Existing | Juni, 2025
GL | TIMELINE NEW GL - FIXING CASE GL | PEMISAHAN MANUAL BOOK |  | Tunning | Addhock | Hafidz Bachtiar | Complete | 100% | 4587600% | 4587600% | 4587600% | 0 | Project Existing | Agustus, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | History Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584500% | 4584600% | 4584600% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Approval Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584400% | 4584500% | 4584500% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | List Data Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584300% | 4584400% | 4584400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | QMS SPV |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584300% | 4584500% | 4584500% | 2 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | History Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584100% | 4584200% | 4584200% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Approval Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4584000% | 4584100% | 4584100% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | List Data Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583900% | 4584000% | 4584000% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | QMS Staff |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583900% | 4584200% | 4584200% | 3 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Form Pengajuan Revisi No. Lama |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583400% | 4583500% | 4583500% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | History Pengajuan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583300% | 4583400% | 4583400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Form Pengajuan No. Baru |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583200% | 4583300% | 4583300% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | List Data |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583200% | 4583200% | 4583200% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | All User |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583200% | 4583500% | 4583500% | 3 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Tampilan Awal |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583100% | 4583100% | 4583100% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX IM Digital (Number Latter) | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4583100% | 4583100% | 4583100% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Submit Driver |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585800% | 4585800% | 4585800% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Edit Driver |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585700% | 4585700% | 4585700% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | History Driver |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585600% | 4585600% | 4585600% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Driver Variant |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585500% | 4585500% | 4585500% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Vehicle Variant |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585400% | 4585400% | 4585400% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Home Page |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585300% | 4585300% | 4585300% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Driver Management | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4585200% | 4585200% | 4585200% | 0 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Choose Category and PIC |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4579500% | 4576200% | 4579600% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Investigasi Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4579300% | 4576200% | 4579400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Timeline Tracking Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4579100% | 4576200% | 4579200% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | List Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4578900% | 4576200% | 4579000% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Form Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4578700% | 4576200% | 4578800% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4578500% | 4576200% | 4578600% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | SPV / IA Asman |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4578300% | 4576200% | 4578400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Approval Screening Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4578100% | 4576200% | 4578200% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Screening Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4577900% | 4576200% | 4578000% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Timeline Tracking Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4577700% | 4576200% | 4577800% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | List Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4577500% | 4576200% | 4577600% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Form Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4577300% | 4576200% | 4577400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4577100% | 4576200% | 4577200% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Desk Audit |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4576900% | 4576200% | 4577000% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Timeline Tracking Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4576700% | 4576200% | 4576800% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | List Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4576500% | 4576200% | 4576600% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Form Pelaporan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4576300% | 4576200% | 4576400% | 1 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Whistle Blowing System | Informant |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4576200% | 4576200% | 4576200% | 0 | Project Charter | Juli, 2025
Design Graphic | Video tutorial AQUA Tebar Untung - SND |  |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4579800% | 4581100% | 4581100% | 13 | Project Existing | Mei, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Detail Items Received |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4537300% | 4537300% | 4585400% | 481 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Items Received |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4537200% | 4537200% | 4585400% | 482 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Create Order Success |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4537100% | 4537100% | 4585400% | 483 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Create New Order |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4537000% | 4537000% | 4585400% | 484 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | History Order/Request |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536900% | 4536900% | 4585400% | 485 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | On Progress |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536800% | 4536800% | 4585400% | 486 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Update Detail New Order |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536700% | 4536700% | 4585400% | 487 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Foto Barang |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536600% | 4536600% | 4585400% | 488 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Upload Foto |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536500% | 4536500% | 4585400% | 489 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Detail New Order |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536400% | 4536400% | 4585400% | 490 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | New Order List |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536300% | 4536300% | 4585400% | 491 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Home Page |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536200% | 4536200% | 4585400% | 492 | Project Charter | Juli, 2025
Design Graphic | Material Design UI & UX - Mobile Kurir Apps | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4536100% | 4536100% | 4585400% | 493 | Project Charter | Juli, 2025
Design Graphic | Update MOM Meeting Update New Portal TVIP Group 261124 | Notifikasi untuk alert masa berlaku SMKPO dan halal |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4565900% | 4566600% | 4572000% | 61 | Project Existing | Januari 2025
Design Graphic | Update MOM Meeting Update New Portal TVIP Group 261124 | Tambahkan Halal Sama seperti SMKPO |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4565900% | 4566600% | 4572000% | 61 | Project Existing | Januari 2025
Design Graphic | Update MOM Meeting Update New Portal TVIP Group 261124 | Facebook, Instagram, Linked In, Jobstreet di hilangkan dari More Info hanya email saja |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4565900% | 4566600% | 4572000% | 61 | Project Existing | Januari 2025
Design Graphic | Update MOM Meeting Update New Portal TVIP Group 261124 | Untuk Isi MRT TBK Tidak perlu di show QO |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4565900% | 4566600% | 4572000% | 61 | Project Existing | Januari 2025
Design Graphic | Update MOM Meeting Update New Portal TVIP Group 261124 | Tambahkan Portal NOVA |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4565900% | 4566600% | 4572000% | 61 | Project Existing | Januari 2025
Design Graphic | Detail Kunjungan | PDF / BERITA ACARA VERIFIKASI & STOK OPNAME GALON | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Kunjungan | Detail Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Kunjungan | Detail Dispenser Accordion | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Kunjungan | List Dispenser dengan Catatan | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Kunjungan | List Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Histori Kunjungan |  | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Perhatian | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Isi Keterangan | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Berhasil | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Apakah Anda yakin? | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Belum Isi | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser / Selesai | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Berhasil Disimpan | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Cek Fisik Dispenser Dengan Catatan | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Cek Fisik Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser TIDAK | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser ADA / Manual Input Seri | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser ADA | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Fisik Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan / Verifikasi Dispenser | Verifikasi Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | PDF / BERITA ACARA VERIFIKASI & STOK OPNAME GALON |  | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Beranda | List Kunjungan Terisi | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Kunjungan | Verifikasi Galon | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Histori Kunjungan | Histori Kunjungan / Filter | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan | Verifikasi Galon / Berhasil Disimpan | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan | Verifikasi Galon / Galon Pinjam Kosong | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan | Verifikasi Galon | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Form Kunjungan | Verifikasi Galon/Dispenser | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Authentication | Logout | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Authentication | Login | Design UI & UX | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4556900% | 4557300% | 4557300% | 4 | Project Charter | Oktober
Design Graphic | Detail Profile | Data Informasi Karyawan NIk, Nama, & Jabatan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | History Cheklist RTG | Summry Penilaian Bobot |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | History Cheklist RTG | Detail History Transaksi Cheklist RTG |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist TIRE / BAN |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist SUSPENSION |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist BRAKE AND CLUTCH |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist ENGINE |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist ELECTRICAL |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist BODY |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist TOOLS |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Cheklist DOCUMENT |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Form Cheklist RTG | Pilih Nopol |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Logout | Untuk Keluar dari aplikasi |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Login | Untuk masuk ke aplikasi |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4529000% | 4531000% | 4531000% | 20 | Project Charter | 2023 Des
Design Graphic | Update MOM Meeting Review Design Mobile Teknisi Dispenser 23 Oktober 2024 | Semua Select Option diganti dengan Radio Button |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4558800% | 4559600% | 4565000% | 62 | Project Charter | Oktober
Design Graphic | Update MOM Meeting Review Design Mobile Teknisi Dispenser 23 Oktober 2024 | Untuk Status Verfikasi di buat radio button untuk meminimalisir terjadinya salah input |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4558800% | 4559600% | 4565000% | 62 | Project Charter | Oktober
Design Graphic | Update MOM Meeting Review Design Mobile Teknisi Dispenser 23 Oktober 2024 | Print Out Hasil kunjungan berupa PDF di ambil dari Detail Kunjungan Perpelanggan |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4558800% | 4559600% | 4565000% | 62 | Project Charter | Oktober
Design Graphic | Update MOM Meeting Review Design Mobile Teknisi Dispenser 23 Oktober 2024 | Pada saat form kunjungan di tambahkan pilih depo (halaman awal) |  | Tunning | Design | Hafidz Bachtiar | Complete | 100% | 4558800% | 4559600% | 4565000% | 62 | Project Charter | Oktober
Design Graphic | Design Mobile Opname Sparepart Bulanan | List Validasi Stock Sparepart - Pass |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | List Validasi Stock Sparepart - Invalid |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Filter Range by Tanggal |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Filter Lokasi Gudang |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Info Profile |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Data Karyawan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Summary Stok Opname Bulanan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | End Date |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Start Date |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | Apply Stok |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | List Stok Fisik |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Design Mobile Opname Sparepart Bulanan | List Outstanding |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4534200% | 4534400% | 4534400% | 2 | Project Charter | Februari
Design Graphic | Form Garuda Store | List Hasl Survei |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Detai Hasil Survei |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Hasil Survei |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Isi stock rak reguler |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Isi stock white chiller |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Foto Survei (Foto Outlet, Shop Blind, Poster, Blue Chiler, White Chiler) |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Form Garuda Store | Tambah Survei (+) |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531000% | 4531800% | 4531800% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | MDBA - List Data Master Surat Tugas |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | MDBA - Upload Master Surat Tugas |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | MDBA - Proses Surat Tugas |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Detail Profile |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Konfigurasi Pengiriman |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Informasi Device |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Realisasi Pengiriman |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Selesai Perjalanan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Detail Istirahat |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Laporan Penjualan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Summary Kunjungan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Scan Barcode |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Calon Pelanggan Baru |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Daftar Kunjungan |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Logout |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Preseller AHS & SPV Channel | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531700% | 4531700% | 1 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Input Market Insight (Market Activity, Competitor Activity, FeedBack Outlet ) |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Listing Toko |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Pilih Segemnt |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Pilih Depo |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Form Daily Activity SND |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Detail Profile |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Logout |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531600% | 4531800% | 4531800% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Daily Activity SND | Login |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531500% | 4531700% | 4531700% | 2 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Monitoring PIC Pengerjaan Job Order | Monitoring (Open, On Progress, Closed) | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Monitoring PIC Pengerjaan Job Order | Card Monitoring PIC Pengerjaan Job Order | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Form MHC Pool & Depo | Penambahan Kategori "Normal" Pada Cheklist Engine | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Logout |  | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Login | Nama Mekanik | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Login | Foto Mekanik | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Design Mobile Mekanik Apps Multi User | Login | Multi Mekanik | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4531800% | 4532600% | 4532600% | 8 | Project Charter | Januari
Design Graphic | Detail Profile | Data Informasi Karyawan NIk, Nama, & Jabatan | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | History RTG | Detail History Transaksi RTG | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Foto Kerusakan + Opsi (Upload BA) | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Foto Samping Kiri + Opsi (Depan + Belakang) | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Foto Samping Kanan + Opsi (Depan + Belakang ) | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Foto Tampak Belakang | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Foto Tampak Depan | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Pilih Driver | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Pilih Nopol | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Form RTG | Pilih Jenis Armada + Opsi (L300 / Engkel Double) | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Logout | Untuk Keluar dari aplikasi | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Login | Untuk masuk ke aplikasi | Fleet - Mobile Security RTG Daily | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4532800% | 4534300% | 4534300% | 15 | Project Charter | Februari
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tambahkan Radius Performance (Target, In Radius, Out Radius) | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Hilangkan AO Performance | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Mobile Preseller AHS & SPV Channel | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tambahkan Target Galon 1200, SPS 100 Per Hari | Update Design Mobile SFA AHS Preseller | New Project | Update Feature | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Kolom qty expired & qty display di hilangkan | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | History penjualan tambahkan average | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | History penjualan tambahkan grouping berdasarkan Galon dan SPS range waktu 3 bulan | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Biodata Calon Pelanggan -> Biodata Prospek NOO | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Produk yang dijual saat ini tambahkan jawaban "RSFT" | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tambahkan pertanyaan "Memiliki mesin isi ulang (RSFT)? Ya/Tidak" | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Pelanggan Lama -> Rute Pelanggan | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Calon Pelanggan Baru -> Prospek NOO | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Tambahkan fitur extra call/luar rute | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Pelanggan lama - Pelanggan | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Design Graphic | Update MOM Meeting Be Weekly Coordination ICT & SND 190724 | Hilangkan inputan KM | Update Design Mobile SFA AHS Preseller | New Project | Design | Hafidz Bachtiar | Complete | 100% | 4549300% | 4549900% | 4560000% | 107 | Project Charter | Juli
Repot & Dashboard | Update Dashboard & Design ModuST Archictecture 'ERP Orbit Data' | Update Design Erp |  | Tunning | Update Feature | Hafidz Bachtiar | Complete | 100% | 4540800% | 4541100% | 4541100% | 3 | Project Existing | April
MDBA | Video Tutorial - Driver Apps canvasser |  | Addhock | Tunning | Addhock | Hafidz Bachtiar | Complete | 100% | 4532900% | 4533100% | 4533500% | 6 | Project Existing | Februari